## 工作表1
Resources Plan
| Resurce Count | Man Day | Hiring Period | Cost
Patrick -BA | 1 | 15 | 2025/11/24 - 2026/01/12
Kent | 1 | 67 | 2025/12/12 - 2026/08/06 | 0
BA/Testing | 1 | 136 | 2025/12/31 - 2026/08/17 | 0
FrontEnd | 1 | 58 | 2025/12/24 - 2026/07/23
New AP Lead | 1 | 72 | 2026/01/21 - 2026/08/14

## Project Planning - B
DMS Development
| TOTAL TASKS | 169 |  |  |  | DURATION | 267 |  | Overall Progress
| Completed | 0 |  |  |  | START | 2025-11-24 |  |  |  | #REF! | Team Member | FTE | Cost / Monthly |  | Difficulty Level | MD
| In progress | 9 |  |  |  | FINISH | 2026-08-17 |  |  |  | 348 | Kent | 1 |  | 1 year | Low | 1-2
| Not Started | 160 | [9 empty] | BA/Testing | 1 | 152250 | 1827000 | Mid | 3-5
|  |  | New SA and Engineer training |  |  |  | 1/5/2026 - 1/9/2026 |  | 100% |  |  | AP Lead | 1 |  | Onboard after Chinese New Year | High | 6-8
[12 empty] | FrontEnd1 | 1 | 152250 | 1827000
[12 empty] | Patrick-BA | 0.5
SPRINT | EPIC | FEATURE | TASKS | STORIES | Difficulty Level | RESPONSIBLE | Man Day Required | START | FINISH | DURATION | STATUS
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Detail Requirement Analysis | Mid | Patrick -BA | 3 | 2025-11-24 | 2025-12-02 | 6 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Document Detail Requirement | Mid | Patrick -BA | 3 | 2025-12-03 | 2025-12-11 | 6 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Mid | Kent | 3 | 2025-12-12 | 2025-12-17 | 3 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | High | Kent | 5 | 2025-12-18 | 2025-12-25 | 5 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Low | Kent | 2 | 2025-12-26 | 2025-12-30 | 2 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Testing | Data Related QA - unit testing | Mid | BA/Testing | 3 | 2025-12-31 | 2026-01-05 | 3 | Not Started
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Balance Detail Requirement Analysis | Low | Patrick -BA | 1.5 | 2025-12-12 | 2025-12-17 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Document Detail Requirement | Low | Patrick -BA | 1.5 | 2025-12-18 | 2025-12-23 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 1 | Low | FrontEnd | 1 | 2025-12-24 | 2025-12-25 | 1 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 2 | High | Kent | 7 | 2025-12-31 | 2026-01-09 | 7 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Testing | Maintain Distributable Balance QA - unit testing | Mid | BA/Testing | 3 | 2026-01-12 | 2026-01-15 | 3 | Not Started
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Detail Requirement Analysis | Low | Patrick -BA | 1.5 | 2025-12-24 | 2025-12-29 | 3 | In progress
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Document Detail Requirement | Low | Patrick -BA | 1.5 | 2025-12-26 | 2025-12-31 | 3 | In progress
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 1 | Mid | FrontEnd | 4 | 2026-01-01 | 2026-01-07 | 4 | Not Started
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 2 | Mid | Kent | 4 | 2026-01-12 | 2026-01-16 | 4 | Not Started
Sprint 5 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Testing | Domestic Dividend Information Inquiry QA - unit testing | Low | BA/Testing | 2 | 2026-01-19 | 2026-01-21 | 2 | Not Started
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Detail Requirement Analysis | Low | Patrick -BA | 1.5 | 2026-01-01 | 2026-01-06 | 3 | In progress
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Document Detail Requirement | Low | Patrick -BA | 1.5 | 2026-01-07 | 2026-01-12 | 3 | In progress
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 1 | Mid | FrontEnd | 4 | 2026-01-08 | 2026-01-14 | 4 | Not Started
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 2 | Mid | Kent | 4 | 2026-01-19 | 2026-01-23 | 4 | Not Started
Sprint 6 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Testing | Upload Domestic Dividend Composition Info to EC QA - unit testing | Low | BA/Testing | 1 | 2026-01-26 | 2026-01-26 | 1 | Not Started
Sprint 1 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | Mid | BA/Testing | 3 | 2026-01-13 | 2026-01-15 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | Mid | BA/Testing | 3 | 2026-01-16 | 2026-01-20 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Mid | New AP Lead | 4 | 2026-01-21 | 2026-01-26 | 4 | Not Started
Sprint 3 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Mid | New AP Lead | 4 | 2026-01-27 | 2026-01-30 | 4 | Not Started
Sprint 4 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Low | New AP Lead | 2 | 2026-02-02 | 2026-02-03 | 2 | Not Started
Sprint 5 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Testing | Data Related QA - unit testing | Mid | BA/Testing | 3 | 2026-02-04 | 2026-02-06 | 3 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement Analysis | Low | BA/Testing | 2 | 2026-01-21 | 2026-01-22 | 2 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement | Low | BA/Testing | 2 | 2026-01-23 | 2026-01-23 | 1 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 1 | Low | FrontEnd | 2 | 2026-01-27 | 2026-01-28 | 2 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 2 | High | New AP Lead | 8 | 2026-02-04 | 2026-02-13 | 8 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Testing | Mandate Client Information Maintenance QA - unit-testing | Low | BA/Testing | 2 | 2026-02-23 | 2026-02-24 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement Analysis | Low | BA/Testing | 2 | 2026-01-27 | 2026-01-28 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement | Low | BA/Testing | 2 | 2026-01-29 | 2026-01-30 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 1 | Low | FrontEnd | 2 | 2026-02-02 | 2026-02-03 | 2 | Not Started
Sprint 7 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 2 | High | Kent | 8 | 2026-02-02 | 2026-02-11 | 8 | Not Started
Sprint 8 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Testing | Mandate Contract Information Maintenance QA - unit-testing | Low | BA/Testing | 2 | 2026-02-25 | 2026-02-26 | 2 | Not Started
Sprint 6 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Analysis | Low | BA/Testing | 2 | 2026-02-02 | 2026-02-03 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Doc | Low | BA/Testing | 2 | 2026-02-09 | 2026-02-10 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 1 | Low | FrontEnd | 2 | 2026-02-11 | 2026-02-12 | 2 | Not Started
Sprint 8 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 2 | High | New AP Lead | 8 | 2026-02-23 | 2026-03-04 | 8 | Not Started
Sprint 9 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Testing | Mandate Subscription Data Entry QA - unit-testing | Low | BA/Testing | 2 | 2026-03-05 | 2026-03-06 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Analysis | Low | BA/Testing | 1 | 2026-02-27 | 2026-02-27 | 1 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Doc | Low | BA/Testing | 2 | 2026-03-02 | 2026-03-03 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 1 | Low | FrontEnd | 1 | 2026-03-04 | 2026-03-04 | 1 | Not Started
Sprint 10 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 2 | Mid | Kent | 3 | 2026-03-05 | 2026-03-09 | 3 | Not Started
Sprint 11 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Testing | Mandate Redemption Data Entry QA - unit-testing | Low | BA/Testing | 2 | 2026-03-10 | 2026-03-11 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | Low | BA/Testing | 1 | 2026-03-04 | 2026-03-04 | 1 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | Low | BA/Testing | 2 | 2026-03-09 | 2026-03-10 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | Low | FrontEnd | 2 | 2026-03-11 | 2026-03-12 | 2 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Low | New AP Lead | 2 | 2026-03-11 | 2026-03-12 | 2 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Testing | Mandate Fund NAV Inquiry QA - unit-testing | Low | BA/Testing | 2 | 2026-03-13 | 2026-03-16 | 2 | Not Started
Sprint 12 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | Low | BA/Testing | 1 | 2026-03-11 | 2026-03-11 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | Low | BA/Testing | 1 | 2026-03-12 | 2026-03-12 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | Low | FrontEnd | 1 | 2026-03-17 | 2026-03-17 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Mid | Kent | 3 | 2026-03-17 | 2026-03-19 | 3 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Testing | Mandate Fund NAV Inquiry QA - unit-testing | Low | BA/Testing | 1 | 2026-03-20 | 2026-03-20 | 1 | Not Started
Sprint 5 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement Analysis | Low | BA/Testing | 1 | 2026-03-17 | 2026-03-17 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement | Low | BA/Testing | 1 | 2026-03-18 | 2026-03-18 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 1 | Low | FrontEnd | 1 | 2026-03-23 | 2026-03-23 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 2 | Low | New AP Lead | 2 | 2026-03-23 | 2026-03-24 | 2 | Not Started
Sprint 7 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Testing | Subscription Details Report QA - unit-testing | Low | BA/Testing | 1 | 2026-03-25 | 2026-03-25 | 1 | Not Started
Sprint 7 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement Analysis | Low | BA/Testing | 2 | 2026-03-23 | 2026-03-24 | 2 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement | Low | BA/Testing | 2 | 2026-03-26 | 2026-03-27 | 2 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 1 | Mid | FrontEnd | 3 | 2026-03-30 | 2026-04-01 | 3 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 2 | Mid | New AP Lead | 5 | 2026-03-30 | 2026-04-07 | 5 | Not Started
Sprint 9 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Testing | Redemption Details Report QA - unit-testing | Low | BA/Testing | 1 | 2026-04-08 | 2026-04-08 | 1 | Not Started
Sprint 9 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement Analysis | Low | BA/Testing | 1 | 2026-03-30 | 2026-03-30 | 1 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement | Low | BA/Testing | 2 | 2026-03-31 | 2026-04-01 | 2 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 1 | Low | FrontEnd | 2 | 2026-04-02 | 2026-04-07 | 2 | Not Started
Sprint 11 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 2 | Mid | New AP Lead | 4 | 2026-04-08 | 2026-04-13 | 4 | Not Started
Sprint 12 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Testing | Mandate NAV Import Process (State Street) QA - unit-testing | Low | BA/Testing | 2 | 2026-04-14 | 2026-04-15 | 2 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement Analysis | Low | BA/Testing | 1 | 2026-04-02 | 2026-04-02 | 1 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement | Low | BA/Testing | 1 | 2026-04-09 | 2026-04-09 | 1 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 1 | Low | FrontEnd | 2 | 2026-04-10 | 2026-04-13 | 2 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 2 | Mid | New AP Lead | 3 | 2026-04-14 | 2026-04-16 | 3 | Not Started
Sprint 14 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Testing | Generate Mandate Subscription/Redemption Data QA - unit-testing | Low | BA/Testing | 1 | 2026-04-17 | 2026-04-17 | 1 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement Analysis | Low | BA/Testing | 2 | 2026-04-10 | 2026-04-13 | 2 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement | Low | BA/Testing | 2 | 2026-04-20 | 2026-04-21 | 2 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 1 | Low | FrontEnd | 2 | 2026-04-22 | 2026-04-23 | 2 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 2 | Mid | New AP Lead | 5 | 2026-04-22 | 2026-04-28 | 5 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Testing | Export Mandate Subscription/Redemption Data QA - unit-testing | Low | BA/Testing | 2 | 2026-04-29 | 2026-04-30 | 2 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement Analysis | Low | BA/Testing | 1 | 2026-04-22 | 2026-04-22 | 1 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement | Low | BA/Testing | 1 | 2026-04-23 | 2026-04-23 | 1 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 1 | Low | FrontEnd | 2 | 2026-04-24 | 2026-04-27 | 2 | Not Started
Sprint 18 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 2 | Mid | New AP Lead | 3 | 2026-04-29 | 2026-05-04 | 3 | Not Started
Sprint 19 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Testing | Generate SSB Mandate Subscription/Redemption Data QA - unit-testing | Low | BA/Testing | 1 | 2026-05-05 | 2026-05-05 | 1 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement Analysis | Low | BA/Testing | 2 | 2026-04-24 | 2026-04-27 | 2 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement | Low | BA/Testing | 2 | 2026-04-28 | 2026-05-04 | 2 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 1 | Mid | FrontEnd | 3 | 2026-05-05 | 2026-05-07 | 3 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 2 | Mid | New AP Lead | 5 | 2026-05-05 | 2026-05-11 | 5 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Testing | Export SSB Mandate Subscription/Redemption Data QA - unit-testing | Low | BA/Testing | 1 | 2026-05-12 | 2026-05-12 | 1 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Requirement Analysis | Low | BA/Testing | 1 | 2026-05-06 | 2026-05-06 | 1 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Data Requirement | Low | BA/Testing | 2 | 2026-05-07 | 2026-05-08 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 1 | Low | FrontEnd | 2 | 2026-05-11 | 2026-05-12 | 2 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 2 | Mid | Kent | 3 | 2026-05-12 | 2026-05-14 | 3 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Testing | Fund NAV Auto Import Process QA - unit-testing | Low | BA/Testing | 1 | 2026-05-15 | 2026-05-15 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Requirement Analysis | Low | BA/Testing | 1 | 2026-05-11 | 2026-05-11 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Data Requirement | Low | BA/Testing | 1 | 2026-05-13 | 2026-05-13 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 1 | Low | FrontEnd | 2 | 2026-05-14 | 2026-05-15 | 2 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 2 | Low | Kent | 2 | 2026-05-15 | 2026-05-18 | 2 | Not Started
Sprint 17 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Testing | Fund NAV Import Status Inquiry QA - unit-testing | Low | BA/Testing | 1 | 2026-05-19 | 2026-05-19 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement Analysis | Low | BA/Testing | 1 | 2026-05-18 | 2026-05-18 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement | Low | BA/Testing | 2 | 2026-05-20 | 2026-05-21 | 2 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 1 | Low | FrontEnd | 1 | 2026-05-22 | 2026-05-22 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 2 | Low | Kent | 2 | 2026-05-22 | 2026-05-25 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Testing | Calendar File QA - unit-testing | Low | BA/Testing | 1 | 2026-05-26 | 2026-05-26 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement Analysis | Low | BA/Testing | 2 | 2026-05-22 | 2026-05-25 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement | Low | BA/Testing | 2 | 2026-05-27 | 2026-05-28 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 1 | Low | FrontEnd | 2 | 2026-05-29 | 2026-06-01 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 2 | Low | Kent | 2 | 2026-05-29 | 2026-06-01 | 2 | Not Started
Sprint 19 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Testing | Payment Notice – Management Fee, Custody Fee QA - unit-testing | Low | BA/Testing | 1 | 2026-06-02 | 2026-06-02 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement Analysis | Low | BA/Testing | 1 | 2026-05-29 | 2026-05-29 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement | Low | BA/Testing | 1 | 2026-06-01 | 2026-06-01 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 1 | Low | FrontEnd | 1 | 2026-06-02 | 2026-06-02 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 2 | Low | Kent | 2 | 2026-06-02 | 2026-06-03 | 2 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Testing | Validation – Dividend Data QA - unit-testing | Low | BA/Testing | 1 | 2026-06-04 | 2026-06-04 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement Analysis | Low | BA/Testing | 1 | 2026-06-03 | 2026-06-03 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement | Low | BA/Testing | 1 | 2026-06-05 | 2026-06-05 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 1 | Low | FrontEnd | 1 | 2026-06-08 | 2026-06-08 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 2 | Low | Kent | 2 | 2026-06-08 | 2026-06-09 | 2 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Testing | Payment Notice – Dividend Distribution QA - unit-testing | Low | BA/Testing | 1 | 2026-06-10 | 2026-06-10 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement Analysis | Low | BA/Testing | 1 | 2026-06-08 | 2026-06-08 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement | Low | BA/Testing | 1 | 2026-06-09 | 2026-06-09 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 1 | Low | FrontEnd | 1 | 2026-06-10 | 2026-06-10 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 2 | Low | Kent | 2 | 2026-06-10 | 2026-06-11 | 2 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Testing | Payment Notice – Dividend Instruction Printing QA - unit-testing | Low | BA/Testing | 1 | 2026-06-12 | 2026-06-12 | 1 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Analysis | Low | BA/Testing | 1 | 2026-06-11 | 2026-06-11 | 1 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Doc | Low | BA/Testing | 1 | 2026-06-15 | 2026-06-15 | 1 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 1 | Mid | FrontEnd | 4 | 2026-06-16 | 2026-06-19 | 4 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 2 | Mid | New AP Lead | 4 | 2026-06-16 | 2026-06-22 | 4 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Testing | Mandate Data Generation Process QA - unit-testing | Low | BA/Testing | 2 | 2026-06-23 | 2026-06-24 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Analysis | Low | BA/Testing | 2 | 2026-06-16 | 2026-06-18 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Doc | Low | BA/Testing | 2 | 2026-06-25 | 2026-06-26 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 1 | Mid | FrontEnd | 3 | 2026-06-29 | 2026-07-01 | 3 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 2 | Mid | Kent | 5 | 2026-06-29 | 2026-07-03 | 5 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Testing | Mandate Data Maintenance Process QA - unit-testing | Low | BA/Testing | 2 | 2026-07-06 | 2026-07-07 | 2 | Not Started
Sprint 11 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Analysis | Low | BA/Testing | 1 | 2026-06-29 | 2026-06-29 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Doc | Low | BA/Testing | 1 | 2026-06-30 | 2026-06-30 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 1 | Low | FrontEnd | 1 | 2026-07-01 | 2026-07-01 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 2 | Low | New AP Lead | 2 | 2026-07-01 | 2026-07-02 | 2 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Testing | Subscription/Redemption Posting Details Report QA - unit-testing | Low | BA/Testing | 1 | 2026-07-08 | 2026-07-08 | 1 | Not Started
Sprint 12 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Analysis | Low | BA/Testing | 1 | 2026-07-09 | 2026-07-09 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Doc | Low | BA/Testing | 1 | 2026-07-10 | 2026-07-10 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 1 | Mid | FrontEnd | 3 | 2026-07-13 | 2026-07-15 | 3 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 2 | Mid | New AP Lead | 4 | 2026-07-13 | 2026-07-16 | 4 | Not Started
Sprint 14 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Testing | Mandate Contract Asset Movement Report QA - unit-testing | Low | BA/Testing | 2 | 2026-07-17 | 2026-07-20 | 2 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Analysis | Low | BA/Testing | 1 | 2026-07-13 | 2026-07-13 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Doc | Low | BA/Testing | 1 | 2026-07-14 | 2026-07-14 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 1 | Low | FrontEnd | 2 | 2026-07-15 | 2026-07-16 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 2 | Low | Kent | 2 | 2026-07-17 | 2026-07-20 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Testing | PAMS Inventory File Export QA - unit-testing | Low | BA/Testing | 1 | 2026-07-21 | 2026-07-21 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement Analysis | Low | BA/Testing | 1 | 2026-07-15 | 2026-07-15 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement | Low | BA/Testing | 1 | 2026-07-22 | 2026-07-22 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 1 | Low | FrontEnd | 1 | 2026-07-23 | 2026-07-23 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 2 | Mid | New AP Lead | 4 | 2026-07-23 | 2026-07-28 | 4 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Testing | Mandate Stock Stop-Loss Control Table QA - unit-testing | Low | BA/Testing | 1 | 2026-07-29 | 2026-07-29 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Analysis | Low | BA/Testing | 1 | 2026-07-23 | 2026-07-23 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Doc | Low | BA/Testing | 1 | 2026-07-24 | 2026-07-24 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | Development | Report - 基金規模報表查詢 - Development | Mid | Kent | 3 | 2026-07-27 | 2026-07-29 | 3 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | Testing | Report - 基金規模報表查詢 QA - unit-testing | Low | BA/Testing | 1 | 2026-07-30 | 2026-07-30 | 1 | Not Started
Sprint 22 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Analysis | Low | BA/Testing | 1 | 2026-07-31 | 2026-07-31 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Doc | Low | BA/Testing | 1 | 2026-08-03 | 2026-08-03 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | Development | Taiwan Ratings Reporting Data - Development | Mid | Kent | 3 | 2026-08-04 | 2026-08-06 | 3 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | Testing | Taiwan Ratings Reporting Data QA - unit-testing | Low | BA/Testing | 1 | 2026-08-07 | 2026-08-07 | 1 | Not Started
Sprint 23 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Analysis | Low | BA/Testing | 1 | 2026-08-10 | 2026-08-10 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Doc | Low | BA/Testing | 1 | 2026-08-11 | 2026-08-11 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | Development | Mutual Fund Asset Size Export Process - Development | Mid | New AP Lead | 3 | 2026-08-12 | 2026-08-14 | 3 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | Testing | Mutual Fund Asset Size Export Process - unit-testing | Low | BA/Testing | 1 | 2026-08-17 | 2026-08-17 | 1 | Not Started
Formulas:
FINISH = WORKDAY([START],[DURATION])
START = WORKDAY([FINISH, row above],1)

## Project Planning - A
DMS Development
| TOTAL TASKS | 199 |  |  | DURATION | 762 |  | Overall Progress |  |  | Team Member | FTE | Cost / Monthly | 1 year
| Completed | 2 |  |  | START | 2025-03-01 |  |  |  | 24 | Kent | 1
| In progress | 7 |  |  | FINISH | 2027-04-01 |  |  |  | 419 | AP Lead | 1
| Not Started | 191 | [8 empty] | FrontEnd1 | 1 | 152250 | 1827000
[8 empty] | 100% |  | 5.728% | Patrick-BA | 0.5
SPRINT | EPIC | FEATURE | TASKS | STORIES | RESPONSIBLE | Man Day Required | START | FINISH | DURATION | STATUS
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | BA | 3 | 2025-09-15 | 2025-09-18 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | BA | 3 | 2025-09-19 | 2025-09-24 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Kent | 5 | 2025-09-25 | 2025-10-02 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Kent | 5 | 2025-10-03 | 2025-10-10 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Kent | 5 | 2025-10-13 | 2025-10-20 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | QA | 3 | 2025-10-21 | 2025-10-24 | 3 | Completed
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Detail Requirement Analysis | Patrick-BA | 3 | 2025-11-24 | 2025-12-02 | 6 | Completed
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Document Detail Requirement | Patrick-BA | 3 | 2025-12-03 | 2025-12-11 | 6 | Completed
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Kent | 3 | 2025-12-12 | 2025-12-17 | 3 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Kent | 5 | 2025-12-18 | 2025-12-25 | 5 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Kent | 2 | 2025-12-26 | 2025-12-30 | 2 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | Kent | 3 | 2025-12-31 | 2026-01-05 | 3 | Not Started
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Balance Detail Requirement Analysis | Patrick-BA | 1.5 | 2025-12-12 | 2025-12-17 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Document Detail Requirement | Patrick-BA | 1.5 | 2025-12-18 | 2025-12-23 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 1 | FrontEnd | 1 | 2025-12-24 | 2025-12-25 | 1 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 2 | Kent | 7 | 2025-12-31 | 2026-01-09 | 7 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | QA | Maintain Distributable Balance QA - unit testing | Kent | 3 | 2026-01-12 | 2026-01-15 | 3 | Not Started
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Detail Requirement Analysis | Patrick-BA | 1.5 | 2025-12-24 | 2025-12-29 | 3 | In progress
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Document Detail Requirement | Patrick-BA | 1.5 | 2025-12-26 | 2025-12-31 | 3 | In progress
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 1 | FrontEnd | 4 | 2026-01-01 | 2026-01-07 | 4 | Not Started
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 2 | Kent | 4 | 2026-01-16 | 2026-01-22 | 4 | Not Started
Sprint 5 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | QA | Domestic Dividend Information Inquiry QA - unit testing | Kent | 2 | 2026-01-23 | 2026-01-27 | 2 | Not Started
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Detail Requirement Analysis | Patrick-BA | 1.5 | 2026-01-01 | 2026-01-06 | 3 | In progress
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Document Detail Requirement | Patrick-BA | 1.5 | 2026-01-07 | 2026-01-12 | 3 | In progress
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 1 | FrontEnd | 4 | 2026-01-08 | 2026-01-14 | 4 | Not Started
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 2 | Kent | 4 | 2026-01-28 | 2026-02-03 | 4 | Not Started
Sprint 6 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | QA | Upload Domestic Dividend Composition Info to EC QA - unit testing | Kent | 2 | 2026-02-04 | 2026-02-06 | 2 | Not Started
Sprint 1 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | New AP Lead | 3 | 2025-12-31 | 2026-01-05 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | New AP Lead | 3 | 2026-01-06 | 2026-01-09 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | New AP Lead | 4 | 2026-01-06 | 2026-01-12 | 4 | Not Started
Sprint 3 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | New AP Lead | 4 | 2026-01-13 | 2026-01-19 | 4 | Not Started
Sprint 4 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | New AP Lead | 2 | 2026-01-20 | 2026-01-22 | 2 | Not Started
Sprint 5 | Mandate | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | New AP Lead | 3 | 2026-01-23 | 2026-01-28 | 3 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement Analysis | New AP Lead | 2 | 2026-01-29 | 2026-02-02 | 2 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement | New AP Lead | 2 | 2026-02-03 | 2026-02-05 | 2 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 1 | FrontEnd | 2 | 2026-02-06 | 2026-02-10 | 2 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 2 | New AP Lead | 8 | 2026-02-06 | 2026-02-18 | 8 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | QA | Mandate Client Information Maintenance QA - unit-testing | New AP Lead | 2 | 2026-02-19 | 2026-02-23 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement Analysis | Kent | 2 | 2026-02-09 | 2026-02-11 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement | Kent | 2 | 2026-02-12 | 2026-02-16 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 1 | FrontEnd | 2 | 2026-02-17 | 2026-02-19 | 2 | Not Started
Sprint 7 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 2 | Kent | 8 | 2026-02-17 | 2026-02-27 | 8 | Not Started
Sprint 8 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | QA | Mandate Contract Information Maintenance QA - unit-testing | Kent | 2 | 2026-03-02 | 2026-03-04 | 2 | Not Started
Sprint 6 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Analysis | New AP Lead | 2 | 2026-02-24 | 2026-02-26 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Doc | New AP Lead | 2 | 2026-02-27 | 2026-03-03 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 1 | FrontEnd | 2 | 2026-03-04 | 2026-03-06 | 2 | Not Started
Sprint 8 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 2 | New AP Lead | 8 | 2026-03-04 | 2026-03-16 | 8 | Not Started
Sprint 9 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | QA | Mandate Subscription Data Entry QA - unit-testing | New AP Lead | 2 | 2026-03-17 | 2026-03-19 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Analysis | Kent | 2 | 2026-03-05 | 2026-03-09 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Doc | Kent | 2 | 2026-03-10 | 2026-03-12 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 1 | FrontEnd | 2 | 2026-03-13 | 2026-03-17 | 2 | Not Started
Sprint 10 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 2 | Kent | 8 | 2026-03-13 | 2026-03-25 | 8 | Not Started
Sprint 11 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | QA | Mandate Redemption Data Entry QA - unit-testing | Kent | 2 | 2026-03-26 | 2026-03-30 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | Kent | 1 | 2026-03-31 | 2026-04-01 | 1 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | Kent | 2 | 2026-04-02 | 2026-04-06 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | Kent | 1 | 2026-04-07 | 2026-04-08 | 1 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Kent | 3 | 2026-04-07 | 2026-04-10 | 3 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | QA | Mandate Fund NAV Inquiry QA - unit-testing | Kent | 2 | 2026-04-13 | 2026-04-15 | 2 | Not Started
Sprint 12 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | New AP Lead | 1 | 2026-03-31 | 2026-04-01 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | New AP Lead | 2 | 2026-04-02 | 2026-04-06 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | New AP Lead | 2 | 2026-04-07 | 2026-04-09 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | New AP Lead | 2 | 2026-04-07 | 2026-04-09 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | QA | Mandate Fund NAV Inquiry QA - unit-testing | New AP Lead | 2 | 2026-04-10 | 2026-04-14 | 2 | Not Started
Sprint 5 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement Analysis | Kent | 1 | 2026-04-16 | 2026-04-17 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement | Kent | 1 | 2026-04-20 | 2026-04-21 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 1 | FrontEnd | 1 | 2026-04-22 | 2026-04-23 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 2 | Kent | 2 | 2026-04-22 | 2026-04-24 | 2 | Not Started
Sprint 7 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | QA | Subscription Details Report QA - unit-testing | Kent | 1 | 2026-04-27 | 2026-04-28 | 1 | Not Started
Sprint 7 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement Analysis | New AP Lead | 1 | 2026-04-15 | 2026-04-16 | 1 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement | New AP Lead | 1 | 2026-04-17 | 2026-04-20 | 1 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 1 | FrontEnd | 1 | 2026-04-21 | 2026-04-22 | 1 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 2 | New AP Lead | 2 | 2026-04-21 | 2026-04-23 | 2 | Not Started
Sprint 9 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | QA | Redemption Details Report QA - unit-testing | New AP Lead | 1 | 2026-04-24 | 2026-04-27 | 1 | Not Started
Sprint 9 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement Analysis | Kent | 2 | 2026-04-29 | 2026-05-01 | 2 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement | Kent | 2 | 2026-05-04 | 2026-05-06 | 2 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 1 | FrontEnd | 3 | 2026-05-07 | 2026-05-12 | 3 | Not Started
Sprint 11 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 2 | Kent | 5 | 2026-05-07 | 2026-05-14 | 5 | Not Started
Sprint 12 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | QA | Mandate NAV Import Process (State Street) QA - unit-testing | Kent | 1 | 2026-05-15 | 2026-05-18 | 1 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement Analysis | New AP Lead | 1 | 2026-04-28 | 2026-04-29 | 1 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement | New AP Lead | 2 | 2026-04-30 | 2026-05-04 | 2 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 2 | 2026-05-05 | 2026-05-07 | 2 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 4 | 2026-05-08 | 2026-05-14 | 4 | Not Started
Sprint 14 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | QA | Generate Mandate Subscription/Redemption Data QA - unit-testing | New AP Lead | 2 | 2026-05-15 | 2026-05-19 | 2 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement Analysis | Kent | 0.5 | 2026-05-19 | 2026-05-19 | 0.5 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement | Kent | 0.5 | 2026-05-20 | 2026-05-20 | 0.5 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 1.5 | 2026-05-21 | 2026-05-22 | 1.5 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 2 | Kent | 2.5 | 2026-05-21 | 2026-05-25 | 2.5 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | QA | Export Mandate Subscription/Redemption Data QA - unit-testing | Kent | 1 | 2026-05-26 | 2026-05-27 | 1 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement Analysis | New AP Lead | 2 | 2026-05-20 | 2026-05-22 | 2 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement | New AP Lead | 2 | 2026-05-25 | 2026-05-27 | 2 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 2 | 2026-05-27 | 2026-05-29 | 2 | Not Started
Sprint 18 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 5 | 2026-05-29 | 2026-06-05 | 5 | Not Started
Sprint 19 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | QA | Generate SSB Mandate Subscription/Redemption Data QA - unit-testing | New AP Lead | 2 | 2026-06-05 | 2026-06-09 | 2 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement Analysis | Kent | 0.5 | 2026-05-28 | 2026-05-28 | 0.5 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement | Kent | 0.5 | 2026-05-29 | 2026-05-29 | 0.5 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 2 | 2026-06-01 | 2026-06-03 | 2 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 2 | Kent | 3 | 2026-06-03 | 2026-06-08 | 3 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | QA | Export SSB Mandate Subscription/Redemption Data QA - unit-testing | Kent | 1 | 2026-06-09 | 2026-06-10 | 1 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Requirement Analysis | New AP Lead | 2 | 2026-06-10 | 2026-06-12 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Data Requirement | New AP Lead | 2 | 2026-06-15 | 2026-06-17 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 1 | FrontEnd | 3 | 2026-06-18 | 2026-06-23 | 3 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 2 | New AP Lead | 5 | 2026-06-23 | 2026-06-30 | 5 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | QA | Fund NAV Auto Import Process QA - unit-testing | New AP Lead | 1 | 2026-07-01 | 2026-07-02 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Requirement Analysis | Kent | 1 | 2026-06-11 | 2026-06-12 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Data Requirement | Kent | 2 | 2026-06-15 | 2026-06-17 | 2 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 1 | FrontEnd | 1.5 | 2026-06-18 | 2026-06-19 | 1.5 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 2 | Kent | 2.5 | 2026-06-19 | 2026-06-23 | 2.5 | Not Started
Sprint 17 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | QA | Fund NAV Import Status Inquiry QA - unit-testing | Kent | 1 | 2026-06-24 | 2026-06-25 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement Analysis | New AP Lead | 1 | 2026-07-03 | 2026-07-06 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement | New AP Lead | 1 | 2026-07-07 | 2026-07-08 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 1 | FrontEnd | 1.5 | 2026-07-09 | 2026-07-10 | 1.5 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 2 | New AP Lead | 1.5 | 2026-07-10 | 2026-07-13 | 1.5 | Not Started
Sprint 18 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | QA | Calendar File QA - unit-testing | New AP Lead | 1 | 2026-07-14 | 2026-07-15 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement Analysis | Kent | 1 | 2026-06-26 | 2026-06-29 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement | Kent | 2 | 2026-06-30 | 2026-07-02 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 1 | FrontEnd | 1 | 2026-07-03 | 2026-07-06 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 2 | Kent | 2 | 2026-07-03 | 2026-07-07 | 2 | Not Started
Sprint 19 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | QA | Payment Notice – Management Fee, Custody Fee QA - unit-testing | Kent | 1 | 2026-07-08 | 2026-07-09 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement Analysis | New AP Lead | 1.5 | 2026-07-16 | 2026-07-17 | 1.5 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement | New AP Lead | 1.5 | 2026-07-20 | 2026-07-21 | 1.5 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 1 | FrontEnd | 2 | 2026-07-22 | 2026-07-24 | 2 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 2 | New AP Lead | 2 | 2026-07-22 | 2026-07-24 | 2 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | QA | Validation – Dividend Data QA - unit-testing | New AP Lead | 1 | 2026-07-27 | 2026-07-28 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement Analysis | Kent | 1 | 2026-07-10 | 2026-07-13 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement | Kent | 1 | 2026-07-14 | 2026-07-15 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 1 | FrontEnd | 1 | 2026-07-16 | 2026-07-17 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 2 | Kent | 2 | 2026-07-16 | 2026-07-20 | 2 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | QA | Payment Notice – Dividend Distribution QA - unit-testing | Kent | 1 | 2026-07-21 | 2026-07-22 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement Analysis | New AP Lead | 1 | 2026-07-29 | 2026-07-30 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement | New AP Lead | 1 | 2026-07-31 | 2026-08-03 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 1 | FrontEnd | 1 | 2026-08-04 | 2026-08-05 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 2 | New AP Lead | 2 | 2026-08-04 | 2026-08-06 | 2 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | QA | Payment Notice – Dividend Instruction Printing QA - unit-testing | New AP Lead | 1 | 2026-08-07 | 2026-08-10 | 1 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Analysis | Kent | 2 | 2026-07-23 | 2026-07-27 | 2 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Doc | Kent | 2 | 2026-07-28 | 2026-07-30 | 2 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 1 | FrontEnd | 3.5 | 2026-07-31 | 2026-08-05 | 3.5 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 2 | Kent | 4 | 2026-07-31 | 2026-08-06 | 4 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | QA | Mandate Data Generation Process QA - unit-testing | Kent | 1.5 | 2026-08-07 | 2026-08-10 | 1.5 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Analysis | New AP Lead | 2 | 2026-08-11 | 2026-08-13 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Doc | New AP Lead | 2 | 2026-08-14 | 2026-08-18 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 1 | FrontEnd | 2.5 | 2026-08-19 | 2026-08-21 | 2.5 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 2 | New AP Lead | 4.5 | 2026-08-19 | 2026-08-25 | 4.5 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | QA | Mandate Data Maintenance Process QA - unit-testing | New AP Lead | 2 | 2026-08-26 | 2026-08-28 | 2 | Not Started
Sprint 11 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Analysis | Kent | 1 | 2026-08-11 | 2026-08-12 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Doc | Kent | 1 | 2026-08-13 | 2026-08-14 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 1 | FrontEnd | 1 | 2026-08-17 | 2026-08-18 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 2 | Kent | 2 | 2026-08-17 | 2026-08-19 | 2 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | QA | Subscription/Redemption Posting Details Report QA - unit-testing | Kent | 1 | 2026-08-20 | 2026-08-21 | 1 | Not Started
Sprint 12 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Analysis | New AP Lead | 1 | 2026-08-31 | 2026-09-01 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Doc | New AP Lead | 1 | 2026-09-02 | 2026-09-03 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 1 | FrontEnd | 3 | 2026-09-04 | 2026-09-09 | 3 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 2 | New AP Lead | 4 | 2026-09-04 | 2026-09-10 | 4 | Not Started
Sprint 14 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | QA | Mandate Contract Asset Movement Report QA - unit-testing | New AP Lead | 2 | 2026-09-11 | 2026-09-15 | 2 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Analysis | Kent | 1 | 2026-08-24 | 2026-08-25 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Doc | Kent | 1 | 2026-08-26 | 2026-08-27 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 1 | FrontEnd | 2 | 2026-08-28 | 2026-09-01 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 2 | Kent | 2 | 2026-08-28 | 2026-09-01 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | QA | PAMS Inventory File Export QA - unit-testing | Kent | 1 | 2026-09-02 | 2026-09-03 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement Analysis | New AP Lead | 1 | 2026-09-16 | 2026-09-17 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement | New AP Lead | 1 | 2026-09-18 | 2026-09-21 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 1 | FrontEnd | 1 | 2026-09-22 | 2026-09-23 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 2 | New AP Lead | 4 | 2026-09-22 | 2026-09-28 | 4 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | QA | Mandate Stock Stop-Loss Control Table QA - unit-testing | New AP Lead | 1 | 2026-09-29 | 2026-09-30 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Analysis | Kent | 1 | 2026-09-22 | 2026-09-23 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Doc | Kent | 1 | 2026-09-24 | 2026-09-25 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | Development | Report - 基金規模報表查詢 - Development | Kent | 3 | 2026-09-28 | 2026-10-01 | 3 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | QA | Report - 基金規模報表查詢 QA - unit-testing | Kent | 1 | 2026-10-02 | 2026-10-05 | 1 | Not Started
Sprint 22 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Analysis | New AP Lead | 1 | 2026-10-01 | 2026-10-02 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Doc | New AP Lead | 1 | 2026-10-05 | 2026-10-06 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | Development | Taiwan Ratings Reporting Data - Development | New AP Lead | 3 | 2026-10-07 | 2026-10-12 | 3 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | QA | Taiwan Ratings Reporting Data QA - unit-testing | New AP Lead | 1 | 2026-10-13 | 2026-10-14 | 1 | Not Started
Sprint 23 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Analysis | Kent | 1 | 2026-10-06 | 2026-10-07 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Doc | Kent | 1 | 2026-10-08 | 2026-10-09 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | Development | Mutual Fund Asset Size Export Process - Development | Kent | 3 | 2026-10-12 | 2026-10-15 | 3 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | QA | Mutual Fund Asset Size Export Process - unit-testing | Kent | 1 | 2026-10-16 | 2026-10-19 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement Analysis | New AP Lead | 1 | 2027-03-01 | 2027-03-02 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement | New AP Lead | 1 | 2027-03-03 | 2027-03-04 | 1 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 1 | FrontEnd | 3 | 2027-03-04 | 2025-03-05 | 3 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 2 | New AP Lead | 4 | 2027-03-05 | 2027-03-11 | 4 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | QA | Generate Shareholder Meeting Data QA - unit-testing | New AP Lead | 2 | 2027-03-12 | 2027-03-16 | 2 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement Analysis | Kent | 1 | 2027-03-01 | 2027-03-02 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement | Kent | 1 | 2027-03-03 | 2027-03-04 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 1 | FrontEnd | 1 | 2027-03-05 | 2027-03-08 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 2 | Kent | 3 | 2027-03-05 | 2027-03-10 | 3 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | QA | Generate Memo for Assigned Personnel/Function QA - unit-testing | Kent | 1 | 2027-03-11 | 2027-03-12 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement Analysis | New AP Lead | 1 | 2027-03-17 | 2027-03-18 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement | New AP Lead | 1 | 2027-03-19 | 2027-03-22 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 1 | FrontEnd | 2 | 2027-03-23 | 2027-03-25 | 2 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 2 | New AP Lead | 2 | 2027-03-23 | 2027-03-25 | 2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | QA | Director/Supervisor Election Report/Function QA - unit-testing | New AP Lead | 1 | 2027-03-26 | 2027-03-29 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement Analysis | Kent | 1 | 2027-03-15 | 2027-03-16 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement | Kent | 1 | 2027-03-17 | 2027-03-18 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 1 | FrontEnd | 1 | 2027-03-19 | 2027-03-22 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 2 | Kent | 1 | 2027-03-19 | 2027-03-22 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | QA | Shareholder Meeting Fund Attendance Details Report QA - unit-testing | Kent | 1 | 2027-03-23 | 2027-03-24 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Requirement Analysis | New AP Lead | 1 | 2027-03-30 | 2027-03-31 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Report Requirement | New AP Lead | 1 | 2027-04-01 | 2027-04-02 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details Report - Development 1 | FrontEnd | 1 | 2027-04-05 | 2027-04-06 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details - Development 2 | New AP Lead | 1 | 2027-04-05 | 2027-04-06 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | QA | Shareholder Meeting Missing Election Report Details QA - unit-testing | New AP Lead | 1 | 2027-04-07 | 2027-04-08 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement Analysis | Kent | 1 | 2027-03-25 | 2027-03-26 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement | Kent | 1 | 2027-03-29 | 2027-03-30 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 1 | FrontEnd | 2 | 2027-03-31 | 2027-04-02 | 2 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 2 | Kent | 3 | 2027-03-31 | 2027-04-05 | 3 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | QA | Stock Basic Data Maintenance QA - unit-testing | Kent | 1 | 2027-04-06 | 2027-04-07 | 1 | Not Started
Sprint30 | Shareholders' Meeting & Management | Pararell Run | All |  | New AP Lead |  | 2027-04-07 | 2027-04-30 |  | Not Started
Formulas:
FINISH = WORKDAY([START],[DURATION])
START = WORKDAY([FINISH, row above],1)
START = [FINISH, row above]

## Shareholders' Meeting & Managem
Shareholders' Meeting & Managem
| TOTAL TASKS | 23 |  |  |  | DURATION | 61 |  | Overall Progress
| Completed | 0 |  |  |  | START | 2027-03-01 |  |  |  | 12 | Team Member | FTE | Cost / Monthly |  | Difficulty Level | MD
| In progress | 0 |  |  |  | FINISH | 2027-04-30 |  |  |  | 52 | Kent | 1 |  | 1 year | Low | 1-2
| Not Started | 24 | [9 empty] | BA/Testing | 1 | 152250 | 1827000 | Mid | 3-5
|  |  | New SA and Engineer training |  |  |  | 1/5/2026 - 1/9/2026 |  | 100% |  |  | AP Lead | 1 |  | Onboard after Chinese New Year | High | 6-8
[12 empty] | FrontEnd1 | 1 | 152250 | 1827000
SPRINT | EPIC | FEATURE | TASKS | STORIES | Difficulty Level | RESPONSIBLE | Man Day Required | START | FINISH | DURATION | STATUS
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement Analysis | Low | BA/Testing | 1 | 2027-03-01 | 2027-03-01 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement | Low | BA/Testing | 1 | 2027-03-02 | 2027-03-02 | 1 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 1 | Mid | FrontEnd | 3 | 2027-03-03 | 2027-03-05 | 3 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 2 | Mid | Kent | 4 | 2027-03-03 | 2027-03-08 | 4 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Testing | Generate Shareholder Meeting Data QA - unit-testing | Low | BA/Testing | 2 | 2027-03-09 | 2027-03-10 | 2 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement Analysis | Low | BA/Testing | 1 | 2027-03-01 | 2027-03-01 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement | Low | BA/Testing | 1 | 2027-03-02 | 2027-03-02 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 1 | Low | FrontEnd | 2 | 2027-03-03 | 2027-03-04 | 2 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 2 | Mid | New AP Lead | 5 | 2027-03-03 | 2027-03-09 | 5 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Testing | Generate Memo for Assigned Personnel/Function QA - unit-testing | Low | BA/Testing | 1 | 2027-03-10 | 2027-03-10 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement Analysis | Low | BA/Testing | 1 | 2027-03-05 | 2027-03-05 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement | Low | BA/Testing | 1 | 2027-03-08 | 2027-03-08 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 1 | Low | FrontEnd | 2 | 2027-03-09 | 2027-03-10 | 2 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 2 | Mid | Kent | 5 | 2027-03-09 | 2027-03-15 | 5 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Testing | Director/Supervisor Election Report/Function QA - unit-testing | Low | BA/Testing | 1 | 2027-03-16 | 2027-03-16 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement Analysis | Low | BA/Testing | 1 | 2027-03-11 | 2027-03-11 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement | Low | BA/Testing | 1 | 2027-03-12 | 2027-03-12 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 1 | Low | FrontEnd | 1 | 2027-03-15 | 2027-03-15 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 2 | Low | New AP Lead | 2 | 2027-03-15 | 2027-03-16 | 2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Testing | Shareholder Meeting Fund Attendance Details Report QA - unit-testing | Low | BA/Testing | 1 | 2027-03-17 | 2027-03-17 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Requirement Analysis | Low | BA/Testing | 1 | 2027-03-15 | 2027-03-15 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Report Requirement | Low | BA/Testing | 1 | 2027-03-16 | 2027-03-16 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details Report - Development 1 | Low | FrontEnd | 1 | 2027-03-17 | 2027-03-17 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details - Development 2 | Low | Kent | 2 | 2027-03-17 | 2027-03-18 | 2 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Testing | Shareholder Meeting Missing Election Report Details QA - unit-testing | Low | BA/Testing | 1 | 2027-03-19 | 2027-03-19 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement Analysis | Low | BA/Testing | 1 | 2027-03-17 | 2027-03-17 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement | Low | BA/Testing | 1 | 2027-03-18 | 2027-03-18 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 1 | Low | FrontEnd | 2 | 2027-03-19 | 2027-03-22 | 2 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 2 | Mid | Kent | 5 | 2027-03-19 | 2027-03-25 | 5 | Not Started
Sprint 30 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Testing | Stock Basic Data Maintenance QA - unit-testing | Low | BA/Testing | 1 | 2027-03-26 | 2027-03-26 | 1 | Not Started
Sprint30 | Shareholders' Meeting & Management | Pararell Run | All |  |  | New AP Lead |  | 2027-03-29 | 2027-04-30 |  | Not Started

## Project Planning - C
DMS Development
| TOTAL TASKS | 199 |  |  | DURATION | 479 |  | Overall Progress |  |  | Team Member | FTE
| Completed | 0 |  |  | START | 2025-09-15 |  |  |  | 24 | Patrick | 0.5
| In progress | 9 |  |  | FINISH | 2027-01-06 |  |  |  | 408 | Kent | 1
| Not Started | 190 | [8 empty] | Richard | 0.5
[8 empty] | 100% |  | 5.882% | AP Lead | 1
[11 empty] | FrontEnd1 | 1
SPRINT | EPIC | FEATURE | TASKS | STORIES | RESPONSIBLE | Man Day Required | START | FINISH | DURATION | STATUS
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | Kent | 3 | 2025-09-15 | 2025-09-18 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | Kent | 3 | 2025-09-19 | 2025-09-24 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Kent | 5 | 2025-09-25 | 2025-10-02 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Kent | 5 | 2025-10-03 | 2025-10-10 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Kent | 5 | 2025-10-13 | 2025-10-20 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | Kent | 3 | 2025-10-21 | 2025-10-24 | 3 | Completed
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Detail Requirement Analysis | Patrick | 3 | 2025-11-24 | 2025-12-02 | 6 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Document Detail Requirement | Patrick | 3 | 2025-12-03 | 2025-12-11 | 6 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Kent | 3 | 2025-11-24 | 2025-11-27 | 3 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Kent | 5 | 2025-11-28 | 2025-12-05 | 5 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Kent | 2 | 2025-12-08 | 2025-12-10 | 2 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | Kent | 3 | 2025-12-11 | 2025-12-16 | 3 | Not Started
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Balance Detail Requirement Analysis | Patrick | 1.5 | 2025-12-12 | 2025-12-17 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Document Detail Requirement | Patrick | 1.5 | 2025-12-18 | 2025-12-23 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 1 | Kent | 4 | 2025-12-17 | 2025-12-23 | 4 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 2 | Kent | 4 | 2025-12-24 | 2025-12-30 | 4 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | QA | Maintain Distributable Balance QA - unit testing | Kent | 3 | 2025-12-31 | 2026-01-05 | 3 | Not Started
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Detail Requirement Analysis | Patrick | 1.5 | 2025-12-24 | 2025-12-29 | 3 | In progress
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Document Detail Requirement | Patrick | 1.5 | 2025-12-30 | 2026-01-02 | 3 | In progress
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 1 | Kent | 4 | 2026-01-06 | 2026-01-12 | 4 | Not Started
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 2 | Kent | 4 | 2026-01-13 | 2026-01-19 | 4 | Not Started
Sprint 5 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | QA | Domestic Dividend Information Inquiry QA - unit testing | Kent | 2 | 2026-01-20 | 2026-01-22 | 2 | Not Started
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Detail Requirement Analysis | Patrick | 1.5 | 2025-12-24 | 2025-12-29 | 3 | In progress
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Document Detail Requirement | Patrick | 1.5 | 2025-12-30 | 2026-01-02 | 3 | In progress
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 1 | Kent | 4 | 2026-01-23 | 2026-01-29 | 4 | Not Started
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 2 | Kent | 4 | 2026-01-30 | 2026-02-05 | 4 | Not Started
Sprint 6 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | QA | Upload Domestic Dividend Composition Info to EC QA - unit testing | Kent | 2 | 2026-02-06 | 2026-02-10 | 2 | Not Started
Sprint 1 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | Richard | 3 | 2025-12-01 | 2025-12-09 | 6 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | Richard | 3 | 2025-12-10 | 2025-12-18 | 6 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Richard | 4 | 2025-12-19 | 2025-12-31 | 8 | Not Started
Sprint 3 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Richard | 4 | 2026-01-01 | 2026-01-13 | 8 | Not Started
Sprint 4 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Richard | 2 | 2026-01-14 | 2026-01-20 | 4 | Not Started
Sprint 5 | Mandate | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | Richard | 3 | 2026-01-21 | 2026-01-29 | 6 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement Analysis | New AP Lead | 2 | 2026-01-05 | 2026-01-07 | 2 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement | New AP Lead | 2 | 2026-01-08 | 2026-01-12 | 2 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 1 | New AP Lead | 5 | 2026-01-13 | 2026-01-20 | 5 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 2 | New AP Lead | 5 | 2026-01-21 | 2026-01-28 | 5 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | QA | Mandate Client Information Maintenance QA - unit-testing | New AP Lead | 2 | 2026-01-29 | 2026-02-02 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement Analysis | New AP Lead | 2 | 2026-02-03 | 2026-02-05 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement | New AP Lead | 2 | 2026-02-06 | 2026-02-10 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 1 | New AP Lead | 5 | 2026-02-11 | 2026-02-18 | 5 | Not Started
Sprint 7 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 2 | New AP Lead | 5 | 2026-02-23 | 2026-03-02 | 5 | Not Started
Sprint 8 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | QA | Mandate Contract Information Maintenance QA - unit-testing | New AP Lead | 2 | 2026-03-03 | 2026-03-05 | 2 | Not Started
Sprint 6 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Analysis | Kent | 2 | 2026-02-11 | 2026-02-13 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Doc | Kent | 2 | 2026-02-23 | 2026-02-25 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 1 | Kent | 5 | 2026-02-26 | 2026-03-05 | 5 | Not Started
Sprint 8 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 2 | Kent | 5 | 2026-03-06 | 2026-03-13 | 5 | Not Started
Sprint 9 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | QA | Mandate Subscription Data Entry QA - unit-testing | Kent | 2 | 2026-03-16 | 2026-03-18 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Analysis | Kent | 2 | 2026-03-19 | 2026-03-23 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Doc | Kent | 2 | 2026-03-24 | 2026-03-26 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 1 | Kent | 5 | 2026-03-27 | 2026-04-03 | 5 | Not Started
Sprint 10 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 2 | Kent | 5 | 2026-04-06 | 2026-04-13 | 5 | Not Started
Sprint 11 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | QA | Mandate Redemption Data Entry QA - unit-testing | Kent | 2 | 2026-04-14 | 2026-04-16 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | Kent | 1 | 2026-04-17 | 2026-04-20 | 1 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | Kent | 2 | 2026-04-21 | 2026-04-23 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | Kent | 2 | 2026-04-24 | 2026-04-28 | 2 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Kent | 2 | 2026-04-29 | 2026-05-01 | 2 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | QA | Mandate Fund NAV Inquiry QA - unit-testing | Kent | 2 | 2026-05-04 | 2026-05-06 | 2 | Not Started
Sprint 12 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | Kent | 1 | 2026-05-07 | 2026-05-08 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | Kent | 2 | 2026-05-11 | 2026-05-13 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | Kent | 2 | 2026-05-14 | 2026-05-18 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Kent | 2 | 2026-05-19 | 2026-05-21 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | QA | Mandate Fund NAV Inquiry QA - unit-testing | Kent | 2 | 2026-05-22 | 2026-05-26 | 2 | Not Started
Sprint 5 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement Analysis | Richard | 1 | 2026-01-30 | 2026-02-03 | 2 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement | Richard | 1 | 2026-02-04 | 2026-02-06 | 2 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 1 | Richard | 1 | 2026-02-09 | 2026-02-11 | 2 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 2 | Richard | 2 | 2026-02-12 | 2026-02-18 | 4 | Not Started
Sprint 7 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | QA | Subscription Details Report QA - unit-testing | Richard | 1 | 2026-02-23 | 2026-02-25 | 2 | Not Started
Sprint 7 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement Analysis | Richard | 1 | 2026-02-26 | 2026-03-02 | 2 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement | Richard | 1 | 2026-03-03 | 2026-03-05 | 2 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 1 | Richard | 1 | 2026-03-06 | 2026-03-10 | 2 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 2 | Richard | 2 | 2026-03-11 | 2026-03-17 | 4 | Not Started
Sprint 9 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | QA | Redemption Details Report QA - unit-testing | Richard | 1 | 2026-03-18 | 2026-03-20 | 2 | Not Started
Sprint 9 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement Analysis | Richard | 2 | 2026-03-23 | 2026-03-27 | 4 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement | Richard | 2 | 2026-03-30 | 2026-04-03 | 4 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 1 | Richard | 3 | 2026-04-06 | 2026-04-14 | 6 | Not Started
Sprint 11 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 2 | Richard | 5 | 2026-04-15 | 2026-04-29 | 10 | Not Started
Sprint 12 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | QA | Mandate NAV Import Process (State Street) QA - unit-testing | Richard | 1 | 2026-04-30 | 2026-05-04 | 2 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement Analysis | Richard | 1 | 2026-05-05 | 2026-05-07 | 2 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement | Richard | 2 | 2026-05-08 | 2026-05-14 | 4 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 1 | Richard | 2 | 2026-05-15 | 2026-05-21 | 4 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 2 | Richard | 4 | 2026-05-22 | 2026-06-03 | 8 | Not Started
Sprint 14 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | QA | Generate Mandate Subscription/Redemption Data QA - unit-testing | Richard | 2 | 2026-06-04 | 2026-06-10 | 4 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement Analysis | Richard | 0.5 | 2026-06-11 | 2026-06-12 | 1 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement | Richard | 0.5 | 2026-06-15 | 2026-06-16 | 1 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 1 | Richard | 1.5 | 2026-06-17 | 2026-06-22 | 3 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 2 | Richard | 2.5 | 2026-06-23 | 2026-06-30 | 5 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | QA | Export Mandate Subscription/Redemption Data QA - unit-testing | Richard | 1 | 2026-07-01 | 2026-07-03 | 2 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement Analysis | Richard | 2 | 2026-07-06 | 2026-07-10 | 4 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement | Richard | 2 | 2026-07-10 | 2026-07-16 | 4 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 1 | Richard | 2 | 2026-07-16 | 2026-07-22 | 4 | Not Started
Sprint 18 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 2 | Richard | 5 | 2026-07-22 | 2026-08-05 | 10 | Not Started
Sprint 19 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | QA | Generate SSB Mandate Subscription/Redemption Data QA - unit-testing | Richard | 2 | 2026-08-05 | 2026-08-11 | 4 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement Analysis | Richard | 0.5 | 2026-08-11 | 2026-08-12 | 1 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement | Richard | 0.5 | 2026-08-12 | 2026-08-13 | 1 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 1 | Richard | 2 | 2026-08-13 | 2026-08-19 | 4 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 2 | Richard | 3 | 2026-08-19 | 2026-08-27 | 6 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | QA | Export SSB Mandate Subscription/Redemption Data QA - unit-testing | Richard | 1 | 2026-08-27 | 2026-08-31 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Requirement Analysis | Kent | 2 | 2026-05-27 | 2026-05-29 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Data Requirement | Kent | 2 | 2026-06-01 | 2026-06-03 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 1 | Kent | 3 | 2026-06-04 | 2026-06-09 | 3 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 2 | Kent | 5 | 2026-06-10 | 2026-06-17 | 5 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | QA | Fund NAV Auto Import Process QA - unit-testing | Kent | 1 | 2026-06-18 | 2026-06-19 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Requirement Analysis | Kent | 1 | 2026-06-22 | 2026-06-23 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Data Requirement | Kent | 2 | 2026-06-24 | 2026-06-26 | 2 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 1 | Kent | 1.5 | 2026-06-29 | 2026-06-30 | 1.5 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 2 | Kent | 2.5 | 2026-07-01 | 2026-07-03 | 2.5 | Not Started
Sprint 17 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | QA | Fund NAV Import Status Inquiry QA - unit-testing | Kent | 1 | 2026-07-06 | 2026-07-07 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement Analysis | Kent | 1 | 2026-07-08 | 2026-07-09 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement | Kent | 1 | 2026-07-10 | 2026-07-13 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 1 | Kent | 1.5 | 2026-07-14 | 2026-07-15 | 1.5 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 2 | Kent | 1.5 | 2026-07-16 | 2026-07-17 | 1.5 | Not Started
Sprint 18 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | QA | Calendar File QA - unit-testing | Kent | 1 | 2026-07-20 | 2026-07-21 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement Analysis | Kent | 1 | 2026-07-22 | 2026-07-23 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement | Kent | 2 | 2026-07-24 | 2026-07-28 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 1 | Kent | 1 | 2026-07-29 | 2026-07-30 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 2 | Kent | 2 | 2026-07-31 | 2026-08-04 | 2 | Not Started
Sprint 19 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | QA | Payment Notice – Management Fee, Custody Fee QA - unit-testing | Kent | 1 | 2026-08-05 | 2026-08-06 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement Analysis | Kent | 1.5 | 2026-08-07 | 2026-08-10 | 1.5 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement | Kent | 1.5 | 2026-08-11 | 2026-08-12 | 1.5 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 1 | Kent | 2 | 2026-08-13 | 2026-08-17 | 2 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 2 | Kent | 2 | 2026-08-18 | 2026-08-20 | 2 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | QA | Validation – Dividend Data QA - unit-testing | Kent | 1 | 2026-08-21 | 2026-08-24 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement Analysis | Kent | 1 | 2026-08-25 | 2026-08-26 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement | Kent | 1 | 2026-08-27 | 2026-08-28 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 1 | Kent | 1 | 2026-08-31 | 2026-09-01 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 2 | Kent | 2 | 2026-09-02 | 2026-09-04 | 2 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | QA | Payment Notice – Dividend Distribution QA - unit-testing | Kent | 1 | 2026-09-07 | 2026-09-08 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement Analysis | Kent | 1 | 2026-09-09 | 2026-09-10 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement | Kent | 1 | 2026-09-11 | 2026-09-14 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 1 | Kent | 1 | 2026-09-15 | 2026-09-16 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 2 | Kent | 2 | 2026-09-17 | 2026-09-21 | 2 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | QA | Payment Notice – Dividend Instruction Printing QA - unit-testing | Kent | 1 | 2026-09-22 | 2026-09-23 | 1 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Analysis | New AP Lead | 2 | 2026-03-06 | 2026-03-10 | 2 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Doc | New AP Lead | 2 | 2026-03-11 | 2026-03-13 | 2 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 1 | New AP Lead | 3.5 | 2026-03-16 | 2026-03-19 | 3.5 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 2 | New AP Lead | 4 | 2026-03-20 | 2026-03-26 | 4 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | QA | Mandate Data Generation Process QA - unit-testing | New AP Lead | 1.5 | 2026-03-27 | 2026-03-30 | 1.5 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Analysis | New AP Lead | 2 | 2026-03-31 | 2026-04-02 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Doc | New AP Lead | 2 | 2026-04-03 | 2026-04-07 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 1 | New AP Lead | 2.5 | 2026-04-08 | 2026-04-10 | 2.5 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 2 | New AP Lead | 4.5 | 2026-04-13 | 2026-04-17 | 4.5 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | QA | Mandate Data Maintenance Process QA - unit-testing | New AP Lead | 2 | 2026-04-20 | 2026-04-22 | 2 | Not Started
Sprint 11 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Analysis | New AP Lead | 1 | 2026-04-23 | 2026-04-24 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Doc | New AP Lead | 1 | 2026-04-27 | 2026-04-28 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 1 | New AP Lead | 1 | 2026-04-29 | 2026-04-30 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 2 | New AP Lead | 2 | 2026-05-01 | 2026-05-05 | 2 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | QA | Subscription/Redemption Posting Details Report QA - unit-testing | New AP Lead | 1 | 2026-05-06 | 2026-05-07 | 1 | Not Started
Sprint 12 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Analysis | New AP Lead | 1 | 2026-05-08 | 2026-05-11 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Doc | New AP Lead | 1 | 2026-05-12 | 2026-05-13 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 1 | New AP Lead | 3 | 2026-05-14 | 2026-05-19 | 3 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 2 | New AP Lead | 4 | 2026-05-20 | 2026-05-26 | 4 | Not Started
Sprint 14 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | QA | Mandate Contract Asset Movement Report QA - unit-testing | New AP Lead | 2 | 2026-05-27 | 2026-05-29 | 2 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Analysis | New AP Lead | 1 | 2026-06-01 | 2026-06-02 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Doc | New AP Lead | 1 | 2026-06-03 | 2026-06-04 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 1 | New AP Lead | 2 | 2026-06-05 | 2026-06-09 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 2 | New AP Lead | 2 | 2026-06-10 | 2026-06-12 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | QA | PAMS Inventory File Export QA - unit-testing | New AP Lead | 1 | 2026-06-15 | 2026-06-16 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement Analysis | New AP Lead | 1 | 2026-06-17 | 2026-06-18 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement | New AP Lead | 1 | 2026-06-19 | 2026-06-22 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 1 | New AP Lead | 1 | 2026-06-23 | 2026-06-24 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 2 | New AP Lead | 4 | 2026-06-25 | 2026-07-01 | 4 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | QA | Mandate Stock Stop-Loss Control Table QA - unit-testing | New AP Lead | 1 | 2026-07-02 | 2026-07-03 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Analysis | New AP Lead | 1 | 2026-07-06 | 2026-07-07 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Doc | New AP Lead | 1 | 2026-07-08 | 2026-07-09 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | Development | Report - 基金規模報表查詢 - Development | New AP Lead | 3 | 2026-07-10 | 2026-07-15 | 3 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | QA | Report - 基金規模報表查詢 QA - unit-testing | New AP Lead | 1 | 2026-07-16 | 2026-07-17 | 1 | Not Started
Sprint 22 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Analysis | Kent | 1 | 2026-09-24 | 2026-09-25 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Doc | Kent | 1 | 2026-09-28 | 2026-09-29 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | Development | Taiwan Ratings Reporting Data - Development | Kent | 3 | 2026-09-30 | 2026-10-05 | 3 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | QA | Taiwan Ratings Reporting Data QA - unit-testing | Kent | 1 | 2026-10-06 | 2026-10-07 | 1 | Not Started
Sprint 23 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Analysis | Kent | 1 | 2026-10-08 | 2026-10-09 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Doc | Kent | 1 | 2026-10-12 | 2026-10-13 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | Development | Mutual Fund Asset Size Export Process - Development | Kent | 3 | 2026-10-14 | 2026-10-19 | 3 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | QA | Mutual Fund Asset Size Export Process - unit-testing | Kent | 1 | 2026-10-20 | 2026-10-21 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement Analysis | Kent | 0.5 | 2026-10-22 | 2026-10-22 | 0.5 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement | Kent | 0.5 | 2026-10-23 | 2026-10-23 | 0.5 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 1 | Kent | 3 | 2026-10-26 | 2026-10-29 | 3 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 2 | Kent | 4 | 2026-10-30 | 2026-11-05 | 4 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | QA | Generate Shareholder Meeting Data QA - unit-testing | Kent | 2 | 2026-11-06 | 2026-11-10 | 2 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement Analysis | Kent | 0.5 | 2026-11-11 | 2026-11-11 | 0.5 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement | Kent | 0.5 | 2026-11-12 | 2026-11-12 | 0.5 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 1 | Kent | 1 | 2026-11-13 | 2026-11-16 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 2 | Kent | 3 | 2026-11-17 | 2026-11-20 | 3 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | QA | Generate Memo for Assigned Personnel/Function QA - unit-testing | Kent | 1 | 2026-11-23 | 2026-11-24 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement Analysis | Kent | 0.5 | 2026-11-25 | 2026-11-25 | 0.5 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement | Kent | 0.5 | 2026-11-26 | 2026-11-26 | 0.5 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 1 | Kent | 2 | 2026-11-27 | 2026-12-01 | 2 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 2 | Kent | 2 | 2026-12-02 | 2026-12-04 | 2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | QA | Director/Supervisor Election Report/Function QA - unit-testing | Kent | 1 | 2026-12-07 | 2026-12-08 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement Analysis | Kent | 0.2 | 2026-12-09 | 2026-12-09 | 0.2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement | Kent | 0.3 | 2026-12-10 | 2026-12-10 | 0.3 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 1 | Kent | 0.2 | 2026-12-11 | 2026-12-11 | 0.2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 2 | Kent | 0.5 | 2026-12-14 | 2026-12-14 | 0.5 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | QA | Shareholder Meeting Fund Attendance Details Report QA - unit-testing | Kent | 0.3 | 2026-12-15 | 2026-12-15 | 0.3 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Requirement Analysis | Kent | 0.2 | 2026-12-16 | 2026-12-16 | 0.2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Report Requirement | Kent | 0.3 | 2026-12-17 | 2026-12-17 | 0.3 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details Report - Development 1 | Kent | 0.2 | 2026-12-18 | 2026-12-18 | 0.2 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details - Development 2 | Kent | 0.5 | 2026-12-21 | 2026-12-21 | 0.5 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | QA | Shareholder Meeting Missing Election Report Details QA - unit-testing | Kent | 0.3 | 2026-12-22 | 2026-12-22 | 0.3 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement Analysis | Kent | 1 | 2026-12-23 | 2026-12-24 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement | Kent | 1 | 2026-12-25 | 2026-12-28 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 1 | Kent | 1.5 | 2026-12-29 | 2026-12-30 | 1.5 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 2 | Kent | 2.5 | 2026-12-31 | 2027-01-04 | 2.5 | Not Started
Sprint 30 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | QA | Stock Basic Data Maintenance QA - unit-testing | Kent | 1 | 2027-01-05 | 2027-01-06 | 1 | Not Started
Formulas:
FINISH = WORKDAY([START],[DURATION])
START = WORKDAY([FINISH, row above],1)
START = [FINISH, row above]

## Project Planning (3)
DMS Development
| TOTAL TASKS | 199 |  |  | DURATION | 325 |  | Overall Progress |  |  | Team Member | FTE
| Completed | 0 |  |  | START | 2025-09-15 |  |  |  | 24 | BA | 1
| In progress | 9 |  |  | FINISH | 2026-08-05 |  |  |  | 408 | Kent | 1
| Not Started | 190 | [8 empty] | QA | 1
[8 empty] | 100% |  | 5.882% | AP Lead | 1
[11 empty] | FrontEnd | 1
SPRINT | EPIC | FEATURE | TASKS | STORIES | RESPONSIBLE | Man Day Required | START | FINISH | DURATION | STATUS
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | BA | 3 | 2025-09-15 | 2025-09-18 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | BA | 3 | 2025-09-19 | 2025-09-24 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Kent | 5 | 2025-09-25 | 2025-10-02 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Kent | 5 | 2025-10-03 | 2025-10-10 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Kent | 5 | 2025-10-13 | 2025-10-20 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | QA | 3 | 2025-10-21 | 2025-10-24 | 3 | Completed
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Detail Requirement Analysis | BA | 3 | 2025-11-24 | 2025-11-27 | 3 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Document Detail Requirement | BA | 3 | 2025-11-28 | 2025-12-03 | 3 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Kent | 3 | 2025-12-04 | 2025-12-09 | 3 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Kent | 5 | 2025-12-10 | 2025-12-17 | 5 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Kent | 2 | 2025-12-18 | 2025-12-22 | 2 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | QA | 3 | 2025-12-23 | 2025-12-26 | 3 | Not Started
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Balance Detail Requirement Analysis | BA | 1.5 | 2025-12-04 | 2025-12-05 | 1.5 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Document Detail Requirement | BA | 1.5 | 2025-12-08 | 2025-12-09 | 1.5 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 1 | FrontEnd | 4 | 2025-12-10 | 2025-12-16 | 4 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 2 | Kent | 4 | 2025-12-10 | 2025-12-16 | 4 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | QA | Maintain Distributable Balance QA - unit testing | QA | 3 | 2025-12-17 | 2025-12-22 | 3 | Not Started
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Detail Requirement Analysis | BA | 1.5 | 2025-12-10 | 2025-12-11 | 1.5 | In progress
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Document Detail Requirement | BA | 1.5 | 2025-12-12 | 2025-12-15 | 1.5 | In progress
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 1 | FrontEnd | 4 | 2025-12-16 | 2025-12-22 | 4 | Not Started
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 2 | Kent | 4 | 2025-12-16 | 2025-12-22 | 4 | Not Started
Sprint 5 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | QA | Domestic Dividend Information Inquiry QA - unit testing | QA | 2 | 2025-12-23 | 2025-12-25 | 2 | Not Started
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Detail Requirement Analysis | BA | 1.5 | 2025-12-16 | 2025-12-17 | 1.5 | In progress
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Document Detail Requirement | BA | 1.5 | 2025-12-18 | 2025-12-19 | 1.5 | In progress
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 1 | FrontEnd | 4 | 2025-12-23 | 2025-12-29 | 4 | Not Started
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 2 | Kent | 4 | 2025-12-23 | 2025-12-29 | 4 | Not Started
Sprint 6 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | QA | Upload Domestic Dividend Composition Info to EC QA - unit testing | QA | 2 | 2025-12-30 | 2026-01-01 | 2 | Not Started
Sprint 1 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | BA | 3 | 2025-12-22 | 2025-12-25 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | BA | 3 | 2025-12-26 | 2025-12-31 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | New AP Lead | 4 | 2026-01-02 | 2026-01-08 | 4 | Not Started
Sprint 3 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | New AP Lead | 4 | 2026-01-09 | 2026-01-15 | 4 | Not Started
Sprint 4 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | New AP Lead | 2 | 2026-01-16 | 2026-01-20 | 2 | Not Started
Sprint 5 | Mandate | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | QA | 3 | 2026-01-21 | 2026-01-26 | 3 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement Analysis | BA | 2 | 2026-01-02 | 2026-01-06 | 2 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement | BA | 2 | 2026-01-07 | 2026-01-09 | 2 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 1 | FrontEnd | 5 | 2026-01-12 | 2026-01-19 | 5 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 2 | New AP Lead | 5 | 2026-01-12 | 2026-01-19 | 5 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | QA | Mandate Client Information Maintenance QA - unit-testing | QA | 2 | 2026-01-20 | 2026-01-22 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement Analysis | BA | 2 | 2026-01-12 | 2026-01-14 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement | BA | 2 | 2026-01-15 | 2026-01-19 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 1 | FrontEnd | 5 | 2026-01-20 | 2026-01-27 | 5 | Not Started
Sprint 7 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 2 | New AP Lead | 5 | 2026-01-20 | 2026-01-27 | 5 | Not Started
Sprint 8 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | QA | Mandate Contract Information Maintenance QA - unit-testing | QA | 2 | 2026-01-28 | 2026-01-30 | 2 | Not Started
Sprint 6 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Analysis | BA | 2 | 2026-01-20 | 2026-01-22 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Doc | BA | 2 | 2026-01-23 | 2026-01-27 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 1 | FrontEnd | 5 | 2026-01-28 | 2026-02-04 | 5 | Not Started
Sprint 8 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 2 | Kent | 5 | 2026-01-28 | 2026-02-04 | 5 | Not Started
Sprint 9 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | QA | Mandate Subscription Data Entry QA - unit-testing | QA | 2 | 2026-02-05 | 2026-02-09 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Analysis | BA | 2 | 2026-01-28 | 2026-01-30 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Doc | BA | 2 | 2026-02-02 | 2026-02-04 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 1 | FrontEnd | 5 | 2026-02-05 | 2026-02-12 | 5 | Not Started
Sprint 10 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 2 | Kent | 5 | 2026-02-05 | 2026-02-12 | 5 | Not Started
Sprint 11 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | QA | Mandate Redemption Data Entry QA - unit-testing | QA | 2 | 2026-02-13 | 2026-02-17 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | BA | 1 | 2026-02-05 | 2026-02-06 | 1 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | BA | 2 | 2026-02-09 | 2026-02-11 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | FrontEnd | 2 | 2026-02-12 | 2026-02-16 | 2 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Kent | 2 | 2026-02-12 | 2026-02-16 | 2 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | QA | Mandate Fund NAV Inquiry QA - unit-testing | QA | 2 | 2026-02-17 | 2026-02-19 | 2 | Not Started
Sprint 12 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | BA | 1 | 2026-02-12 | 2026-02-13 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | BA | 2 | 2026-02-16 | 2026-02-18 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | FrontEnd | 2 | 2026-02-19 | 2026-02-23 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Kent | 2 | 2026-02-19 | 2026-02-23 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | QA | Mandate Fund NAV Inquiry QA - unit-testing | QA | 2 | 2026-02-24 | 2026-02-26 | 2 | Not Started
Sprint 5 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement Analysis | BA | 1 | 2026-02-19 | 2026-02-20 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement | BA | 1 | 2026-02-23 | 2026-02-24 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 1 | FrontEnd | 1 | 2026-02-25 | 2026-02-26 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 2 | New AP Lead | 2 | 2026-02-25 | 2026-02-27 | 2 | Not Started
Sprint 7 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | QA | Subscription Details Report QA - unit-testing | QA | 1 | 2026-02-23 | 2026-02-24 | 1 | Not Started
Sprint 7 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement Analysis | BA | 1 | 2026-02-25 | 2026-02-26 | 1 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement | BA | 1 | 2026-02-27 | 2026-03-02 | 1 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 1 | FrontEnd | 1 | 2026-03-03 | 2026-03-04 | 1 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 2 | New AP Lead | 2 | 2026-03-03 | 2026-03-05 | 2 | Not Started
Sprint 9 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | QA | Redemption Details Report QA - unit-testing | QA | 1 | 2026-03-06 | 2026-03-09 | 1 | Not Started
Sprint 9 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement Analysis | BA | 2 | 2026-03-03 | 2026-03-05 | 2 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement | BA | 2 | 2026-03-06 | 2026-03-10 | 2 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 1 | FrontEnd | 3 | 2026-03-11 | 2026-03-16 | 3 | Not Started
Sprint 11 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 2 | New AP Lead | 5 | 2026-03-11 | 2026-03-18 | 5 | Not Started
Sprint 12 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | QA | Mandate NAV Import Process (State Street) QA - unit-testing | QA | 1 | 2026-03-19 | 2026-03-20 | 1 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement Analysis | BA | 1 | 2026-03-11 | 2026-03-12 | 1 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement | BA | 2 | 2026-03-13 | 2026-03-17 | 2 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 2 | 2026-03-18 | 2026-03-20 | 2 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 4 | 2026-03-19 | 2026-03-25 | 4 | Not Started
Sprint 14 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | QA | Generate Mandate Subscription/Redemption Data QA - unit-testing | QA | 2 | 2026-03-26 | 2026-03-30 | 2 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement Analysis | BA | 0.5 | 2026-03-18 | 2026-03-18 | 0.5 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement | BA | 0.5 | 2026-03-19 | 2026-03-19 | 0.5 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 1.5 | 2026-03-21 | 2026-03-23 | 1.5 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 2.5 | 2026-03-26 | 2026-03-30 | 2.5 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | QA | Export Mandate Subscription/Redemption Data QA - unit-testing | QA | 1 | 2026-03-31 | 2026-04-01 | 1 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement Analysis | BA | 2 | 2026-03-20 | 2026-03-24 | 2 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement | BA | 2 | 2026-03-25 | 2026-03-27 | 2 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 2 | 2026-03-27 | 2026-03-31 | 2 | Not Started
Sprint 18 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 5 | 2026-03-31 | 2026-04-07 | 5 | Not Started
Sprint 19 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | QA | Generate SSB Mandate Subscription/Redemption Data QA - unit-testing | QA | 2 | 2026-04-07 | 2026-04-09 | 2 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement Analysis | BA | 0.5 | 2026-03-30 | 2026-03-30 | 0.5 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement | BA | 0.5 | 2026-03-31 | 2026-03-31 | 0.5 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 2 | 2026-04-01 | 2026-04-03 | 2 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 3 | 2026-04-08 | 2026-04-13 | 3 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | QA | Export SSB Mandate Subscription/Redemption Data QA - unit-testing | QA | 1 | 2026-04-13 | 2026-04-14 | 1 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Requirement Analysis | BA | 2 | 2026-04-01 | 2026-04-03 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Data Requirement | BA | 2 | 2026-04-06 | 2026-04-08 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 1 | FrontEnd | 3 | 2026-04-09 | 2026-04-14 | 3 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 2 | Kent | 5 | 2026-04-14 | 2026-04-21 | 5 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | QA | Fund NAV Auto Import Process QA - unit-testing | QA | 1 | 2026-04-22 | 2026-04-23 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Requirement Analysis | BA | 1 | 2026-04-09 | 2026-04-10 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Data Requirement | BA | 2 | 2026-04-13 | 2026-04-15 | 2 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 1 | FrontEnd | 1.5 | 2026-04-16 | 2026-04-17 | 1.5 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 2 | Kent | 2.5 | 2026-04-22 | 2026-04-24 | 2.5 | Not Started
Sprint 17 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | QA | Fund NAV Import Status Inquiry QA - unit-testing | QA | 1 | 2026-04-27 | 2026-04-28 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement Analysis | BA | 1 | 2026-04-16 | 2026-04-17 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement | BA | 1 | 2026-04-20 | 2026-04-21 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 1 | FrontEnd | 1.5 | 2026-04-22 | 2026-04-23 | 1.5 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 2 | Kent | 1.5 | 2026-04-27 | 2026-04-28 | 1.5 | Not Started
Sprint 18 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | QA | Calendar File QA - unit-testing | QA | 1 | 2026-04-29 | 2026-04-30 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement Analysis | BA | 1 | 2026-04-22 | 2026-04-23 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement | BA | 2 | 2026-04-24 | 2026-04-28 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 1 | FrontEnd | 1 | 2026-04-29 | 2026-04-30 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 2 | Kent | 2 | 2026-04-29 | 2026-05-01 | 2 | Not Started
Sprint 19 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | QA | Payment Notice – Management Fee, Custody Fee QA - unit-testing | QA | 1 | 2026-05-04 | 2026-05-05 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement Analysis | BA | 1.5 | 2026-04-29 | 2026-04-30 | 1.5 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement | BA | 1.5 | 2026-05-01 | 2026-05-04 | 1.5 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 1 | FrontEnd | 2 | 2026-05-05 | 2026-05-07 | 2 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 2 | Kent | 2 | 2026-05-05 | 2026-05-07 | 2 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | QA | Validation – Dividend Data QA - unit-testing | QA | 1 | 2026-05-08 | 2026-05-11 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement Analysis | BA | 1 | 2026-05-05 | 2026-05-06 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement | BA | 1 | 2026-05-07 | 2026-05-08 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 1 | FrontEnd | 1 | 2026-05-11 | 2026-05-12 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 2 | Kent | 2 | 2026-05-11 | 2026-05-13 | 2 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | QA | Payment Notice – Dividend Distribution QA - unit-testing | QA | 1 | 2026-05-14 | 2026-05-15 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement Analysis | BA | 1 | 2026-05-11 | 2026-05-12 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement | BA | 1 | 2026-05-13 | 2026-05-14 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 1 | FrontEnd | 1 | 2026-05-15 | 2026-05-18 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 2 | Kent | 2 | 2026-05-15 | 2026-05-19 | 2 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | QA | Payment Notice – Dividend Instruction Printing QA - unit-testing | QA | 1 | 2026-05-20 | 2026-05-21 | 1 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Analysis | BA | 2 | 2026-05-15 | 2026-05-19 | 2 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Doc | BA | 2 | 2026-05-20 | 2026-05-22 | 2 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 1 | FrontEnd | 3.5 | 2026-05-25 | 2026-05-28 | 3.5 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 2 | New AP Lead | 4 | 2026-05-25 | 2026-05-29 | 4 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | QA | Mandate Data Generation Process QA - unit-testing | QA | 1.5 | 2026-06-01 | 2026-06-02 | 1.5 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Analysis | BA | 2 | 2026-05-25 | 2026-05-27 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Doc | BA | 2 | 2026-05-28 | 2026-06-01 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 1 | FrontEnd | 2.5 | 2026-06-02 | 2026-06-04 | 2.5 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 2 | Kent | 4.5 | 2026-06-02 | 2026-06-08 | 4.5 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | QA | Mandate Data Maintenance Process QA - unit-testing | QA | 2 | 2026-06-09 | 2026-06-11 | 2 | Not Started
Sprint 11 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Analysis | BA | 1 | 2026-06-02 | 2026-06-03 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Doc | BA | 1 | 2026-06-04 | 2026-06-05 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 1 | FrontEnd | 1 | 2026-06-08 | 2026-06-09 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 2 | New AP Lead | 2 | 2026-06-08 | 2026-06-10 | 2 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | QA | Subscription/Redemption Posting Details Report QA - unit-testing | QA | 1 | 2026-06-11 | 2026-06-12 | 1 | Not Started
Sprint 12 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Analysis | BA | 1 | 2026-06-08 | 2026-06-09 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Doc | BA | 1 | 2026-06-10 | 2026-06-11 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 1 | FrontEnd | 3 | 2026-06-12 | 2026-06-17 | 3 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 2 | New AP Lead | 4 | 2026-06-12 | 2026-06-18 | 4 | Not Started
Sprint 14 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | QA | Mandate Contract Asset Movement Report QA - unit-testing | QA | 2 | 2026-06-19 | 2026-06-23 | 2 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Analysis | BA | 1 | 2026-06-12 | 2026-06-15 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Doc | BA | 1 | 2026-06-16 | 2026-06-17 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 1 | FrontEnd | 2 | 2026-06-18 | 2026-06-22 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 2 | Kent | 2 | 2026-06-18 | 2026-06-22 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | QA | PAMS Inventory File Export QA - unit-testing | QA | 1 | 2026-06-23 | 2026-06-24 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement Analysis | BA | 1 | 2026-06-18 | 2026-06-19 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement | BA | 1 | 2026-06-22 | 2026-06-23 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 1 | FrontEnd | 1 | 2026-06-24 | 2026-06-25 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 2 | New AP Lead | 4 | 2026-06-24 | 2026-06-30 | 4 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | QA | Mandate Stock Stop-Loss Control Table QA - unit-testing | QA | 1 | 2026-07-01 | 2026-07-02 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Analysis | BA | 1 | 2026-06-24 | 2026-06-25 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Doc | BA | 1 | 2026-06-26 | 2026-06-29 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | Development | Report - 基金規模報表查詢 - Development | Kent | 3 | 2026-06-30 | 2026-07-03 | 3 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | QA | Report - 基金規模報表查詢 QA - unit-testing | QA | 1 | 2026-07-06 | 2026-07-07 | 1 | Not Started
Sprint 22 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Analysis | BA | 1 | 2026-06-30 | 2026-07-01 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Doc | BA | 1 | 2026-07-02 | 2026-07-03 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | Development | Taiwan Ratings Reporting Data - Development | Kent | 3 | 2026-07-06 | 2026-07-09 | 3 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | QA | Taiwan Ratings Reporting Data QA - unit-testing | QA | 1 | 2026-07-10 | 2026-07-13 | 1 | Not Started
Sprint 23 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Analysis | BA | 1 | 2026-07-06 | 2026-07-07 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Doc | BA | 1 | 2026-07-08 | 2026-07-09 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | Development | Mutual Fund Asset Size Export Process - Development | New AP Lead | 3 | 2026-07-10 | 2026-07-15 | 3 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | QA | Mutual Fund Asset Size Export Process - unit-testing | QA | 1 | 2026-07-16 | 2026-07-17 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement Analysis | BA | 0.5 | 2026-07-10 | 2026-07-10 | 0.5 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement | BA | 0.5 | 2026-07-13 | 2026-07-13 | 0.5 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 1 | FrontEnd | 3 | 2026-07-14 | 2026-07-17 | 3 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 2 | Kent | 4 | 2026-07-14 | 2026-07-20 | 4 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | QA | Generate Shareholder Meeting Data QA - unit-testing | QA | 2 | 2026-07-21 | 2026-07-23 | 2 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement Analysis | BA | 0.5 | 2026-07-14 | 2026-07-14 | 0.5 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement | BA | 0.5 | 2026-07-15 | 2026-07-15 | 0.5 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 1 | FrontEnd | 1 | 2026-07-16 | 2026-07-17 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 2 | New AP Lead | 3 | 2026-07-16 | 2026-07-21 | 3 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | QA | Generate Memo for Assigned Personnel/Function QA - unit-testing | QA | 1 | 2026-07-22 | 2026-07-23 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement Analysis | BA | 0.5 | 2026-07-16 | 2026-07-16 | 0.5 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement | BA | 0.5 | 2026-07-17 | 2026-07-17 | 0.5 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 1 | FrontEnd | 2 | 2026-07-20 | 2026-07-22 | 2 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 2 | Kent | 2 | 2026-07-21 | 2026-07-23 | 2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | QA | Director/Supervisor Election Report/Function QA - unit-testing | QA | 1 | 2026-07-24 | 2026-07-27 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement Analysis | BA | 0.2 | 2026-07-20 | 2026-07-20 | 0.2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement | BA | 0.3 | 2026-07-21 | 2026-07-21 | 0.3 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 1 | FrontEnd | 0.2 | 2026-07-23 | 2026-07-23 | 0.2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 2 | New AP Lead | 0.5 | 2026-07-23 | 2026-07-23 | 0.5 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | QA | Shareholder Meeting Fund Attendance Details Report QA - unit-testing | QA | 0.3 | 2026-07-24 | 2026-07-24 | 0.3 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Requirement Analysis | BA | 0.2 | 2026-07-22 | 2026-07-22 | 0.2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Report Requirement | BA | 0.3 | 2026-07-23 | 2026-07-23 | 0.3 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details Report - Development 1 | FrontEnd | 0.2 | 2026-07-24 | 2026-07-24 | 0.2 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details - Development 2 | Kent | 0.5 | 2026-07-24 | 2026-07-24 | 0.5 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | QA | Shareholder Meeting Missing Election Report Details QA - unit-testing | QA | 0.3 | 2026-07-27 | 2026-07-27 | 0.3 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement Analysis | BA | 1 | 2026-07-24 | 2026-07-27 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement | BA | 1 | 2026-07-28 | 2026-07-29 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 1 | FrontEnd | 1.5 | 2026-07-30 | 2026-07-31 | 1.5 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 2 | Kent | 2.5 | 2026-07-30 | 2026-08-03 | 2.5 | Not Started
Sprint 30 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | QA | Stock Basic Data Maintenance QA - unit-testing | QA | 1 | 2026-08-04 | 2026-08-05 | 1 | Not Started
Formulas:
FINISH = WORKDAY([START],[DURATION])
START = WORKDAY([FINISH, row above],1)
START = [FINISH, row above]

## Sprint Calendar
Sprint | Start Date | End Date
Sprint 1 | 2025-11-24 | 2025-12-07
Sprint 2 | 2025-12-08 | 2025-12-21
Sprint 3 | 2025-12-22 | 2026-01-04
Sprint 4 | 2026-01-05 | 2026-01-18
Sprint 5 | 2026-01-19 | 2026-02-01
Sprint 6 | 2026-02-02 | 2026-02-15
Sprint 7 | 2026-02-16 | 2026-03-01
Sprint 8 | 2026-03-02 | 2026-03-15
Sprint 9 | 2026-03-16 | 2026-03-29
Sprint 10 | 2026-03-30 | 2026-04-12
Sprint 11 | 2026-04-13 | 2026-04-26
Sprint 12 | 2026-04-27 | 2026-05-10
Sprint 13 | 2026-05-11 | 2026-05-24
Sprint 14 | 2026-05-25 | 2026-06-07
Sprint 15 | 2026-06-08 | 2026-06-21
Sprint 16 | 2026-06-22 | 2026-07-05
Sprint 17 | 2026-07-06 | 2026-07-19
Sprint 18 | 2026-07-20 | 2026-08-02
Sprint 19 | 2026-08-03 | 2026-08-16
Sprint 20 | 2026-08-17 | 2026-08-30
Sprint 21 | 2026-08-31 | 2026-09-13
Sprint 22 | 2026-09-14 | 2026-09-27
Sprint 23 | 2026-09-28 | 2026-10-11
Sprint 24 | 2026-10-12 | 2026-10-25
Sprint 25 | 2026-10-26 | 2026-11-08
Sprint 26 | 2026-11-09 | 2026-11-22
Sprint 27 | 2026-11-23 | 2026-12-06
Sprint 28 | 2026-12-07 | 2026-12-20
Sprint 29 | 2026-12-21 | 2026-12-31
Sprint 30 | 2027-01-01 | 2027-01-15
Sprint 31 | 2027-01-18 | 2027-01-29
Sprint 32 | 2027-02-01 | 2027-02-19
Sprint 33 | 2027-02-22 | 2027-03-05

## Project Planning (2)
DMS Development
| TOTAL TASKS | 199 |  |  | DURATION | #DIV/0! |  | Overall Progress |  |  | Team Member | FTE
| Completed | 4 |  |  | START | #DIV/0! |  |  |  | 15 | BA | 1
| In progress | 5 |  |  | FINISH | #DIV/0! |  |  |  | 408 | Kent | 1
| Not Started | 190 | [8 empty] | QA | 1
[8 empty] | 100% |  | 3.676% | AP Lead | 1
SPRINT | EPIC | FEATURE | TASKS | STORIES | RESPONSIBLE | Man Day Required | START | FINISH | DURATION | STATUS
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | Kent | 3 | 2025-09-15 | 2025-09-18 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | Kent | 3 | 2025-09-19 | 2025-09-24 | 3 | Completed
Sprint 5 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Detail Requirement Analysis | BA | 3 | 2026-01-01 | 2026-01-06 | 3 | In progress
Sprint 5 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Document Detail Requirement | BA | 3 | 2026-01-07 | 2026-01-12 | 3 | In progress
Sprint 6 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Balance Detail Requirement Analysis | BA | 1.5 | 2026-01-13 | 2026-01-14 | 1.5 | In progress
Sprint 6 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Document Detail Requirement | BA | 1.5 | 2026-01-15 | 2026-01-16 | 1.5 | In progress
Sprint 8 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Detail Requirement Analysis | BA | 1.5 | 2026-01-19 | 2026-01-20 | 1.5 | In progress
Sprint 8 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Document Detail Requirement | BA | 1.5 | 2026-01-21 | 2026-01-22 | 1.5 | In progress
Sprint 9 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Detail Requirement Analysis | BA | 1.5 | 2026-01-23 | 2026-01-26 | 1.5 | In progress
Sprint 9 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Document Detail Requirement | BA | 1.5 | 2026-01-27 | 2026-01-28 | 1.5 | In progress
Sprint 10 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | BA | 3 | 2026-01-29 | 2026-02-03 | 3 | Not Started
Sprint 10 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | BA | 3 | 2026-02-04 | 2026-02-09 | 3 | Not Started
Sprint 12 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement Analysis | BA | 2 | 2026-02-10 | 2026-02-12 | 2 | Not Started
Sprint 12 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement | BA | 2 | 2026-02-13 | 2026-02-17 | 2 | Not Started
Sprint 12 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement Analysis | BA | 2 | 2026-02-18 | 2026-02-20 | 2 | Not Started
Sprint 13 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement | BA | 2 | 2026-02-23 | 2026-02-25 | 2 | Not Started
Sprint 14 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Analysis | BA | 2 | 2026-02-26 | 2026-03-02 | 2 | Not Started
Sprint 14 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Doc | BA | 2 | 2026-03-03 | 2026-03-05 | 2 | Not Started
Sprint 15 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Analysis | BA | 2 | 2026-03-06 | 2026-03-10 | 2 | Not Started
Sprint 15 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Doc | BA | 2 | 2026-03-11 | 2026-03-13 | 2 | Not Started
Sprint 16 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | BA | 1 | 2026-03-16 | 2026-03-17 | 1 | Not Started
Sprint 16 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | BA | 2 | 2026-03-18 | 2026-03-20 | 2 | Not Started
Sprint 17 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | BA | 1 | 2026-03-23 | 2026-03-24 | 1 | Not Started
Sprint 17 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | BA | 2 | 2026-03-25 | 2026-03-27 | 2 | Not Started
Sprint 18 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement Analysis | BA | 1 | 2026-03-30 | 2026-03-31 | 1 | Not Started
Sprint 18 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement | BA | 1 | 2026-04-01 | 2026-04-02 | 1 | Not Started
Sprint 19 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement Analysis | BA | 1 | 2026-04-03 | 2026-04-06 | 1 | Not Started
Sprint 19 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement | BA | 1 | 2026-04-07 | 2026-04-08 | 1 | Not Started
Sprint 20 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement Analysis | BA | 2 | 2026-04-09 | 2026-04-13 | 2 | Not Started
Sprint 20 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement | BA | 2 | 2026-04-14 | 2026-04-16 | 2 | Not Started
Sprint 20 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement Analysis | BA | 1 | 2026-04-17 | 2026-04-20 | 1 | Not Started
Sprint 21 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement | BA | 2 | 2026-04-21 | 2026-04-23 | 2 | Not Started
Sprint 22 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement Analysis | BA | 0.5 | 2026-04-24 | 2026-04-24 | 0.5 | Not Started
Sprint 22 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement | BA | 0.5 | 2026-04-27 | 2026-04-27 | 0.5 | Not Started
Sprint 1 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement Analysis | BA | 2 | 2026-04-28 | 2026-04-30 | 2 | Not Started
Sprint 1 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement | BA | 2 | 2026-05-01 | 2026-05-05 | 2 | Not Started
Sprint 2 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement Analysis | BA | 0.5 | 2026-05-06 | 2026-05-06 | 0.5 | Not Started
Sprint 3 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement | BA | 0.5 | 2026-05-07 | 2026-05-07 | 0.5 | Not Started
Sprint 5 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Requirement Analysis | BA | 2 | 2026-05-08 | 2026-05-12 | 2 | Not Started
Sprint 6 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Data Requirement | BA | 2 | 2026-05-13 | 2026-05-15 | 2 | Not Started
Sprint 7 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Requirement Analysis | BA | 1 | 2026-05-18 | 2026-05-19 | 1 | Not Started
Sprint 8 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Data Requirement | BA | 2 | 2026-05-20 | 2026-05-22 | 2 | Not Started
Sprint 8 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement Analysis | BA | 1 | 2026-05-25 | 2026-05-26 | 1 | Not Started
Sprint 9 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement | BA | 1 | 2026-05-27 | 2026-05-28 | 1 | Not Started
Sprint 10 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement Analysis | BA | 1 | 2026-05-29 | 2026-06-01 | 1 | Not Started
Sprint 10 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement | BA | 2 | 2026-06-02 | 2026-06-04 | 2 | Not Started
#N/A | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement Analysis | BA | 1.5 | 2026-06-05 | 2026-06-08 | 1.5 | Not Started
#N/A | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement | BA | 1.5 | 2026-06-09 | 2026-06-10 | 1.5 | Not Started
#N/A | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement Analysis | BA | 1 | 2026-06-11 | 2026-06-12 | 1 | Not Started
#N/A | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement | BA | 1 | 2026-06-15 | 2026-06-16 | 1 | Not Started
#N/A | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement Analysis | BA | 1 | 2026-06-17 | 2026-06-18 | 1 | Not Started
#N/A | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement | BA | 1 | 2026-06-19 | 2026-06-22 | 1 | Not Started
#N/A | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Analysis | BA | 2 | 2026-06-23 | 2026-06-25 | 2 | Not Started
#N/A | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Doc | BA | 2 | 2026-06-26 | 2026-06-30 | 2 | Not Started
Sprint 5 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Analysis | BA | 2 | 2026-07-01 | 2026-07-03 | 2 | Not Started
Sprint 5 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Doc | BA | 2 | 2026-07-06 | 2026-07-08 | 2 | Not Started
Sprint 7 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Analysis | BA | 1 | 2026-07-09 | 2026-07-10 | 1 | Not Started
Sprint 8 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Doc | BA | 1 | 2026-07-13 | 2026-07-14 | 1 | Not Started
Sprint 9 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Analysis | BA | 1 | 2026-07-15 | 2026-07-16 | 1 | Not Started
Sprint 9 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Doc | BA | 1 | 2026-07-17 | 2026-07-20 | 1 | Not Started
Sprint 11 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Analysis | BA | 1 | 2026-07-21 | 2026-07-22 | 1 | Not Started
Sprint 11 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Doc | BA | 1 | 2026-07-23 | 2026-07-24 | 1 | Not Started
Sprint 12 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement Analysis | BA | 1 | 2026-07-27 | 2026-07-28 | 1 | Not Started
Sprint 13 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement | BA | 1 | 2026-07-29 | 2026-07-30 | 1 | Not Started
Sprint 13 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Analysis | BA | 1 | 2026-07-31 | 2026-08-03 | 1 | Not Started
Sprint 13 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Doc | BA | 1 | 2026-08-04 | 2026-08-05 | 1 | Not Started
Sprint 15 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Analysis | BA | 1 | 2026-08-06 | 2026-08-07 | 1 | Not Started
Sprint 15 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Doc | BA | 1 | 2026-08-10 | 2026-08-11 | 1 | Not Started
Sprint 16 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Analysis | BA | 1 | 2026-08-12 | 2026-08-13 | 1 | Not Started
Sprint 17 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Doc | BA | 1 | 2026-08-14 | 2026-08-17 | 1 | Not Started
Sprint 18 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement Analysis | BA | 0.5 | 2026-08-18 | 2026-08-18 | 0.5 | Not Started
Sprint 18 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement | BA | 0.5 | 2026-08-19 | 2026-08-19 | 0.5 | Not Started
Sprint 19 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement Analysis | BA | 0.5 | 2026-08-20 | 2026-08-20 | 0.5 | Not Started
Sprint 20 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement | BA | 0.5 | 2026-08-21 | 2026-08-21 | 0.5 | Not Started
Sprint 21 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement Analysis | BA | 0.5 | 2026-08-24 | 2026-08-24 | 0.5 | Not Started
Sprint 21 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement | BA | 0.5 | 2026-08-25 | 2026-08-25 | 0.5 | Not Started
Sprint 22 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement Analysis | BA | 0.2 | 2026-08-26 | 2026-08-26 | 0.2 | Not Started
Sprint 22 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement | BA | 0.3 | 2026-08-27 | 2026-08-27 | 0.3 | Not Started
Sprint 23 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Requirement Analysis | BA | 0.2 | 2026-08-28 | 2026-08-28 | 0.2 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Report Requirement | BA | 0.3 | 2026-08-31 | 2026-08-31 | 0.3 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement Analysis | BA | 1 | 2026-09-01 | 2026-09-02 | 1 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement | BA | 1 | 2026-09-03 | 2026-09-04 | 1 | Not Started
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Kent | 5 | 2026-09-07 | 2026-09-14 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Kent | 5 | 2026-09-15 | 2026-09-22 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Kent | 5 | 2026-09-23 | 2026-09-30 | 5 | Completed
Sprint 5 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Kent | 3 | 2025-11-24 | 2025-11-27 | 3 | In progress
Sprint 5 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Kent | 5 | 2025-11-28 | 2025-12-05 | 5 | Not Started
Sprint 5 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Kent | 2 | 2025-12-08 | 2025-12-10 | 2 | Not Started
Sprint 7 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 1 | Kent | 4 | 2025-11-28 | 2025-12-04 | 4 | Not Started
Sprint 7 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 2 | Kent | 4 | 2025-12-05 | 2025-12-11 | 4 | Not Started
Sprint 8 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 1 | Kent | 4 | 2025-12-11 | 2025-12-17 | 4 | Not Started
Sprint 9 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 2 | Kent | 4 | 2025-12-18 | 2025-12-24 | 4 | Not Started
Sprint 10 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 1 | Kent | 4 | 2025-12-12 | 2025-12-18 | 4 | Not Started
Sprint 10 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 2 | Kent | 4 | 2025-12-19 | 2025-12-25 | 4 | Not Started
Sprint 14 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 1 | Kent | 5 | 2025-12-26 | 2026-01-02 | 5 | Not Started
Sprint 14 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 2 | Kent | 5 | 2026-01-05 | 2026-01-12 | 5 | Not Started
Sprint 15 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 1 | Kent | 5 | 2026-01-13 | 2026-01-20 | 5 | Not Started
Sprint 15 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 2 | Kent | 5 | 2026-01-21 | 2026-01-28 | 5 | Not Started
Sprint 17 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | Kent | 2 | 2026-01-29 | 2026-02-02 | 2 | Not Started
Sprint 17 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Kent | 2 | 2026-02-03 | 2026-02-05 | 2 | Not Started
Sprint 18 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | Kent | 2 | 2026-02-06 | 2026-02-10 | 2 | Not Started
Sprint 18 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Kent | 2 | 2026-02-11 | 2026-02-13 | 2 | Not Started
Sprint 6 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 1 | Kent | 3 | 2026-02-16 | 2026-02-19 | 3 | Not Started
Sprint 6 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 2 | Kent | 5 | 2026-02-20 | 2026-02-27 | 5 | Not Started
Sprint 8 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 1 | Kent | 1.5 | 2026-03-02 | 2026-03-03 | 1.5 | Not Started
Sprint 8 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 2 | Kent | 2.5 | 2026-03-04 | 2026-03-06 | 2.5 | Not Started
Sprint 9 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 1 | Kent | 1.5 | 2026-03-09 | 2026-03-10 | 1.5 | Not Started
Sprint 9 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 2 | Kent | 1.5 | 2026-03-11 | 2026-03-12 | 1.5 | Not Started
Sprint 10 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 1 | Kent | 1 | 2026-03-13 | 2026-03-16 | 1 | Not Started
Sprint 11 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 2 | Kent | 2 | 2026-03-17 | 2026-03-19 | 2 | Not Started
#N/A | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 1 | Kent | 2 | 2026-03-20 | 2026-03-24 | 2 | Not Started
#N/A | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 2 | Kent | 2 | 2026-03-25 | 2026-03-27 | 2 | Not Started
#N/A | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 1 | Kent | 1 | 2026-03-30 | 2026-03-31 | 1 | Not Started
#N/A | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 2 | Kent | 2 | 2026-04-01 | 2026-04-03 | 2 | Not Started
#N/A | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 1 | Kent | 1 | 2026-04-06 | 2026-04-07 | 1 | Not Started
#N/A | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 2 | Kent | 2 | 2026-04-08 | 2026-04-10 | 2 | Not Started
Sprint 15 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | Development | Taiwan Ratings Reporting Data - Development | Kent | 3 | 2026-04-13 | 2026-04-16 | 3 | Not Started
Sprint 17 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | Development | Mutual Fund Asset Size Export Process - Development | Kent | 3 | 2026-04-17 | 2026-04-22 | 3 | Not Started
Sprint 6 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | QA | 3 | 2026-04-23 | #DIV/0! | #DIV/0! | Not Started
Sprint 7 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | QA | Maintain Distributable Balance QA - unit testing | QA | 3 | #DIV/0! | #DIV/0! | 3 | Not Started
Sprint 9 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | QA | Domestic Dividend Information Inquiry QA - unit testing | QA | 2 | #DIV/0! | #DIV/0! | 2 | Not Started
Sprint 10 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | QA | Upload Domestic Dividend Composition Info to EC QA - unit testing | QA | 2 | #DIV/0! | #DIV/0! | 2 | Not Started
Sprint 15 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | QA | Mandate Subscription Data Entry QA - unit-testing | QA | 2 | #DIV/0! | #DIV/0! | 2 | Not Started
Sprint 16 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | QA | Mandate Redemption Data Entry QA - unit-testing | QA | 2 | #DIV/0! | #DIV/0! | 2 | Not Started
Sprint 17 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | QA | Mandate Fund NAV Inquiry QA - unit-testing | QA | 2 | #DIV/0! | #DIV/0! | 2 | Not Started
Sprint 18 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | QA | Mandate Fund NAV Inquiry QA - unit-testing | QA | 2 | #DIV/0! | #DIV/0! | 2 | Not Started
Sprint 7 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | QA | Fund NAV Auto Import Process QA - unit-testing | QA | 1 | #DIV/0! | #DIV/0! | 1 | Not Started
Sprint 8 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | QA | Fund NAV Import Status Inquiry QA - unit-testing | QA | 1 | #DIV/0! | #DIV/0! | 1 | Not Started
Sprint 10 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | QA | Calendar File QA - unit-testing | QA | 1 | #DIV/0! | #DIV/0! | 1 | Not Started
Sprint 11 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | QA | Payment Notice – Management Fee, Custody Fee QA - unit-testing | QA | 1 | #DIV/0! | #DIV/0! | 1 | Not Started
#N/A | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | QA | Validation – Dividend Data QA - unit-testing | QA | 1 | #DIV/0! | #DIV/0! | 1 | Not Started
#N/A | Mandate | FAS 893 Payment Notice – Dividend Distribution | QA | Payment Notice – Dividend Distribution QA - unit-testing | QA | 1 | #DIV/0! | #DIV/0! | 1 | Not Started
#N/A | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | QA | Payment Notice – Dividend Instruction Printing QA - unit-testing | QA | 1 | #DIV/0! | #DIV/0! | 1 | Not Started
Sprint 16 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | QA | Taiwan Ratings Reporting Data QA - unit-testing | QA | 1 | #DIV/0! | #DIV/0! | 1 | Not Started
Sprint 17 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | QA | Mutual Fund Asset Size Export Process - unit-testing | QA | 1 | #DIV/0! | #DIV/0! | 1 | Not Started
Sprint 11 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | New AP Lead | 4 | 2026-01-01 | 2026-01-07 | 4 | Not Started
Sprint 11 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | New AP Lead | 4 | 2026-01-08 | 2026-01-14 | 4 | Not Started
Sprint 11 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | New AP Lead | 2 | 2026-01-15 | 2026-01-19 | 2 | Not Started
Sprint 12 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 1 | New AP Lead | 5 | 2026-01-20 | 2026-01-27 | 5 | Not Started
Sprint 12 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 2 | New AP Lead | 5 | 2026-01-28 | 2026-02-04 | 5 | Not Started
Sprint 13 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 1 | New AP Lead | 5 | 2026-02-05 | 2026-02-12 | 5 | Not Started
Sprint 13 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 2 | New AP Lead | 5 | 2026-02-13 | 2026-02-20 | 5 | Not Started
Sprint 19 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 1 | New AP Lead | 1 | 2026-02-23 | 2026-02-24 | 1 | Not Started
Sprint 19 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 2 | New AP Lead | 2 | 2026-02-25 | 2026-02-27 | 2 | Not Started
Sprint 20 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 1 | New AP Lead | 1 | 2026-03-02 | 2026-03-03 | 1 | Not Started
Sprint 20 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 2 | New AP Lead | 2 | 2026-03-04 | 2026-03-06 | 2 | Not Started
Sprint 20 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 1 | New AP Lead | 3 | 2026-03-09 | 2026-03-12 | 3 | Not Started
Sprint 20 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 2 | New AP Lead | 5 | 2026-03-13 | 2026-03-20 | 5 | Not Started
Sprint 21 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 1 | New AP Lead | 2 | 2026-03-23 | 2026-03-25 | 2 | Not Started
Sprint 21 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 4 | 2026-03-26 | 2026-04-01 | 4 | Not Started
Sprint 1 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 1 | New AP Lead | 1.5 | 2026-04-02 | 2026-04-03 | 1.5 | Not Started
Sprint 1 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 2.5 | 2026-04-06 | 2026-04-08 | 2.5 | Not Started
Sprint 18 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 1 | Kent | 3 | 2026-04-09 | 2026-04-14 | 3 | Not Started
Sprint 19 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 2 | Kent | 4 | 2026-04-15 | 2026-04-21 | 4 | Not Started
Sprint 20 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 1 | Kent | 1 | 2026-04-22 | 2026-04-23 | 1 | Not Started
Sprint 20 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 2 | Kent | 3 | 2026-04-24 | 2026-04-29 | 3 | Not Started
Sprint 21 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 1 | Kent | 2 | 2026-04-30 | 2026-05-04 | 2 | Not Started
Sprint 22 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 2 | Kent | 2 | 2026-05-05 | 2026-05-07 | 2 | Not Started
Sprint 23 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 1 | Kent | 0.2 | 2026-05-08 | 2026-05-08 | 0.2 | Not Started
Sprint 23 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 2 | Kent | 0.5 | 2026-05-11 | 2026-05-11 | 0.5 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details Report - Development 1 | Kent | 0.2 | 2026-05-12 | 2026-05-12 | 0.2 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details - Development 2 | Kent | 0.5 | 2026-05-13 | 2026-05-13 | 0.5 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 1 | Kent | 1.5 | 2026-05-14 | 2026-05-15 | 1.5 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 2 | Kent | 2.5 | 2026-05-18 | 2026-05-20 | 2.5 | Not Started
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | Kent | 3 | 2026-05-21 | 2026-05-26 | 3 | Completed
Sprint 2 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 1 | New AP Lead | 2 | 2026-05-27 | 2026-05-29 | 2 | Not Started
Sprint 2 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 5 | 2026-06-01 | 2026-06-08 | 5 | Not Started
Sprint 4 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 1 | New AP Lead | 2 | 2026-06-09 | 2026-06-11 | 2 | Not Started
Sprint 4 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 3 | 2026-06-12 | 2026-06-17 | 3 | Not Started
Sprint 3 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 1 | New AP Lead | 3.5 | 2026-06-18 | 2026-06-23 | 3.5 | Not Started
Sprint 4 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 2 | New AP Lead | 4 | 2026-06-24 | 2026-06-30 | 4 | Not Started
Sprint 6 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 1 | New AP Lead | 2.5 | 2026-07-01 | 2026-07-03 | 2.5 | Not Started
Sprint 6 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 2 | New AP Lead | 4.5 | 2026-07-06 | 2026-07-10 | 4.5 | Not Started
Sprint 8 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 1 | New AP Lead | 1 | 2026-07-13 | 2026-07-14 | 1 | Not Started
Sprint 8 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 2 | New AP Lead | 2 | 2026-07-15 | 2026-07-17 | 2 | Not Started
Sprint 10 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 1 | New AP Lead | 3 | 2026-07-20 | 2026-07-23 | 3 | Not Started
Sprint 10 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 2 | New AP Lead | 4 | 2026-07-24 | 2026-07-30 | 4 | Not Started
Sprint 11 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 1 | New AP Lead | 2 | 2026-07-31 | 2026-08-04 | 2 | Not Started
Sprint 12 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 2 | New AP Lead | 2 | 2026-08-05 | 2026-08-07 | 2 | Not Started
Sprint 13 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 1 | New AP Lead | 1 | 2026-08-10 | 2026-08-11 | 1 | Not Started
Sprint 13 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 2 | New AP Lead | 4 | 2026-08-12 | 2026-08-18 | 4 | Not Started
Sprint 14 | Mandate | Report - 基金規模報表查詢 | Development | Report - 基金規模報表查詢 - Development | New AP Lead | 3 | 2026-08-19 | 2026-08-24 | 3 | Not Started
Sprint 12 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | QA | Mandate Client Information Maintenance QA - unit-testing | QA | 2 | 2026-08-24 | 2026-08-26 | 2 | Not Started
Sprint 14 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | QA | Mandate Contract Information Maintenance QA - unit-testing | QA | 2 | 2026-08-27 | 2026-08-31 | 2 | Not Started
Sprint 4 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | QA | Mandate Data Generation Process QA - unit-testing | QA | 1.5 | 2026-09-01 | 2026-09-02 | 1.5 | Not Started
Sprint 7 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | QA | Mandate Data Maintenance Process QA - unit-testing | QA | 2 | 2026-09-03 | 2026-09-07 | 2 | Not Started
Sprint 8 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | QA | Subscription/Redemption Posting Details Report QA - unit-testing | QA | 1 | 2026-09-08 | 2026-09-09 | 1 | Not Started
Sprint 10 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | QA | Mandate Contract Asset Movement Report QA - unit-testing | QA | 2 | 2026-09-10 | 2026-09-14 | 2 | Not Started
Sprint 12 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | QA | PAMS Inventory File Export QA - unit-testing | QA | 1 | 2026-09-15 | 2026-09-16 | 1 | Not Started
Sprint 13 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | QA | Mandate Stock Stop-Loss Control Table QA - unit-testing | QA | 1 | 2026-09-17 | 2026-09-18 | 1 | Not Started
Sprint 14 | Mandate | Report - 基金規模報表查詢 | QA | Report - 基金規模報表查詢 QA - unit-testing | QA | 1 | 2026-09-21 | 2026-09-22 | 1 | Not Started
Sprint 11 | Mandate | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | QA | 3 | 2026-09-23 | 2026-09-28 | 3 | Not Started
Sprint 19 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | QA | Subscription Details Report QA - unit-testing | QA | 1 | 2026-09-29 | 2026-09-30 | 1 | Not Started
Sprint 20 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | QA | Redemption Details Report QA - unit-testing | QA | 1 | 2026-10-01 | 2026-10-02 | 1 | Not Started
Sprint 20 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | QA | Mandate NAV Import Process (State Street) QA - unit-testing | QA | 1 | 2026-10-05 | 2026-10-06 | 1 | Not Started
Sprint 21 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | QA | Generate Mandate Subscription/Redemption Data QA - unit-testing | QA | 2 | 2026-10-07 | 2026-10-09 | 2 | Not Started
Sprint 2 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | QA | Export Mandate Subscription/Redemption Data QA - unit-testing | QA | 1 | 2026-10-12 | 2026-10-13 | 1 | Not Started
Sprint 2 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | QA | Generate SSB Mandate Subscription/Redemption Data QA - unit-testing | QA | 2 | 2026-10-14 | 2026-10-16 | 2 | Not Started
Sprint 5 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | QA | Export SSB Mandate Subscription/Redemption Data QA - unit-testing | QA | 1 | 2026-10-19 | 2026-10-20 | 1 | Not Started
Sprint 19 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | QA | Generate Shareholder Meeting Data QA - unit-testing | Kent | 2 | 2026-10-21 | 2026-10-23 | 2 | Not Started
Sprint 21 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | QA | Generate Memo for Assigned Personnel/Function QA - unit-testing | Kent | 1 | 2026-10-26 | 2026-10-27 | 1 | Not Started
Sprint 22 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | QA | Director/Supervisor Election Report/Function QA - unit-testing | Kent | 1 | 2026-10-28 | 2026-10-29 | 1 | Not Started
Sprint 23 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | QA | Shareholder Meeting Fund Attendance Details Report QA - unit-testing | Kent | 0.3 | 2026-10-30 | 2026-10-30 | 0.3 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | QA | Shareholder Meeting Missing Election Report Details QA - unit-testing | Kent | 0.3 | 2026-11-02 | 2026-11-02 | 0.3 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | QA | Stock Basic Data Maintenance QA - unit-testing | Kent | 1 | 2026-11-03 | 2026-11-04 | 1 | Not Started
Formulas:
FINISH = WORKDAY([START],[DURATION])
START = WORKDAY([FINISH, row above],1)

## TimeLine_Ver2
App | Module | Code | Chinese Name | Features | Detailed req est. | Dev + Unit test est. | Detailed req est. 2 | Dev + Unit test est.3 | Full Time Estimate(%) | Status | Req ETA | DEV ETA | UAT ETA
DMS | Shareholders' Meeting & Management |  |  | Data mapping | 3 | 5 | 2025-10-01 | 2025-10-30 | 70% | In Unit Testing | 2025-10-07 | 2025-10-16
DMS | Shareholders' Meeting & Management |  |  | Data Migration | 3 | 5 | 2025-10-01 | 2025-10-30 | 70% | In Unit Testing | 2025-10-22 | 2025-10-31
DMS | Shareholders' Meeting & Management |  |  | Create Tables in DB | 3 | 5 | 2025-10-01 | 2025-10-30 | 70% | In Unit Testing | 2025-11-06 | 2025-11-17
DMS | Shareholders' Meeting & Management | 7911、79161 | 股東會資料產生 | Generate Shareholder Meeting Data | 1 | 9 | #REF! | #REF! | 70% | In Unit Testing | 2025-11-18 | 2025-12-04
DMS | Shareholders' Meeting & Management | 7931 | 指派人員產生簽呈 | Generate Memo for Assigned Personnel/Function | 1 | 5 | #REF! | #REF! | 100% | In Development | 2025-12-05 | 2025-12-12
DMS | Shareholders' Meeting & Management | 7942 | 董監改補選報告 | Director/Supervisor Election Report/Function | 1 | 5 | #REF! | #REF! | 100% |  | 2025-12-15 | 2025-12-22
DMS | Shareholders' Meeting & Management | 7951 | 股東會基金出席明細表 | Shareholder Meeting Fund Attendance Details Report | 0.5 | 1 | #REF! | #REF! | 100% |  | 2025-12-22 | 2025-12-23
DMS | Shareholders' Meeting & Management | 7953 | 股東會董監改選缺交報告明細表 | Shareholder Meeting Missing Election Report Details | 0.5 | 1 | #REF! | #REF! | 100% |  | 2025-12-23 | 2025-12-24
DMS | Shareholders' Meeting & Management | 1111 | 股票基本資料維護 | Stock Basic Data Maintenance | 2 | 5 | #REF! | #REF! | 100% |  | 2025-12-26 | 2026-01-02 | 2026-01-16
DMS | Shareholders' Meeting & Management | 3181 | 轉入Stock_Pool List | Import Stock_Pool List | 0 | 0 | #REF! | #REF! | 200% |  | 2026-01-02 | 2026-01-02
DMS | Shareholders' Meeting & Management | 3182 | 維護Stock_Pool List | Maintain Stock_Pool List | 0 | 0 | #REF! | #REF! | 200% |  | 2026-01-02 | 2026-01-02 | 2026-01-16
[12 empty] | #DIV/0! | #DIV/0!
DMS | Dividend |  |  | Data mapping | 2 | 4 | #REF! | #REF! | 200% |  | 2026-01-05 | 2026-01-07
DMS | Dividend |  |  | Data Migration | 2 | 6 | #REF! | #REF! | 200% |  | 2026-01-08 | 2026-01-13
DMS | Dividend |  |  | Create Tables in DB | 2 | 3 | #REF! | #REF! | 200% |  | 2026-01-14 | 2026-01-15
DMS | Dividend |  |  | Maintain Distributable Balance | 3 | 11 | #REF! | #REF! | 200% |  | 2026-01-16 | 2026-01-23
DMS | Dividend |  |  | Domestic Dividend Information Inquiry | 3 | 10 | #REF! | #REF! | 200% |  | 2026-01-26 | 2026-02-02
DMS | Dividend |  |  | Upload Domestic Dividend Composition Info to EC | 3 | 10 | #REF! | #REF! | 200% |  | 2026-02-03 | 2026-02-10 | 2026-03-10
[12 empty] | #DIV/0! | #DIV/0!
DMS | Mandate |  |  | Create Tables in DB | 2 | 5 | #REF! | #REF! | 200% |  | 2026-02-11 | 2026-02-13
DMS | Mandate |  |  | Data mapping | 2 | 7 | #REF! | #REF! | 200% |  | 2026-02-16 | 2026-02-19
DMS | Mandate |  |  | Data Migration | 2 | 4 | #REF! | #REF! | 200% |  | 2026-02-20 | 2026-02-24
FAS | Mandate |  |  | Subscription Details Report | 2 | 4 | #REF! | #REF! | 200% |  | 2026-02-25 | 2026-02-27
FAS | Mandate |  |  | Redemption Details Report | 2 | 4 | #REF! | #REF! | 200% |  | 2026-03-02 | 2026-03-04
FAS | Mandate |  |  | Full Discretionary NAV Import Process (State Street) | 2 | 5 | #REF! | #REF! | 200% |  | 2026-03-05 | 2026-03-09
FAS | Mandate |  |  | Generate Full Discretionary Subscription/Redemption Data | 4 | 9 | #REF! | #REF! | 200% |  | 2026-03-11 | 2026-03-17
FAS | Mandate |  |  | Export Full Discretionary Subscription/Redemption Data | 2 | 5 | #REF! | #REF! | 200% |  | 2026-03-18 | 2026-03-20
FAS | Mandate |  |  | Generate SSB Full Discretionary Subscription/Redemption Data | 4 | 9 | #REF! | #REF! | 200% |  | 2026-03-24 | 2026-03-30
FAS | Mandate |  |  | Export SSB Full Discretionary Subscription/Redemption Data | 5 | 9 | #REF! | #REF! | 200% |  | 2026-04-01 | 2026-04-07
FAS | Mandate |  |  | Fund NAV Auto Import Process | 4 | 9 | #REF! | #REF! | 200% |  | 2026-04-09 | 2026-04-15
FAS | Mandate |  |  | Fund NAV Import Status Inquiry | 3 | 5 | #REF! | #REF! | 200% |  | 2026-04-16 | 2026-04-20
FAS | Mandate |  |  | Payment Notice for Aladdin – Sales Fee File | 2 | 4 | #REF! | #REF! | 200% |  | 2026-04-21 | 2026-04-23
FAS | Mandate |  |  | Calendar File - 全委 | 2 | 4 | #REF! | #REF! | 200% |  | 2026-04-24 | 2026-04-28
FAS | Mandate |  |  | Payment Notice – Management Fee, Custody Fee | 3 | 5 | #REF! | #REF! | 200% |  | 2026-04-29 | 2026-05-01
FAS | Mandate |  |  | Payment Notice – Dividend Distribution | 3 | 5 | #REF! | #REF! | 200% |  | 2026-05-04 | 2026-05-06
FAS | Mandate |  |  | Payment Notice – Dividend Instruction Printing | 2 | 4 | #REF! | #REF! | 200% |  | 2026-05-07 | 2026-05-11
FAS | Mandate |  |  | Validation – Dividend Data | 3 | 4 | #REF! | #REF! | 200% |  | 2026-05-12 | 2026-05-14
FAS | Mandate |  |  | Last 10 Years Fund Distribution Amounts | 3 | 4 | #REF! | #REF! | 200% |  | 2026-05-15 | 2026-05-19
FAS | Mandate |  |  | FND Monthly Report (Electronic File) | 3 | 4 | #REF! | #REF! | 200% |  | 2026-05-20 | 2026-05-22
DMS | Mandate |  |  | Full Discretionary Data Generation Process | 4 | 9 | #REF! | #REF! | 200% |  | 2026-05-26 | 2026-06-01
DMS | Mandate |  |  | Full Discretionary Data Maintenance Process | 4 | 9 | #REF! | #REF! | 200% |  | 2026-06-03 | 2026-06-09
DMS | Mandate |  |  | Subscription/Redemption Posting Details Report | 2 | 4 | #REF! | #REF! | 200% |  | 2026-06-10 | 2026-06-12
DMS | Mandate |  |  | Full Discretionary Contract Asset Movement Report | 2 | 9 | #REF! | #REF! | 200% |  | 2026-06-15 | 2026-06-19
DMS | Mandate |  |  | PAMS Inventory File Export | 2 | 5 | #REF! | #REF! | 200% |  | 2026-06-22 | 2026-06-24
DMS | Mandate |  |  | Full Discretionary Stock Stop-Loss Control Table | 2 | 5 | #REF! | #REF! | 200% |  | 2026-06-25 | 2026-06-29
FAS | Mandate |  |  | Automated Fund NAV Import Process | 4 | 9 | #REF! | #REF! | 200% |  | 2026-07-01 | 2026-07-07
FAS | Mandate |  |  | Full Discretionary Client Information Maintenance | 5 | 9 | #REF! | #REF! | 200% |  | 2026-07-09 | 2026-07-15 | 07/31/2026
Formulas:
Req ETA = WORKDAY("10/1/2025",表格1_32[[#This Row],[Detailed req est. ]]/表格1_32[[#This Row],[Full Time Estimate(%)]])
Req ETA = WORKDAY([DEV ETA, row above],表格1_32[[#This Row],[Detailed req est. ]]/表格1_32[[#This Row],[Full Time Estimate(%)]])
DEV ETA = WORKDAY(表格1_32[[#This Row],[Req ETA]],表格1_32[[#This Row],[Dev + Unit test est.]]/表格1_32[[#This Row],[Full Time Estimate(%)]])
Dev + Unit test est.3 = WORKDAY(表格1_32[[#This Row],[Detailed req est. 2]],#REF!)
Detailed req est. 2 = WORKDAY([Dev + Unit test est.3, row above],#REF!)
UAT ETA = WORKDAY(表格1_32[[#This Row],[ DEV ETA]],10)

## TimeLine
App | Module | Features | BA | Mandate | Detailed req est. | Dev + Unit test est. | Status | Req ETA | DEV ETA | UAT ETA
DMS | Shareholders' Meeting & Management | Data mapping | 3 | 5 | 2025-10-01 | 2025-10-30 | In Unit Testing | 2025-11-13 | 2025-11-06 | 2025-11-20
DMS | Shareholders' Meeting & Management | Data Migration | 3 | 5 | 2025-10-01 | 2025-10-30 | In Unit Testing | 2025-11-13 | 2025-11-06 | 2025-11-20
DMS | Shareholders' Meeting & Management | Create Tables in DB | 3 | 5 | 2025-10-01 | 2025-10-30 | In Unit Testing | 2025-11-13 | 2025-11-06 | 2025-11-20
DMS | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | 4 | 10 | 2025-10-20 | 2025-11-03 | In Unit Testing | 2025-11-12 | 2025-11-10 | 2025-11-24
DMS | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | 2 | 5 | 2025-11-05 | 2025-11-12 | In Development | 2025-11-05 | 2025-11-19 | 2025-12-03
DMS | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | 2 | 5 | 2025-11-14 | 2025-11-21 |  | 2025-11-14 | 2025-11-28 | 2025-12-12
DMS | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | 2 | 3 | 2025-11-25 | 2025-11-28 |  | 2025-11-25 | 2025-12-05 | 2025-12-19
DMS | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | 2 | 3 | 2025-12-02 | 2025-12-05 |  | 2025-12-02 | 2025-12-12 | 2025-12-26
DMS | Shareholders' Meeting & Management | Stock Basic Data Maintenance | 4 | 10 | 2025-12-11 | 2025-12-25 |  | 2026-01-09 | 2026-01-01 | 2026-01-15
DMS | Shareholders' Meeting & Management | Import Stock_Pool List | 2 | 3 | 2025-12-29 | 2026-01-01 |  | 2026-01-27 | 2026-01-08 | 2026-01-22
DMS | Shareholders' Meeting & Management | Maintain Stock_Pool List | 2 | 5 | 2026-01-05 | 2026-01-12 |  | 2026-02-04 | 2026-01-19 | 2026-02-02
DMS | Dividend | Data mapping | 2 | 4 | 2026-01-14 | 2026-01-20 |  | 2026-02-03 | 2026-01-27 | 2026-02-10
DMS | Dividend | Data Migration | 2 | 6 | 2026-01-22 | 2026-01-30 |  | 2026-02-13 | 2026-02-06 | 2026-02-20
DMS | Dividend | Create Tables in DB | 2 | 3 | 2026-02-03 | 2026-02-06 |  | 2026-02-20 | 2026-02-13 | 2026-02-27
DMS | Dividend | Maintain Distributable Balance | 5 | 15 | 2026-02-13 | 2026-03-06 |  | 2026-02-18 | 2026-03-13 | 2026-03-27
DMS | Dividend | Domestic Dividend Information Inquiry | 5 | 15 | 2026-03-13 | 2026-04-03 |  | 2026-03-18 | 2026-04-10 | 2026-04-24
DMS | Dividend | Upload Domestic Dividend Composition Info to EC | 5 | 15 | 2026-04-10 | 2026-05-01 |  | 2026-04-15 | 2026-05-08 | 2026-05-22
DMS | Mandate | Create Tables in DB | 2 | 5 | 2026-05-05 | 2026-05-12 |  | 2026-05-26 | 2026-05-19 | 2026-06-02
DMS | Mandate | Data mapping | 2 | 7 | 2026-05-14 | 2026-05-25 |  | 2026-06-08 | 2026-06-01 | 2026-06-15
DMS | Mandate | Data Migration | 2 | 4 | 2026-05-27 | 2026-06-02 |  | 2026-06-16 | 2026-06-09 | 2026-06-23
FAS | Mandate | Subscription Details Report | 2 | 4 | 2026-06-04 | 2026-06-10 |  | 2026-08-25 | 2026-06-17 | 2026-07-01
FAS | Mandate | Redemption Details Report | 2 | 4 | 2026-06-12 | 2026-06-18 |  | 2026-09-04 | 2026-06-25 | 2026-07-09
FAS | Mandate | Full Discretionary NAV Import Process (State Street) | 2 | 5 | 2026-06-22 | 2026-06-29 |  | 2026-09-16 | 2026-07-06 | 2026-07-20
FAS | Mandate | Generate Full Discretionary Subscription/Redemption Data | 4 | 10 | 2026-07-03 | 2026-07-17 |  | 2026-09-28 | 2026-07-24 | 2026-08-07
FAS | Mandate | Export Full Discretionary Subscription/Redemption Data | 2 | 5 | 2026-07-21 | 2026-07-28 |  | 2026-10-08 | 2026-08-04 | 2026-08-18
FAS | Mandate | Generate SSB Full Discretionary Subscription/Redemption Data | 4 | 10 | 2026-08-03 | 2026-08-17 |  | 2026-10-20 | 2026-08-24 | 2026-09-07
FAS | Mandate | Export SSB Full Discretionary Subscription/Redemption Data | 5 | 15 | 2026-08-24 | 2026-09-14 |  | 2026-10-30 | 2026-09-21 | 2026-10-05
FAS | Mandate | Fund NAV Auto Import Process | 4 | 10 | 2026-09-18 | 2026-10-02 |  | 2026-11-13 | 2026-10-09 | 2026-10-23
FAS | Mandate | Fund NAV Import Status Inquiry | 3 | 5 | 2026-10-07 | 2026-10-14 |  | 2026-12-02 | 2026-10-21 | 2026-11-04
FAS | Mandate | Payment Notice for Aladdin – Sales Fee File | 2 | 4 | 2026-10-16 | 2026-10-22 |  | 2026-12-11 | 2026-10-29 | 2026-11-12
FAS | Mandate | Calendar File | 2 | 4 | 2026-10-26 | 2026-10-30 |  | 2026-12-21 | 2026-11-06 | 2026-11-20
FAS | Mandate | Payment Notice – Management Fee, Custody Fee | 3 | 5 | 2026-11-04 | 2026-11-11 |  | 2026-12-29 | 2026-11-18 | 2026-12-02
FAS | Mandate | Payment Notice – Dividend Distribution | 3 | 5 | 2026-11-16 | 2026-11-23 |  | 2027-01-06 | 2026-11-30 | 2026-12-14
FAS | Mandate | Payment Notice – Dividend Instruction Printing | 2 | 3 | 2026-11-25 | 2026-11-30 |  | 2027-01-08 | 2026-12-07 | 2026-12-21
FAS | Mandate | Validation – Dividend Data | 3 | 5 | 2026-12-03 | 2026-12-10 |  | 2027-01-18 | 2026-12-17 | 2026-12-31
FAS | Mandate | Last 10 Years Fund Distribution Amounts | 3 | 5 | 2026-12-15 | 2026-12-22 |  | 2027-01-26 | 2026-12-29 | 2027-01-12
FAS | Mandate | FND Monthly Report (Electronic File) | 3 | 5 | 2026-12-25 | 2027-01-01 |  | 2027-02-02 | 2027-01-08 | 2027-01-22
DMS | Mandate | Full Discretionary Data Generation Process | 4 | 10 | 2027-01-07 | 2027-01-21 |  | 2027-02-12 | 2027-02-26 | 2027-03-12
DMS | Mandate | Full Discretionary Data Maintenance Process | 4 | 10 | 2027-01-27 | 2027-02-10 |  | 2027-03-05 | 2027-03-19 | 2027-04-02
DMS | Mandate | Subscription/Redemption Posting Details Report | 2 | 4 | 2027-02-12 | 2027-02-18 |  | 2027-03-23 | 2027-02-25 | 2027-03-11
DMS | Mandate | Full Discretionary Contract Asset Movement Report | 4 | 10 | 2027-02-24 | 2027-03-10 |  | 2027-03-31 | 2027-03-17 | 2027-03-31
DMS | Mandate | PAMS Inventory File Export | 2 | 5 | 2027-03-12 | 2027-03-19 |  | 2027-04-12 | 2027-03-26 | 2027-04-09
DMS | Mandate | Full Discretionary Stock Stop-Loss Control Table | 2 | 5 | 2027-03-23 | 2027-03-30 |  | 2027-04-22 | 2027-04-06 | 2027-04-20
FAS | Mandate | Automated Fund NAV Import Process | 4 | 10 | 2027-04-05 | 2027-04-19 |  | 2027-04-23 | 2027-04-26 | 2027-05-10
FAS | Mandate | Full Discretionary Client Information Maintenance | 5 | 15 | 2027-04-26 | 2027-05-17 |  | 2027-04-24 | 2027-05-24 | 2027-06-07
Formulas:
Req ETA = [Dev + Unit test est.]+14
Req ETA = [Detailed req est.]
DEV ETA = [Dev + Unit test est.]+7
DEV ETA = [Req ETA]+14
UAT ETA = [DEV ETA]+14
Detailed req est. = [Detailed req est., row above]+[Mandate, row above]+E3+E2+4
Detailed req est. = WORKDAY([Dev + Unit test est., row above],表格1_3[[#This Row],[BA]])
Dev + Unit test est. = WORKDAY(表格1_3[[#This Row],[Detailed req est. ]],表格1_3[[#This Row],[Mandate]])

## Project Planning - B (2)
DMS Development
| TOTAL TASKS | 229 |  |  | DURATION | 593 |  | Overall Progress
| Completed | 0 |  |  | START | 2025-09-15 |  |  |  | 24 | Team Member | FTE | Cost / Monthly
| In progress | 9 |  |  | FINISH | 2027-04-30 |  |  |  | 408 | Kent | 1 |  | 1 year
| Not Started | 221 | [8 empty] | BA / QA | 1 | 152250 | 1827000
|  |  | New SA and Engineer training |  |  | 1/5/2026 - 1/9/2026 |  | 100% |  |  | AP Lead | 1
[11 empty] | FrontEnd1 | 1 | 152250 | 1827000
[11 empty] | Patrick-BA | 0.5
[11 empty] | Richard | 0.5
SPRINT | EPIC | FEATURE | TASKS | STORIES | RESPONSIBLE | Man Day Required | START | FINISH | DURATION | STATUS
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | BA | 3 | 2025-09-15 | 2025-09-18 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | BA | 3 | 2025-09-19 | 2025-09-24 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Kent | 5 | 2025-09-25 | 2025-10-02 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Kent | 5 | 2025-10-03 | 2025-10-10 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Kent | 5 | 2025-10-13 | 2025-10-20 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | QA | 3 | 2025-10-21 | 2025-10-24 | 3 | Completed
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Detail Requirement Analysis | Patrick -BA | 3 | 2025-11-24 | 2025-12-02 | 6 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Document Detail Requirement | Patrick -BA | 3 | 2025-12-03 | 2025-12-11 | 6 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Kent | 3 | 2025-12-12 | 2025-12-17 | 3 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Kent | 5 | 2025-12-18 | 2025-12-25 | 5 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Kent | 2 | 2025-12-26 | 2025-12-30 | 2 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | QA | 3 | 2025-12-31 | 2026-01-05 | 3 | Not Started
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Balance Detail Requirement Analysis | Patrick -BA | 1.5 | 2025-12-12 | 2025-12-17 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Document Detail Requirement | Patrick -BA | 1.5 | 2025-12-18 | 2025-12-23 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 1 | FrontEnd | 1 | 2025-12-24 | 2025-12-25 | 1 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 2 | Kent | 7 | 2025-12-31 | 2026-01-09 | 7 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | QA | Maintain Distributable Balance QA - unit testing | QA | 3 | 2026-01-12 | 2026-01-15 | 3 | Not Started
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Detail Requirement Analysis | Patrick -BA | 1.5 | 2025-12-24 | 2025-12-29 | 3 | In progress
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Document Detail Requirement | Patrick -BA | 1.5 | 2025-12-26 | 2025-12-31 | 3 | In progress
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 1 | FrontEnd | 4 | 2026-01-01 | 2026-01-07 | 4 | Not Started
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 2 | Kent | 4 | 2026-01-12 | 2026-01-16 | 4 | Not Started
Sprint 5 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | QA | Domestic Dividend Information Inquiry QA - unit testing | QA | 2 | 2026-01-19 | 2026-01-21 | 2 | Not Started
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Detail Requirement Analysis | Patrick -BA | 1.5 | 2026-01-01 | 2026-01-06 | 3 | In progress
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Document Detail Requirement | Patrick -BA | 1.5 | 2026-01-07 | 2026-01-12 | 3 | In progress
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 1 | FrontEnd | 4 | 2026-01-08 | 2026-01-14 | 4 | Not Started
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 2 | Kent | 4 | 2026-01-19 | 2026-01-23 | 4 | Not Started
Sprint 6 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | QA | Upload Domestic Dividend Composition Info to EC QA - unit testing | QA | 2 | 2026-01-26 | 2026-01-28 | 2 | Not Started
Sprint 1 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | BA | 3 | 2026-01-13 | 2026-01-16 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | BA | 3 | 2026-01-19 | 2026-01-22 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | New AP Lead | 4 | 2026-01-19 | 2026-01-23 | 4 | Not Started
Sprint 3 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | New AP Lead | 4 | 2026-01-26 | 2026-01-30 | 4 | Not Started
Sprint 4 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | New AP Lead | 2 | 2026-02-02 | 2026-02-04 | 2 | Not Started
Sprint 5 | Mandate | Data Mapping, Data Migration & Create Tables in DB | QA | Data Related QA - unit testing | QA | 3 | 2026-02-05 | 2026-02-10 | 3 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement Analysis | BA | 2 | 2026-01-23 | 2026-01-27 | 2 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement | BA | 2 | 2026-01-28 | 2026-01-30 | 2 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 1 | FrontEnd | 2 | 2026-02-02 | 2026-02-04 | 2 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 2 | New AP Lead | 8 | 2026-02-02 | 2026-02-12 | 8 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | QA | Mandate Client Information Maintenance QA - unit-testing | QA | 2 | 2026-02-13 | 2026-02-17 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement Analysis | BA | 2 | 2026-02-02 | 2026-02-04 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement | BA | 2 | 2026-02-05 | 2026-02-09 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 1 | FrontEnd | 2 | 2026-02-10 | 2026-02-12 | 2 | Not Started
Sprint 7 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 2 | Kent | 8 | 2026-02-10 | 2026-02-20 | 8 | Not Started
Sprint 8 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | QA | Mandate Contract Information Maintenance QA - unit-testing | QA | 2 | 2026-02-23 | 2026-02-25 | 2 | Not Started
Sprint 6 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Analysis | BA | 2 | 2026-02-10 | 2026-02-12 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Doc | BA | 2 | 2026-02-13 | 2026-02-17 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 1 | FrontEnd | 2 | 2026-02-18 | 2026-02-20 | 2 | Not Started
Sprint 8 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 2 | New AP Lead | 8 | 2026-02-18 | 2026-03-02 | 8 | Not Started
Sprint 9 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | QA | Mandate Subscription Data Entry QA - unit-testing | QA | 2 | 2026-03-03 | 2026-03-05 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Analysis | BA | 2 | 2026-02-18 | 2026-02-20 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Doc | BA | 2 | 2026-02-23 | 2026-02-25 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 1 | FrontEnd | 2 | 2026-02-26 | 2026-03-02 | 2 | Not Started
Sprint 10 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 2 | Kent | 8 | 2026-02-26 | 2026-03-10 | 8 | Not Started
Sprint 11 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | QA | Mandate Redemption Data Entry QA - unit-testing | QA | 2 | 2026-03-11 | 2026-03-13 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | BA | 1 | 2026-02-26 | 2026-02-27 | 1 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | BA | 2 | 2026-03-02 | 2026-03-04 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | FrontEnd | 1 | 2026-03-05 | 2026-03-06 | 1 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | New AP Lead | 3 | 2026-03-05 | 2026-03-10 | 3 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | QA | Mandate Fund NAV Inquiry QA - unit-testing | QA | 2 | 2026-03-11 | 2026-03-13 | 2 | Not Started
Sprint 12 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | BA | 1 | 2026-03-05 | 2026-03-06 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | BA | 2 | 2026-03-09 | 2026-03-11 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | FrontEnd | 2 | 2026-03-12 | 2026-03-16 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Kent | 2 | 2026-03-12 | 2026-03-16 | 2 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | QA | Mandate Fund NAV Inquiry QA - unit-testing | QA | 2 | 2026-03-17 | 2026-03-19 | 2 | Not Started
Sprint 5 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement Analysis | BA | 1 | 2026-03-12 | 2026-03-13 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement | BA | 1 | 2026-03-16 | 2026-03-17 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 1 | FrontEnd | 1 | 2026-03-18 | 2026-03-19 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 2 | New AP Lead | 2 | 2026-03-18 | 2026-03-20 | 2 | Not Started
Sprint 7 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | QA | Subscription Details Report QA - unit-testing | QA | 1 | 2026-03-23 | 2026-03-24 | 1 | Not Started
Sprint 7 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement Analysis | BA | 1 | 2026-03-18 | 2026-03-19 | 1 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement | BA | 1 | 2026-03-20 | 2026-03-23 | 1 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 1 | FrontEnd | 1 | 2026-03-24 | 2026-03-25 | 1 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 2 | New AP Lead | 2 | 2026-03-24 | 2026-03-26 | 2 | Not Started
Sprint 9 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | QA | Redemption Details Report QA - unit-testing | QA | 1 | 2026-03-27 | 2026-03-30 | 1 | Not Started
Sprint 9 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement Analysis | BA | 2 | 2026-03-24 | 2026-03-26 | 2 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement | BA | 2 | 2026-03-27 | 2026-03-31 | 2 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 1 | FrontEnd | 3 | 2026-04-01 | 2026-04-06 | 3 | Not Started
Sprint 11 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 2 | New AP Lead | 5 | 2026-04-01 | 2026-04-08 | 5 | Not Started
Sprint 12 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | QA | Mandate NAV Import Process (State Street) QA - unit-testing | QA | 1 | 2026-04-09 | 2026-04-10 | 1 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement Analysis | BA | 1 | 2026-04-01 | 2026-04-02 | 1 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement | BA | 2 | 2026-04-03 | 2026-04-07 | 2 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 2 | 2026-04-08 | 2026-04-10 | 2 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 4 | 2026-04-13 | 2026-04-17 | 4 | Not Started
Sprint 14 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | QA | Generate Mandate Subscription/Redemption Data QA - unit-testing | QA | 2 | 2026-04-20 | 2026-04-22 | 2 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement Analysis | BA | 0.5 | 2026-04-08 | 2026-04-08 | 0.5 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement | BA | 0.5 | 2026-04-09 | 2026-04-09 | 0.5 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 1.5 | 2026-04-10 | 2026-04-13 | 1.5 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 2.5 | 2026-04-10 | 2026-04-14 | 2.5 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | QA | Export Mandate Subscription/Redemption Data QA - unit-testing | QA | 1 | 2026-04-15 | 2026-04-16 | 1 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement Analysis | BA | 2 | 2026-04-10 | 2026-04-14 | 2 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement | BA | 2 | 2026-04-15 | 2026-04-17 | 2 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 2 | 2026-04-17 | 2026-04-21 | 2 | Not Started
Sprint 18 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 5 | 2026-04-21 | 2026-04-28 | 5 | Not Started
Sprint 19 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | QA | Generate SSB Mandate Subscription/Redemption Data QA - unit-testing | QA | 2 | 2026-04-28 | 2026-04-30 | 2 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement Analysis | BA | 0.5 | 2026-04-20 | 2026-04-20 | 0.5 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement | BA | 0.5 | 2026-04-21 | 2026-04-21 | 0.5 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 1 | FrontEnd | 2 | 2026-04-22 | 2026-04-24 | 2 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 2 | New AP Lead | 3 | 2026-04-24 | 2026-04-29 | 3 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | QA | Export SSB Mandate Subscription/Redemption Data QA - unit-testing | QA | 1 | 2026-04-30 | 2026-05-01 | 1 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Requirement Analysis | BA | 2 | 2026-04-22 | 2026-04-24 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Data Requirement | BA | 2 | 2026-04-27 | 2026-04-29 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 1 | FrontEnd | 3 | 2026-04-30 | 2026-05-05 | 3 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 2 | Kent | 5 | 2026-05-05 | 2026-05-12 | 5 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | QA | Fund NAV Auto Import Process QA - unit-testing | QA | 1 | 2026-05-13 | 2026-05-14 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Requirement Analysis | BA | 1 | 2026-04-30 | 2026-05-01 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Data Requirement | BA | 2 | 2026-05-04 | 2026-05-06 | 2 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 1 | FrontEnd | 1.5 | 2026-05-07 | 2026-05-08 | 1.5 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 2 | Kent | 2.5 | 2026-05-08 | 2026-05-12 | 2.5 | Not Started
Sprint 17 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | QA | Fund NAV Import Status Inquiry QA - unit-testing | QA | 1 | 2026-05-13 | 2026-05-14 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement Analysis | BA | 1 | 2026-05-07 | 2026-05-08 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement | BA | 1 | 2026-05-11 | 2026-05-12 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 1 | FrontEnd | 1.5 | 2026-05-13 | 2026-05-14 | 1.5 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 2 | Kent | 1.5 | 2026-05-14 | 2026-05-15 | 1.5 | Not Started
Sprint 18 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | QA | Calendar File QA - unit-testing | QA | 1 | 2026-05-18 | 2026-05-19 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement Analysis | BA | 1 | 2026-05-13 | 2026-05-14 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement | BA | 2 | 2026-05-15 | 2026-05-19 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 1 | FrontEnd | 1 | 2026-05-20 | 2026-05-21 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 2 | Kent | 2 | 2026-05-20 | 2026-05-22 | 2 | Not Started
Sprint 19 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | QA | Payment Notice – Management Fee, Custody Fee QA - unit-testing | QA | 1 | 2026-05-25 | 2026-05-26 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement Analysis | BA | 1.5 | 2026-05-20 | 2026-05-21 | 1.5 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement | BA | 1.5 | 2026-05-22 | 2026-05-25 | 1.5 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 1 | FrontEnd | 2 | 2026-05-26 | 2026-05-28 | 2 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 2 | Kent | 2 | 2026-05-26 | 2026-05-28 | 2 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | QA | Validation – Dividend Data QA - unit-testing | QA | 1 | 2026-05-29 | 2026-06-01 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement Analysis | BA | 1 | 2026-05-26 | 2026-05-27 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement | BA | 1 | 2026-05-28 | 2026-05-29 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 1 | FrontEnd | 1 | 2026-06-01 | 2026-06-02 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 2 | Kent | 2 | 2026-06-01 | 2026-06-03 | 2 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | QA | Payment Notice – Dividend Distribution QA - unit-testing | QA | 1 | 2026-06-04 | 2026-06-05 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement Analysis | BA | 1 | 2026-06-01 | 2026-06-02 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement | BA | 1 | 2026-06-03 | 2026-06-04 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 1 | FrontEnd | 1 | 2026-06-05 | 2026-06-08 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 2 | Kent | 2 | 2026-06-05 | 2026-06-09 | 2 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | QA | Payment Notice – Dividend Instruction Printing QA - unit-testing | QA | 1 | 2026-06-10 | 2026-06-11 | 1 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Analysis | BA | 2 | 2026-06-05 | 2026-06-09 | 2 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Doc | BA | 2 | 2026-06-10 | 2026-06-12 | 2 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 1 | FrontEnd | 3.5 | 2026-06-15 | 2026-06-18 | 3.5 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 2 | New AP Lead | 4 | 2026-06-15 | 2026-06-19 | 4 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | QA | Mandate Data Generation Process QA - unit-testing | QA | 1.5 | 2026-06-22 | 2026-06-23 | 1.5 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Analysis | BA | 2 | 2026-06-15 | 2026-06-17 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Doc | BA | 2 | 2026-06-18 | 2026-06-22 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 1 | FrontEnd | 2.5 | 2026-06-23 | 2026-06-25 | 2.5 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 2 | Kent | 4.5 | 2026-06-23 | 2026-06-29 | 4.5 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | QA | Mandate Data Maintenance Process QA - unit-testing | QA | 2 | 2026-06-30 | 2026-07-02 | 2 | Not Started
Sprint 11 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Analysis | BA | 1 | 2026-06-23 | 2026-06-24 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Doc | BA | 1 | 2026-06-25 | 2026-06-26 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 1 | FrontEnd | 1 | 2026-06-29 | 2026-06-30 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 2 | New AP Lead | 2 | 2026-06-29 | 2026-07-01 | 2 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | QA | Subscription/Redemption Posting Details Report QA - unit-testing | QA | 1 | 2026-07-02 | 2026-07-03 | 1 | Not Started
Sprint 12 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Analysis | BA | 1 | 2026-06-29 | 2026-06-30 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Doc | BA | 1 | 2026-07-01 | 2026-07-02 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 1 | FrontEnd | 3 | 2026-07-03 | 2026-07-08 | 3 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 2 | New AP Lead | 4 | 2026-07-03 | 2026-07-09 | 4 | Not Started
Sprint 14 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | QA | Mandate Contract Asset Movement Report QA - unit-testing | QA | 2 | 2026-07-10 | 2026-07-14 | 2 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Analysis | BA | 1 | 2026-07-03 | 2026-07-06 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Doc | BA | 1 | 2026-07-07 | 2026-07-08 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 1 | FrontEnd | 2 | 2026-07-09 | 2026-07-13 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 2 | Kent | 2 | 2026-07-09 | 2026-07-13 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | QA | PAMS Inventory File Export QA - unit-testing | QA | 1 | 2026-07-14 | 2026-07-15 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement Analysis | BA | 1 | 2026-07-09 | 2026-07-10 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement | BA | 1 | 2026-07-13 | 2026-07-14 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 1 | FrontEnd | 1 | 2026-07-15 | 2026-07-16 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 2 | New AP Lead | 4 | 2026-07-15 | 2026-07-21 | 4 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | QA | Mandate Stock Stop-Loss Control Table QA - unit-testing | QA | 1 | 2026-07-22 | 2026-07-23 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Analysis | BA | 1 | 2026-07-15 | 2026-07-16 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Doc | BA | 1 | 2026-07-17 | 2026-07-20 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | Development | Report - 基金規模報表查詢 - Development | Kent | 3 | 2026-07-21 | 2026-07-24 | 3 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | QA | Report - 基金規模報表查詢 QA - unit-testing | QA | 1 | 2026-07-27 | 2026-07-28 | 1 | Not Started
Sprint 22 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Analysis | BA | 1 | 2026-07-21 | 2026-07-22 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Doc | BA | 1 | 2026-07-23 | 2026-07-24 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | Development | Taiwan Ratings Reporting Data - Development | Kent | 3 | 2026-07-27 | 2026-07-30 | 3 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | QA | Taiwan Ratings Reporting Data QA - unit-testing | QA | 1 | 2026-07-31 | 2026-08-03 | 1 | Not Started
Sprint 23 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Analysis | BA | 1 | 2026-07-27 | 2026-07-28 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Doc | BA | 1 | 2026-07-29 | 2026-07-30 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | Development | Mutual Fund Asset Size Export Process - Development | New AP Lead | 3 | 2026-07-31 | 2026-08-05 | 3 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | QA | Mutual Fund Asset Size Export Process - unit-testing | QA | 1 | 2026-08-06 | 2026-08-07 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement Analysis | BA | 0.5 | 2026-07-31 | 2026-07-31 | 0.5 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement | BA | 0.5 | 2026-08-03 | 2026-08-03 | 0.5 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 1 | FrontEnd | 3 | 2026-08-04 | 2026-08-07 | 3 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 2 | Kent | 4 | 2026-08-04 | 2026-08-10 | 4 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | QA | Generate Shareholder Meeting Data QA - unit-testing | QA | 2 | 2026-08-11 | 2026-08-13 | 2 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement Analysis | BA | 0.5 | 2026-08-04 | 2026-08-04 | 0.5 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement | BA | 0.5 | 2026-08-05 | 2026-08-05 | 0.5 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 1 | FrontEnd | 1 | 2026-08-06 | 2026-08-07 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 2 | New AP Lead | 3 | 2026-08-06 | 2026-08-11 | 3 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | QA | Generate Memo for Assigned Personnel/Function QA - unit-testing | QA | 1 | 2026-08-12 | 2026-08-13 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement Analysis | BA | 0.5 | 2026-08-06 | 2026-08-06 | 0.5 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement | BA | 0.5 | 2026-08-07 | 2026-08-07 | 0.5 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 1 | FrontEnd | 2 | 2026-08-10 | 2026-08-12 | 2 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 2 | Kent | 2 | 2026-07-21 | 2026-07-23 | 2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | QA | Director/Supervisor Election Report/Function QA - unit-testing | QA | 1 | 2026-07-24 | 2026-07-27 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement Analysis | BA | 0.2 | 2026-08-10 | 2026-08-10 | 0.2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement | BA | 0.3 | 2026-08-11 | 2026-08-11 | 0.3 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 1 | FrontEnd | 0.2 | 2026-07-23 | 2026-07-23 | 0.2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 2 | New AP Lead | 0.5 | 2026-07-23 | 2026-07-23 | 0.5 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | QA | Shareholder Meeting Fund Attendance Details Report QA - unit-testing | QA | 0.3 | 2026-07-24 | 2026-07-24 | 0.3 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Requirement Analysis | BA | 0.2 | 2026-08-12 | 2026-08-12 | 0.2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Report Requirement | BA | 0.3 | 2026-08-13 | 2026-08-13 | 0.3 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details Report - Development 1 | FrontEnd | 0.2 | 2026-08-14 | 2026-08-14 | 0.2 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details - Development 2 | Kent | 0.5 | 2026-08-14 | 2026-08-14 | 0.5 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | QA | Shareholder Meeting Missing Election Report Details QA - unit-testing | QA | 0.3 | 2026-08-17 | 2026-08-17 | 0.3 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement Analysis | BA | 1 | 2026-08-14 | 2026-08-17 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement | BA | 1 | 2026-08-18 | 2026-08-19 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 1 | FrontEnd | 1.5 | 2026-08-20 | 2026-08-21 | 1.5 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 2 | Kent | 2.5 | 2026-08-20 | 2026-08-24 | 2.5 | Not Started
Sprint 30 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | QA | Stock Basic Data Maintenance QA - unit-testing | QA | 1 | 2026-08-25 | 2026-08-26 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement Analysis | BA | 1 | 2027-03-01 | 2027-03-02 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement | BA | 1 | 2027-03-03 | 2027-03-04 | 1 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 1 | FrontEnd | 3 | 2027-03-05 | 2027-03-10 | 3 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 2 | New AP Lead | 4 | 2027-03-05 | 2027-03-11 | 4 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | QA | Generate Shareholder Meeting Data QA - unit-testing | New AP Lead | 2 | 2027-03-12 | 2027-03-16 | 2 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement Analysis | Kent | 1 | 2027-03-01 | 2027-03-02 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement | Kent | 1 | 2027-03-03 | 2027-03-04 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 1 | FrontEnd | 1 | 2027-03-05 | 2027-03-08 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 2 | Kent | 3 | 2027-03-05 | 2027-03-10 | 3 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | QA | Generate Memo for Assigned Personnel/Function QA - unit-testing | Kent | 1 | 2027-03-11 | 2027-03-12 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement Analysis | BA | 1 | 2027-03-05 | 2027-03-08 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement | BA | 1 | 2027-03-09 | 2027-03-10 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 1 | FrontEnd | 2 | 2027-03-11 | 2027-03-15 | 2 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 2 | New AP Lead | 2 | 2027-03-11 | 2027-03-15 | 2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | QA | Director/Supervisor Election Report/Function QA - unit-testing | New AP Lead | 1 | 2027-03-16 | 2027-03-17 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement Analysis | BA | 1 | 2027-03-11 | 2027-03-12 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement | BA | 1 | 2027-03-15 | 2027-03-16 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 1 | FrontEnd | 1 | 2027-03-17 | 2027-03-18 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 2 | New AP Lead | 1 | 2027-03-18 | 2027-03-19 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | QA | Shareholder Meeting Fund Attendance Details Report QA - unit-testing | New AP Lead | 1 | 2027-03-22 | 2027-03-23 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Requirement Analysis | Kent | 1 | 2027-03-15 | 2027-03-16 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Report Requirement | Kent | 1 | 2027-03-17 | 2027-03-18 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details Report - Development 1 | FrontEnd | 1 | 2027-03-19 | 2027-03-22 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details - Development 2 | New AP Lead | 1 | 2027-03-19 | 2027-03-22 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | QA | Shareholder Meeting Missing Election Report Details QA - unit-testing | New AP Lead | 1 | 2027-03-23 | 2027-03-24 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement Analysis | BA | 1 | 2027-03-17 | 2027-03-18 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement | BA | 1 | 2027-03-19 | 2027-03-22 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 1 | FrontEnd | 2 | 2027-03-23 | 2027-03-25 | 2 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 2 | Kent | 3 | 2027-03-23 | 2027-03-26 | 3 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | QA | Stock Basic Data Maintenance QA - unit-testing | Kent | 1 | 2027-03-29 | 2027-03-30 | 1 | Not Started
Sprint30 | Shareholders' Meeting & Management | Pararell Run | All |  | New AP Lead |  | 2027-03-31 | 2027-04-30 |  | Not Started
Formulas:
FINISH = WORKDAY([START],[DURATION])
START = WORKDAY([FINISH, row above],1)
START = [FINISH, row above]

## Project Planning - B (3)
DMS Development
| TOTAL TASKS | 199 |  |  |  | DURATION | 593 |  | Overall Progress
| Completed | 0 |  |  |  | START | 2025-09-15 |  |  |  | 24 | Team Member | FTE | Cost / Monthly |  | Difficulty Level | MD
| In progress | 9 |  |  |  | FINISH | 2027-04-30 |  |  |  | 425 | Kent | 1 |  | 1 year | Low | 1-2
| Not Started | 191 | [9 empty] | BA/Testing | 1 | 152250 | 1827000 | Mid | 3-5
|  |  | New SA and Engineer training |  |  |  | 1/5/2026 - 1/9/2026 |  | 100% |  |  | AP Lead | 1 |  | Onboard after Chinese New Year | High | 6-8
[12 empty] | FrontEnd1 | 1 | 152250 | 1827000
[12 empty] | Patrick-BA | 0.5
SPRINT | EPIC | FEATURE | TASKS | STORIES | Difficulty Level | RESPONSIBLE | Man Day Required | START | FINISH | DURATION | STATUS
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | Mid | BA/Testing | 3 | 2025-09-15 | 2025-09-18 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | Mid | BA/Testing | 3 | 2025-09-19 | 2025-09-24 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Mid | Kent | 5 | 2025-09-25 | 2025-10-02 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Mid | Kent | 5 | 2025-10-03 | 2025-10-10 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Mid | Kent | 5 | 2025-10-13 | 2025-10-20 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Testing | Data Related QA - unit testing | Mid | BA/Testing | 3 | 2025-10-21 | 2025-10-24 | 3 | Completed
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Detail Requirement Analysis | Mid | Patrick -BA | 3 | 2025-11-24 | 2025-12-02 | 6 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Document Detail Requirement | Mid | Patrick -BA | 3 | 2025-12-03 | 2025-12-11 | 6 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Mid | Kent | 3 | 2025-12-12 | 2025-12-17 | 3 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | High | Kent | 5 | 2025-12-18 | 2025-12-25 | 5 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Low | Kent | 2 | 2025-12-26 | 2025-12-30 | 2 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Testing | Data Related QA - unit testing | Mid | BA/Testing | 3 | 2025-12-31 | 2026-01-05 | 3 | Not Started
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Balance Detail Requirement Analysis | Low | Patrick -BA | 1.5 | 2025-12-12 | 2025-12-17 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Document Detail Requirement | Low | Patrick -BA | 1.5 | 2025-12-18 | 2025-12-23 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 1 | Low | FrontEnd | 1 | 2025-12-24 | 2025-12-25 | 1 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 2 | High | Kent | 7 | 2025-12-31 | 2026-01-09 | 7 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Testing | Maintain Distributable Balance QA - unit testing | Mid | BA/Testing | 3 | 2026-01-12 | 2026-01-15 | 3 | Not Started
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Detail Requirement Analysis | Low | Patrick -BA | 1.5 | 2025-12-24 | 2025-12-29 | 3 | In progress
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Document Detail Requirement | Mid | Patrick -BA | 1.5 | 2025-12-26 | 2025-12-31 | 3 | In progress
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 1 | Mid | FrontEnd | 4 | 2026-01-01 | 2026-01-07 | 4 | Not Started
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 2 | Mid | Kent | 4 | 2026-01-12 | 2026-01-16 | 4 | Not Started
Sprint 5 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Testing | Domestic Dividend Information Inquiry QA - unit testing | High | BA/Testing | 2 | 2026-01-19 | 2026-01-21 | 2 | Not Started
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Detail Requirement Analysis | Low | Patrick -BA | 1.5 | 2026-01-01 | 2026-01-06 | 3 | In progress
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Document Detail Requirement | Mid | Patrick -BA | 1.5 | 2026-01-07 | 2026-01-12 | 3 | In progress
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 1 | Mid | FrontEnd | 4 | 2026-01-08 | 2026-01-14 | 4 | Not Started
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 2 | Mid | Kent | 4 | 2026-01-19 | 2026-01-23 | 4 | Not Started
Sprint 6 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Testing | Upload Domestic Dividend Composition Info to EC QA - unit testing | Low | BA/Testing | 1 | 2026-01-26 | 2026-01-26 | 1 | Not Started
Sprint 1 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | Mid | BA/Testing | 3 | 2026-01-13 | 2026-01-15 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | Mid | BA/Testing | 3 | 2026-01-16 | 2026-01-20 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Mid | New AP Lead | 4 | 2026-01-21 | 2026-01-26 | 4 | Not Started
Sprint 3 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Mid | New AP Lead | 4 | 2026-01-27 | 2026-01-30 | 4 | Not Started
Sprint 4 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Mid | New AP Lead | 2 | 2026-02-02 | 2026-02-03 | 2 | Not Started
Sprint 5 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Testing | Data Related QA - unit testing | Mid | BA/Testing | 3 | 2026-02-04 | 2026-02-06 | 3 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement Analysis | High | BA/Testing | 2 | 2026-01-21 | 2026-01-22 | 2 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement | Low | BA/Testing | 2 | 2026-01-23 | 2026-01-23 | 1 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 1 | Mid | FrontEnd | 2 | 2026-01-27 | 2026-01-28 | 2 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 2 | High | New AP Lead | 8 | 2026-02-04 | 2026-02-13 | 8 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Testing | Mandate Client Information Maintenance QA - unit-testing | Low | BA/Testing | 2 | 2026-02-23 | 2026-02-24 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement Analysis | Low | BA/Testing | 2 | 2026-01-27 | 2026-01-28 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement | Low | BA/Testing | 2 | 2026-01-29 | 2026-01-30 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 1 | Low | FrontEnd | 2 | 2026-02-02 | 2026-02-03 | 2 | Not Started
Sprint 7 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 2 | High | Kent | 8 | 2026-02-02 | 2026-02-11 | 8 | Not Started
Sprint 8 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Testing | Mandate Contract Information Maintenance QA - unit-testing | Mid | BA/Testing | 2 | 2026-02-25 | 2026-02-26 | 2 | Not Started
Sprint 6 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Analysis | Mid | BA/Testing | 2 | 2026-02-02 | 2026-02-03 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Doc | Mid | BA/Testing | 2 | 2026-02-09 | 2026-02-10 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 1 | High | FrontEnd | 2 | 2026-02-11 | 2026-02-12 | 2 | Not Started
Sprint 8 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 2 | Low | New AP Lead | 8 | 2026-02-23 | 2026-03-04 | 8 | Not Started
Sprint 9 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Testing | Mandate Subscription Data Entry QA - unit-testing | Mid | BA/Testing | 2 | 2026-03-05 | 2026-03-06 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Analysis | Low | BA/Testing | 1 | 2026-02-27 | 2026-02-27 | 1 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Doc | Low | BA/Testing | 2 | 2026-03-02 | 2026-03-03 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 1 | Low | FrontEnd | 1 | 2026-03-04 | 2026-03-04 | 1 | Not Started
Sprint 10 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 2 | Mid | Kent | 3 | 2026-03-05 | 2026-03-09 | 3 | Not Started
Sprint 11 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Testing | Mandate Redemption Data Entry QA - unit-testing | Low | BA/Testing | 2 | 2026-03-10 | 2026-03-11 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | Low | BA/Testing | 1 | 2026-03-04 | 2026-03-04 | 1 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | Mid | BA/Testing | 2 | 2026-03-09 | 2026-03-10 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | Mid | FrontEnd | 2 | 2026-03-11 | 2026-03-12 | 2 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Mid | New AP Lead | 2 | 2026-03-11 | 2026-03-12 | 2 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Testing | Mandate Fund NAV Inquiry QA - unit-testing | High | BA/Testing | 2 | 2026-03-13 | 2026-03-16 | 2 | Not Started
Sprint 12 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | Low | BA/Testing | 1 | 2026-03-11 | 2026-03-11 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | Mid | BA/Testing | 1 | 2026-03-12 | 2026-03-12 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | Low | FrontEnd | 1 | 2026-03-17 | 2026-03-17 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Mid | Kent | 3 | 2026-03-17 | 2026-03-19 | 3 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Testing | Mandate Fund NAV Inquiry QA - unit-testing | Low | BA/Testing | 1 | 2026-03-20 | 2026-03-20 | 1 | Not Started
Sprint 5 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement Analysis | Low | BA/Testing | 1 | 2026-03-17 | 2026-03-17 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement | Low | BA/Testing | 1 | 2026-03-18 | 2026-03-18 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 1 | Low | FrontEnd | 1 | 2026-03-23 | 2026-03-23 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 2 | Mid | New AP Lead | 2 | 2026-03-23 | 2026-03-24 | 2 | Not Started
Sprint 7 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Testing | Subscription Details Report QA - unit-testing | Mid | BA/Testing | 1 | 2026-03-25 | 2026-03-25 | 1 | Not Started
Sprint 7 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement Analysis | Mid | BA/Testing | 2 | 2026-03-23 | 2026-03-24 | 2 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement | High | BA/Testing | 2 | 2026-03-26 | 2026-03-27 | 2 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 1 | Low | FrontEnd | 3 | 2026-03-30 | 2026-04-01 | 3 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 2 | Mid | New AP Lead | 5 | 2026-03-30 | 2026-04-07 | 5 | Not Started
Sprint 9 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Testing | Redemption Details Report QA - unit-testing | Low | BA/Testing | 1 | 2026-04-08 | 2026-04-08 | 1 | Not Started
Sprint 9 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement Analysis | Low | BA/Testing | 1 | 2026-03-30 | 2026-03-30 | 1 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement | Low | BA/Testing | 2 | 2026-03-31 | 2026-04-01 | 2 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 1 | Low | FrontEnd | 2 | 2026-04-02 | 2026-04-07 | 2 | Not Started
Sprint 11 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 2 | Mid | New AP Lead | 4 | 2026-04-08 | 2026-04-13 | 4 | Not Started
Sprint 12 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Testing | Mandate NAV Import Process (State Street) QA - unit-testing | Low | BA/Testing | 2 | 2026-04-14 | 2026-04-15 | 2 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement Analysis | Mid | BA/Testing | 1 | 2026-04-02 | 2026-04-02 | 1 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement | Mid | BA/Testing | 1 | 2026-04-09 | 2026-04-09 | 1 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 1 | Mid | FrontEnd | 2 | 2026-04-10 | 2026-04-13 | 2 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 2 | High | New AP Lead | 3 | 2026-04-14 | 2026-04-16 | 3 | Not Started
Sprint 14 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Testing | Generate Mandate Subscription/Redemption Data QA - unit-testing | Low | BA/Testing | 1 | 2026-04-17 | 2026-04-17 | 1 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement Analysis | Mid | BA/Testing | 2 | 2026-04-10 | 2026-04-13 | 2 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement | Low | BA/Testing | 2 | 2026-04-20 | 2026-04-21 | 2 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 1 | Low | FrontEnd | 2 | 2026-04-22 | 2026-04-23 | 2 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 2 | Mid | New AP Lead | 5 | 2026-04-22 | 2026-04-28 | 5 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Testing | Export Mandate Subscription/Redemption Data QA - unit-testing | Low | BA/Testing | 2 | 2026-04-29 | 2026-04-30 | 2 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement Analysis | Low | BA/Testing | 1 | 2026-04-22 | 2026-04-22 | 1 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement | Low | BA/Testing | 1 | 2026-04-23 | 2026-04-23 | 1 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 1 | Mid | FrontEnd | 2 | 2026-04-24 | 2026-04-27 | 2 | Not Started
Sprint 18 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 2 | Mid | New AP Lead | 3 | 2026-04-29 | 2026-05-04 | 3 | Not Started
Sprint 19 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Testing | Generate SSB Mandate Subscription/Redemption Data QA - unit-testing | Mid | BA/Testing | 1 | 2026-05-05 | 2026-05-05 | 1 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement Analysis | High | BA/Testing | 2 | 2026-04-24 | 2026-04-27 | 2 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement | Low | BA/Testing | 2 | 2026-04-28 | 2026-05-04 | 2 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 1 | Mid | FrontEnd | 3 | 2026-05-05 | 2026-05-07 | 3 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 2 | Mid | New AP Lead | 5 | 2026-05-05 | 2026-05-11 | 5 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Testing | Export SSB Mandate Subscription/Redemption Data QA - unit-testing | Low | BA/Testing | 1 | 2026-05-12 | 2026-05-12 | 1 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Requirement Analysis | Low | BA/Testing | 1 | 2026-05-06 | 2026-05-06 | 1 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Data Requirement | Low | BA/Testing | 2 | 2026-05-07 | 2026-05-08 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 1 | Low | FrontEnd | 2 | 2026-05-11 | 2026-05-12 | 2 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 2 | Mid | Kent | 3 | 2026-05-12 | 2026-05-14 | 3 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Testing | Fund NAV Auto Import Process QA - unit-testing | Mid | BA/Testing | 1 | 2026-05-15 | 2026-05-15 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Requirement Analysis | Mid | BA/Testing | 1 | 2026-05-11 | 2026-05-11 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Data Requirement | Mid | BA/Testing | 1 | 2026-05-13 | 2026-05-13 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 1 | High | FrontEnd | 2 | 2026-05-14 | 2026-05-15 | 2 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 2 | Low | Kent | 2 | 2026-05-15 | 2026-05-18 | 2 | Not Started
Sprint 17 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Testing | Fund NAV Import Status Inquiry QA - unit-testing | Mid | BA/Testing | 1 | 2026-05-19 | 2026-05-19 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement Analysis | Low | BA/Testing | 1 | 2026-05-18 | 2026-05-18 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement | Low | BA/Testing | 2 | 2026-05-20 | 2026-05-21 | 2 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 1 | Low | FrontEnd | 1 | 2026-05-22 | 2026-05-22 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 2 | Low | Kent | 2 | 2026-05-22 | 2026-05-25 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Testing | Calendar File QA - unit-testing | Low | BA/Testing | 1 | 2026-05-26 | 2026-05-26 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement Analysis | Low | BA/Testing | 2 | 2026-05-22 | 2026-05-25 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement | Mid | BA/Testing | 2 | 2026-05-27 | 2026-05-28 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 1 | Mid | FrontEnd | 2 | 2026-05-29 | 2026-06-01 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 2 | Mid | Kent | 2 | 2026-05-29 | 2026-06-01 | 2 | Not Started
Sprint 19 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Testing | Payment Notice – Management Fee, Custody Fee QA - unit-testing | High | BA/Testing | 1 | 2026-06-02 | 2026-06-02 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement Analysis | Low | BA/Testing | 1 | 2026-05-29 | 2026-05-29 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement | Mid | BA/Testing | 1 | 2026-06-01 | 2026-06-01 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 1 | Low | FrontEnd | 1 | 2026-06-02 | 2026-06-02 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 2 | Low | Kent | 2 | 2026-06-02 | 2026-06-03 | 2 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Testing | Validation – Dividend Data QA - unit-testing | Low | BA/Testing | 1 | 2026-06-04 | 2026-06-04 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement Analysis | Low | BA/Testing | 1 | 2026-06-03 | 2026-06-03 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement | Low | BA/Testing | 1 | 2026-06-05 | 2026-06-05 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 1 | Low | FrontEnd | 1 | 2026-06-08 | 2026-06-08 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 2 | Mid | Kent | 2 | 2026-06-08 | 2026-06-09 | 2 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Testing | Payment Notice – Dividend Distribution QA - unit-testing | Mid | BA/Testing | 1 | 2026-06-10 | 2026-06-10 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement Analysis | Mid | BA/Testing | 1 | 2026-06-08 | 2026-06-08 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement | High | BA/Testing | 1 | 2026-06-09 | 2026-06-09 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 1 | Low | FrontEnd | 1 | 2026-06-10 | 2026-06-10 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 2 | Mid | Kent | 2 | 2026-06-10 | 2026-06-11 | 2 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Testing | Payment Notice – Dividend Instruction Printing QA - unit-testing | Low | BA/Testing | 1 | 2026-06-12 | 2026-06-12 | 1 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Analysis | Low | BA/Testing | 1 | 2026-06-11 | 2026-06-11 | 1 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Doc | Low | BA/Testing | 1 | 2026-06-15 | 2026-06-15 | 1 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 1 | Mid | FrontEnd | 4 | 2026-06-16 | 2026-06-19 | 4 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 2 | Mid | New AP Lead | 4 | 2026-06-16 | 2026-06-22 | 4 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Testing | Mandate Data Generation Process QA - unit-testing | Low | BA/Testing | 2 | 2026-06-23 | 2026-06-24 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Analysis | Mid | BA/Testing | 2 | 2026-06-16 | 2026-06-18 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Doc | Mid | BA/Testing | 2 | 2026-06-25 | 2026-06-26 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 1 | Mid | FrontEnd | 3 | 2026-06-29 | 2026-07-01 | 3 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 2 | High | Kent | 5 | 2026-06-29 | 2026-07-03 | 5 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Testing | Mandate Data Maintenance Process QA - unit-testing | Low | BA/Testing | 2 | 2026-07-06 | 2026-07-07 | 2 | Not Started
Sprint 11 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Analysis | Mid | BA/Testing | 1 | 2026-06-29 | 2026-06-29 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Doc | Low | BA/Testing | 1 | 2026-06-30 | 2026-06-30 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 1 | Low | FrontEnd | 1 | 2026-07-01 | 2026-07-01 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 2 | Low | New AP Lead | 2 | 2026-07-01 | 2026-07-02 | 2 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Testing | Subscription/Redemption Posting Details Report QA - unit-testing | Low | BA/Testing | 1 | 2026-07-08 | 2026-07-08 | 1 | Not Started
Sprint 12 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Analysis | Low | BA/Testing | 1 | 2026-07-09 | 2026-07-09 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Doc | Low | BA/Testing | 1 | 2026-07-10 | 2026-07-10 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 1 | Mid | FrontEnd | 3 | 2026-07-13 | 2026-07-15 | 3 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 2 | Mid | New AP Lead | 4 | 2026-07-13 | 2026-07-16 | 4 | Not Started
Sprint 14 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Testing | Mandate Contract Asset Movement Report QA - unit-testing | Mid | BA/Testing | 2 | 2026-07-17 | 2026-07-20 | 2 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Analysis | High | BA/Testing | 1 | 2026-07-13 | 2026-07-13 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Doc | Low | BA/Testing | 1 | 2026-07-14 | 2026-07-14 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 1 | Mid | FrontEnd | 2 | 2026-07-15 | 2026-07-16 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 2 | Low | Kent | 2 | 2026-07-17 | 2026-07-20 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Testing | PAMS Inventory File Export QA - unit-testing | Low | BA/Testing | 1 | 2026-07-21 | 2026-07-21 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement Analysis | Low | BA/Testing | 1 | 2026-07-15 | 2026-07-15 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement | Low | BA/Testing | 1 | 2026-07-22 | 2026-07-22 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 1 | Low | FrontEnd | 1 | 2026-07-23 | 2026-07-23 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 2 | Mid | New AP Lead | 4 | 2026-07-23 | 2026-07-28 | 4 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Testing | Mandate Stock Stop-Loss Control Table QA - unit-testing | Mid | BA/Testing | 1 | 2026-07-29 | 2026-07-29 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Analysis | Mid | BA/Testing | 1 | 2026-07-23 | 2026-07-23 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Doc | Mid | BA/Testing | 1 | 2026-07-24 | 2026-07-24 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | Development | Report - 基金規模報表查詢 - Development | High | Kent | 3 | 2026-07-27 | 2026-07-29 | 3 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | Testing | Report - 基金規模報表查詢 QA - unit-testing | Low | BA/Testing | 1 | 2026-07-30 | 2026-07-30 | 1 | Not Started
Sprint 22 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Analysis | Mid | BA/Testing | 1 | 2026-07-31 | 2026-07-31 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Doc | Low | BA/Testing | 1 | 2026-08-03 | 2026-08-03 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | Development | Taiwan Ratings Reporting Data - Development | Mid | Kent | 3 | 2026-08-04 | 2026-08-06 | 3 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | Testing | Taiwan Ratings Reporting Data QA - unit-testing | Low | BA/Testing | 1 | 2026-08-07 | 2026-08-07 | 1 | Not Started
Sprint 23 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Analysis | Low | BA/Testing | 1 | 2026-08-10 | 2026-08-10 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Doc | Low | BA/Testing | 1 | 2026-08-11 | 2026-08-11 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | Development | Mutual Fund Asset Size Export Process - Development | Mid | New AP Lead | 3 | 2026-08-12 | 2026-08-14 | 3 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | Testing | Mutual Fund Asset Size Export Process - unit-testing | Low | BA/Testing | 1 | 2026-08-17 | 2026-08-17 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement Analysis | Low | BA/Testing | 1 | 2027-03-01 | 2027-03-01 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement | Low | BA/Testing | 1 | 2027-03-02 | 2027-03-02 | 1 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 1 | Mid | FrontEnd | 3 | 2027-03-03 | 2027-03-05 | 3 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 2 | Mid | Kent | 4 | 2027-03-03 | 2027-03-08 | 4 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Testing | Generate Shareholder Meeting Data QA - unit-testing | Low | BA/Testing | 2 | 2027-03-09 | 2027-03-10 | 2 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement Analysis | Low | BA/Testing | 1 | 2027-03-01 | 2027-03-01 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement | Low | BA/Testing | 1 | 2027-03-02 | 2027-03-02 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 1 | Low | FrontEnd | 2 | 2027-03-03 | 2027-03-04 | 2 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 2 | Mid | New AP Lead | 5 | 2027-03-03 | 2027-03-09 | 5 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Testing | Generate Memo for Assigned Personnel/Function QA - unit-testing | Low | BA/Testing | 1 | 2027-03-10 | 2027-03-10 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement Analysis | Low | BA/Testing | 1 | 2027-03-05 | 2027-03-05 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement | Low | BA/Testing | 1 | 2027-03-08 | 2027-03-08 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 1 | Low | FrontEnd | 2 | 2027-03-09 | 2027-03-10 | 2 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 2 | Mid | Kent | 5 | 2027-03-09 | 2027-03-15 | 5 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Testing | Director/Supervisor Election Report/Function QA - unit-testing | Low | BA/Testing | 1 | 2027-03-16 | 2027-03-16 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement Analysis | Low | BA/Testing | 1 | 2027-03-11 | 2027-03-11 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement | Low | BA/Testing | 1 | 2027-03-12 | 2027-03-12 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 1 | Low | FrontEnd | 1 | 2027-03-15 | 2027-03-15 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 2 | Low | New AP Lead | 2 | 2027-03-15 | 2027-03-16 | 2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Testing | Shareholder Meeting Fund Attendance Details Report QA - unit-testing | Low | BA/Testing | 1 | 2027-03-17 | 2027-03-17 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Requirement Analysis | Low | BA/Testing | 1 | 2027-03-15 | 2027-03-15 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Report Requirement | Low | BA/Testing | 1 | 2027-03-16 | 2027-03-16 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details Report - Development 1 | Low | FrontEnd | 1 | 2027-03-17 | 2027-03-17 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details - Development 2 | Low | Kent | 2 | 2027-03-17 | 2027-03-18 | 2 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Testing | Shareholder Meeting Missing Election Report Details QA - unit-testing | Low | BA/Testing | 1 | 2027-03-19 | 2027-03-19 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement Analysis | Low | BA/Testing | 1 | 2027-03-17 | 2027-03-17 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement | Low | BA/Testing | 1 | 2027-03-18 | 2027-03-18 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 1 | Low | FrontEnd | 2 | 2027-03-19 | 2027-03-22 | 2 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 2 | Mid | Kent | 5 | 2027-03-19 | 2027-03-25 | 5 | Not Started
Sprint 30 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Testing | Stock Basic Data Maintenance QA - unit-testing | Low | BA/Testing | 1 | 2027-03-26 | 2027-03-26 | 1 | Not Started
Sprint30 | Shareholders' Meeting & Management | Pararell Run | All |  |  | New AP Lead |  | 2027-03-29 | 2027-04-30 |  | Not Started
Formulas:
FINISH = WORKDAY([START],[DURATION])
START = WORKDAY([FINISH, row above],1)

## Not in Scope
DMS Development
| TOTAL TASKS | 25 |  |  | DURATION |  |  | Overall Progress |  |  | Team Member | FTE
| Completed | 0 |  |  | START | [5 empty] | Patrick | 0.5
| In progress | 0 |  |  | FINISH | [5 empty] | Kent | 1
| Not Started | 25 | [8 empty] | Richard | 0.5
[8 empty] | 100% |  |  | AP Lead | 1
SPRINT | EPIC | FEATURE | TASKS | STORIES | RESPONSIBLE | Man Day Required | START | FINISH | DURATION | STATUS
| Mandate | Last 10 Years Fund Distribution Amounts | BA | Last 10 Years Fund Distribution Amounts Requirement Analysis | Kent | 1 | #REF! | #REF! | 1 | Not Started
| Mandate | Last 10 Years Fund Distribution Amounts | BA | Last 10 Years Fund Distribution Amounts Data Requirement | Kent | 2 | #REF! | #REF! | 2 | Not Started
| Mandate | Last 10 Years Fund Distribution Amounts | Development | Last 10 Years Fund Distribution Amounts - Development 1 | Kent | 1.5 | #REF! | #REF! | 1.5 | Not Started
| Mandate | Last 10 Years Fund Distribution Amounts | Development | Last 10 Years Fund Distribution Amounts - Development 2 | Kent | 1.5 | #REF! | #REF! | 1.5 | Not Started
| Mandate | Last 10 Years Fund Distribution Amounts | QA | Last 10 Years Fund Distribution Amounts QA - unit-testing | Kent | 1 | #REF! | #REF! | 1 | Not Started
| Mandate | FND Monthly Report (Electronic File) | BA | FND Monthly Report (Electronic File) Requirement Analysis | Kent | 1.5 | #REF! | #REF! | 1.5 | Not Started
| Mandate | FND Monthly Report (Electronic File) | BA | FND Monthly Report (Electronic File) Requirement | Kent | 1.5 | #REF! | #REF! | 1.5 | Not Started
| Mandate | FND Monthly Report (Electronic File) | Development | FND Monthly Report (Electronic File) - Development 1 | Kent | 2 | #REF! | #REF! | 2 | Not Started
| Mandate | FND Monthly Report (Electronic File) | Development | FND Monthly Report (Electronic File) - Development 2 | Kent | 2 | #REF! | #REF! | 2 | Not Started
| Mandate | FND Monthly Report (Electronic File) | QA | FND Monthly Report (Electronic File) QA - unit-testing | Kent | 1 | #REF! | #REF! | 1 | Not Started
| Mandate | Payment Notice for Aladdin – Sales Fee File | BA | Payment Notice for Aladdin – Sales Fee File Requirement Analysis | Kent | 1 | #REF! | #REF! | 1 | Not Started
| Mandate | Payment Notice for Aladdin – Sales Fee File | BA | Payment Notice for Aladdin – Sales Fee File Requirement | Kent | 1 | #REF! | #REF! | 1 | Not Started
| Mandate | Payment Notice for Aladdin – Sales Fee File | Development | Payment Notice for Aladdin – Sales Fee File - Development 1 | Kent | 1 | #REF! | #REF! | 1 | Not Started
| Mandate | Payment Notice for Aladdin – Sales Fee File | Development | Payment Notice for Aladdin – Sales Fee File - Development 2 | Kent | 2 | #REF! | #REF! | 2 | Not Started
| Mandate | Payment Notice for Aladdin – Sales Fee File | QA | Payment Notice for Aladdin – Sales Fee File QA - unit-testing | Kent | 1 | #REF! | #REF! | 1 | Not Started
| Mandate | Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement Analysis | Kent | 1.5 | #REF! | #REF! | 1.5 | Not Started
| Mandate | Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement | Kent | 1.5 | #REF! | #REF! | 1.5 | Not Started
| Mandate | Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 1 | Kent | 1.5 | #REF! | #REF! | 1.5 | Not Started
| Mandate | Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 2 | Kent | 2.5 | #REF! | #REF! | 2.5 | Not Started
| Mandate | Payment Notice – Dividend Distribution | QA | Payment Notice – Dividend Distribution QA - unit-testing | Kent | 1 | #REF! | #REF! | 1 | Not Started
| Mandate | Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement Analysis | Kent | 1 | #REF! | #REF! | 1 | Not Started
| Mandate | Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement | Kent | 1 | #REF! | #REF! | 1 | Not Started
| Mandate | Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 1 | Kent | 1 | #REF! | #REF! | 1 | Not Started
| Mandate | Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 2 | Kent | 3 | #REF! | #REF! | 3 | Not Started
| Mandate | Payment Notice – Dividend Instruction Printing | QA | Payment Notice – Dividend Instruction Printing QA - unit-testing | Kent | 1 | #REF! | #REF! | 1 | Not Started
Formulas:
FINISH = WORKDAY([START],[DURATION])