## Project Planning - B
DMS Development
| TOTAL TASKS | 229 |  |  |  | DURATION | 593 |  | Overall Progress
| Completed | 0 |  |  |  | START | 2025-09-15 |  |  |  | 24 | Team Member | FTE | Cost / Monthly |  | Difficulty Level | MD
| In progress | 9 |  |  |  | FINISH | 2027-04-30 |  |  |  | 414 | Kent | 1 |  | 1 year | Low | 1-2
| Not Started | 221 | [9 empty] | BA/Testing | 1 | 152250 | 1827000 | Mid | 3-5
|  |  | New SA and Engineer training |  |  |  | 1/5/2026 - 1/9/2026 |  | 100% |  |  | AP Lead | 1 |  | Onboard after Chinese New Year | High | 6-8
[12 empty] | FrontEnd1 | 1 | 152250 | 1827000
[12 empty] | Patrick-BA | 0.5
SPRINT | EPIC | FEATURE | TASKS | STORIES | Difficulty Level | RESPONSIBLE | Man Day Required | START | FINISH | DURATION | STATUS
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | Mid | BA/Testing | 3 | 2025-09-15 | 2025-09-18 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | Mid | BA/Testing | 3 | 2025-09-19 | 2025-09-24 | 3 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Mid | Kent | 5 | 2025-09-25 | 2025-10-02 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Mid | Kent | 5 | 2025-10-03 | 2025-10-10 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Mid | Kent | 5 | 2025-10-13 | 2025-10-20 | 5 | Completed
Sprint 0 | Shareholders' Meeting & Management | Data Mapping, Data Migration & Create Tables in DB | Testing | Data Related QA - unit testing | Mid | BA/Testing | 3 | 2025-10-21 | 2025-10-24 | 3 | Completed
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Detail Requirement Analysis | Mid | Patrick -BA | 3 | 2025-11-24 | 2025-12-02 | 6 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | BA | Data Related Document Detail Requirement | Mid | Patrick -BA | 3 | 2025-12-03 | 2025-12-11 | 6 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Mid | Kent | 3 | 2025-12-12 | 2025-12-17 | 3 | In progress
Sprint 1 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | High | Kent | 5 | 2025-12-18 | 2025-12-25 | 5 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Low | Kent | 2 | 2025-12-26 | 2025-12-30 | 2 | Not Started
Sprint 2 | Dividend Distribution | Data Mapping, Data Migration & Create Tables in DB | Testing | Data Related QA - unit testing | Mid | BA/Testing | 3 | 2025-12-31 | 2026-01-05 | 3 | Not Started
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Balance Detail Requirement Analysis | Low | Patrick -BA | 1.5 | 2025-12-12 | 2025-12-17 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | BA | Maintain Distributable Document Detail Requirement | Low | Patrick -BA | 1.5 | 2025-12-18 | 2025-12-23 | 3 | In progress
Sprint 2 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 1 | Low | FrontEnd | 1 | 2025-12-24 | 2025-12-25 | 1 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Development | Maintain Distributable Balance - Development 2 | High | Kent | 7 | 2025-12-31 | 2026-01-09 | 7 | Not Started
Sprint 3 | Dividend Distribution | Maintain Distributable Balance 可分配餘額維護作業 | Testing | Maintain Distributable Balance QA - unit testing | Mid | BA/Testing | 3 | 2026-01-12 | 2026-01-15 | 3 | Not Started
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Detail Requirement Analysis | Low | Patrick -BA | 1.5 | 2025-12-24 | 2025-12-29 | 3 | In progress
Sprint 3 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | BA | Domestic Dividend Information Inquiry Document Detail Requirement | Mid | Patrick -BA | 1.5 | 2025-12-26 | 2025-12-31 | 3 | In progress
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 1 | Mid | FrontEnd | 4 | 2026-01-01 | 2026-01-07 | 4 | Not Started
Sprint 4 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Development | Domestic Dividend Information Inquiry - Development 2 | Mid | Kent | 4 | 2026-01-12 | 2026-01-16 | 4 | Not Started
Sprint 5 | Dividend Distribution | Domestic Dividend Information Inquiry 境內配息資訊查詢作業 | Testing | Domestic Dividend Information Inquiry QA - unit testing | High | BA/Testing | 2 | 2026-01-19 | 2026-01-21 | 2 | Not Started
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Detail Requirement Analysis | Low | Patrick -BA | 1.5 | 2026-01-01 | 2026-01-06 | 3 | In progress
Sprint 3 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | BA | Upload Domestic Dividend Composition Info to EC - Document Detail Requirement | Mid | Patrick -BA | 1.5 | 2026-01-07 | 2026-01-12 | 3 | In progress
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 1 | Mid | FrontEnd | 4 | 2026-01-08 | 2026-01-14 | 4 | Not Started
Sprint 5 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Development | Upload Domestic Dividend Composition Info to EC - Development 2 | Mid | Kent | 4 | 2026-01-19 | 2026-01-23 | 4 | Not Started
Sprint 6 | Dividend Distribution | Upload Domestic Dividend Composition Info to EC 境內配息組成資訊上傳EC | Testing | Upload Domestic Dividend Composition Info to EC QA - unit testing | Low | BA/Testing | 1 | 2026-01-26 | 2026-01-26 | 1 | Not Started
Sprint 1 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement Analysis | Mid | BA/Testing | 3 | 2026-01-13 | 2026-01-15 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | BA | Data Mapping, Data Migration & Create Tables in DB Requirement | Mid | BA/Testing | 3 | 2026-01-16 | 2026-01-20 | 3 | Not Started
Sprint 2 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Mapping - Development | Mid | New AP Lead | 4 | 2026-01-21 | 2026-01-26 | 4 | Not Started
Sprint 3 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Data Migration - Development | Mid | New AP Lead | 4 | 2026-01-27 | 2026-01-30 | 4 | Not Started
Sprint 4 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Development | Create Tables in DB - Development | Mid | New AP Lead | 2 | 2026-02-02 | 2026-02-03 | 2 | Not Started
Sprint 5 | Mandate | Data Mapping, Data Migration & Create Tables in DB | Testing | Data Related QA - unit testing | Mid | BA/Testing | 3 | 2026-02-04 | 2026-02-06 | 3 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement Analysis | High | BA/Testing | 2 | 2026-01-21 | 2026-01-22 | 2 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | BA | Mandate Client Information Maintenance Requirement | Low | BA/Testing | 2 | 2026-01-23 | 2026-01-23 | 1 | Not Started
Sprint 4 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 1 | Mid | FrontEnd | 2 | 2026-01-27 | 2026-01-28 | 2 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Development | Mandate Client Information Maintenance - Development 2 | High | New AP Lead | 8 | 2026-02-04 | 2026-02-13 | 8 | Not Started
Sprint 5 | Mandate | FAS 8111 Mandate Client Information Maintenance 全委委託人資料維護 | Testing | Mandate Client Information Maintenance QA - unit-testing | Low | BA/Testing | 2 | 2026-02-23 | 2026-02-24 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement Analysis | Low | BA/Testing | 2 | 2026-01-27 | 2026-01-28 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | BA | Mandate Contract Information Maintenance Requirement | Low | BA/Testing | 2 | 2026-01-29 | 2026-01-30 | 2 | Not Started
Sprint 6 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 1 | Low | FrontEnd | 2 | 2026-02-02 | 2026-02-03 | 2 | Not Started
Sprint 7 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Development | Mandate Contract Information Maintenance - Development 2 | High | Kent | 8 | 2026-02-02 | 2026-02-11 | 8 | Not Started
Sprint 8 | Mandate | FAS 8112 Mandate Contract Information Maintenance 全委契約資料維護 | Testing | Mandate Contract Information Maintenance QA - unit-testing | Mid | BA/Testing | 2 | 2026-02-25 | 2026-02-26 | 2 | Not Started
Sprint 6 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Analysis | Mid | BA/Testing | 2 | 2026-02-02 | 2026-02-03 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | BA | Mandate Subscription Data Entry Requirement Doc | Mid | BA/Testing | 2 | 2026-02-09 | 2026-02-10 | 2 | Not Started
Sprint 7 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 1 | High | FrontEnd | 2 | 2026-02-11 | 2026-02-12 | 2 | Not Started
Sprint 8 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Development | Mandate Subscription Data Entry - Development 2 | Low | New AP Lead | 8 | 2026-02-23 | 2026-03-04 | 8 | Not Started
Sprint 9 | Mandate | FAS 8121 Mandate Subscription Data Entry 全委申購資料登錄 | Testing | Mandate Subscription Data Entry QA - unit-testing | Mid | BA/Testing | 2 | 2026-03-05 | 2026-03-06 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Analysis | Low | BA/Testing | 1 | 2026-02-27 | 2026-02-27 | 1 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | BA | Mandate Redemption Data Entry Requirement Doc | Low | BA/Testing | 2 | 2026-03-02 | 2026-03-03 | 2 | Not Started
Sprint 9 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 1 | Low | FrontEnd | 1 | 2026-03-04 | 2026-03-04 | 1 | Not Started
Sprint 10 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Development | Mandate Redemption Data Entry - Development 2 | Mid | Kent | 3 | 2026-03-05 | 2026-03-09 | 3 | Not Started
Sprint 11 | Mandate | FAS 8122 Mandate Redemption Data Entry 全委買回資料登錄 | Testing | Mandate Redemption Data Entry QA - unit-testing | Low | BA/Testing | 2 | 2026-03-10 | 2026-03-11 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | Low | BA/Testing | 1 | 2026-03-04 | 2026-03-04 | 1 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | Mid | BA/Testing | 2 | 2026-03-09 | 2026-03-10 | 2 | Not Started
Sprint 11 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | Mid | FrontEnd | 2 | 2026-03-11 | 2026-03-12 | 2 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Mid | New AP Lead | 2 | 2026-03-11 | 2026-03-12 | 2 | Not Started
Sprint 12 | Mandate | FAS 8151 Mandate Fund NAV Inquiry 全委基金淨值查詢 | Testing | Mandate Fund NAV Inquiry QA - unit-testing | High | BA/Testing | 2 | 2026-03-13 | 2026-03-16 | 2 | Not Started
Sprint 12 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Analysis | Low | BA/Testing | 1 | 2026-03-11 | 2026-03-11 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | BA | Mandate Fund NAV Inquiry Requirement Doc | Mid | BA/Testing | 1 | 2026-03-12 | 2026-03-12 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 1 | Low | FrontEnd | 1 | 2026-03-17 | 2026-03-17 | 1 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Development | Mandate Fund NAV Inquiry - Development 2 | Mid | Kent | 3 | 2026-03-17 | 2026-03-19 | 3 | Not Started
Sprint 13 | Mandate | FAS 8152 Mandate Account Holdings Inquiry 全委帳戶庫存查詢 | Testing | Mandate Fund NAV Inquiry QA - unit-testing | Low | BA/Testing | 1 | 2026-03-20 | 2026-03-20 | 1 | Not Started
Sprint 5 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement Analysis | Low | BA/Testing | 1 | 2026-03-17 | 2026-03-17 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | BA | Subscription Details Report Requirement | Low | BA/Testing | 1 | 2026-03-18 | 2026-03-18 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 1 | Low | FrontEnd | 1 | 2026-03-23 | 2026-03-23 | 1 | Not Started
Sprint 6 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Development | Subscription Details Report - Development 2 | Mid | New AP Lead | 2 | 2026-03-23 | 2026-03-24 | 2 | Not Started
Sprint 7 | Mandate | FAS 81611 Subscription Details Report 申購資料明細表 | Testing | Subscription Details Report QA - unit-testing | Mid | BA/Testing | 1 | 2026-03-25 | 2026-03-25 | 1 | Not Started
Sprint 7 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement Analysis | Mid | BA/Testing | 2 | 2026-03-23 | 2026-03-24 | 2 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | BA | Redemption Details Report Requirement | High | BA/Testing | 2 | 2026-03-26 | 2026-03-27 | 2 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 1 | Low | FrontEnd | 3 | 2026-03-30 | 2026-04-01 | 3 | Not Started
Sprint 8 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Development | Redemption Details Report - Development 2 | Mid | New AP Lead | 5 | 2026-03-30 | 2026-04-07 | 5 | Not Started
Sprint 9 | Mandate | FAS 81621 Redemption Details Report 買回資料明細表 | Testing | Redemption Details Report QA - unit-testing | Low | BA/Testing | 1 | 2026-04-08 | 2026-04-08 | 1 | Not Started
Sprint 9 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement Analysis | Low | BA/Testing | 1 | 2026-03-30 | 2026-03-30 | 1 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | BA | Mandate NAV Import Process (State Street) Requirement | Low | BA/Testing | 2 | 2026-03-31 | 2026-04-01 | 2 | Not Started
Sprint 10 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 1 | Low | FrontEnd | 2 | 2026-04-02 | 2026-04-07 | 2 | Not Started
Sprint 11 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Development | Mandate NAV Import Process (State Street) - Development 2 | Mid | New AP Lead | 4 | 2026-04-08 | 2026-04-13 | 4 | Not Started
Sprint 12 | Mandate | FAS 8171 Mandate NAV Import Process (State Street) 全委淨值匯入作業(道富) | Testing | Mandate NAV Import Process (State Street) QA - unit-testing | Low | BA/Testing | 2 | 2026-04-14 | 2026-04-15 | 2 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement Analysis | Mid | BA/Testing | 1 | 2026-04-02 | 2026-04-02 | 1 | Not Started
Sprint 12 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | BA | Generate Mandate Subscription/Redemption Data Requirement | Mid | BA/Testing | 1 | 2026-04-09 | 2026-04-09 | 1 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 1 | Mid | FrontEnd | 2 | 2026-04-10 | 2026-04-13 | 2 | Not Started
Sprint 13 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Development | Generate Mandate Subscription/Redemption Data - Development 2 | High | New AP Lead | 3 | 2026-04-14 | 2026-04-16 | 3 | Not Started
Sprint 14 | Mandate | FAS 81811 Generate Mandate Subscription/Redemption Data 全委申贖資料產生 | Testing | Generate Mandate Subscription/Redemption Data QA - unit-testing | Low | BA/Testing | 1 | 2026-04-17 | 2026-04-17 | 1 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement Analysis | Mid | BA/Testing | 2 | 2026-04-10 | 2026-04-13 | 2 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | BA | Export Mandate Subscription/Redemption Data Requirement | Low | BA/Testing | 2 | 2026-04-20 | 2026-04-21 | 2 | Not Started
Sprint 15 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 1 | Low | FrontEnd | 2 | 2026-04-22 | 2026-04-23 | 2 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Development | Export Mandate Subscription/Redemption Data - Development 2 | Mid | New AP Lead | 5 | 2026-04-22 | 2026-04-28 | 5 | Not Started
Sprint 16 | Mandate | FAS 81812 Export Mandate Subscription/Redemption Data 全委申贖資料匯出 | Testing | Export Mandate Subscription/Redemption Data QA - unit-testing | Low | BA/Testing | 2 | 2026-04-29 | 2026-04-30 | 2 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement Analysis | Low | BA/Testing | 1 | 2026-04-22 | 2026-04-22 | 1 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | BA | Generate SSB Mandate Subscription/Redemption Data Requirement | Low | BA/Testing | 1 | 2026-04-23 | 2026-04-23 | 1 | Not Started
Sprint 17 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 1 | Mid | FrontEnd | 2 | 2026-04-24 | 2026-04-27 | 2 | Not Started
Sprint 18 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Development | Generate SSB Mandate Subscription/Redemption Data - Development 2 | Mid | New AP Lead | 3 | 2026-04-29 | 2026-05-04 | 3 | Not Started
Sprint 19 | Mandate | FAS 81831 Generate SSB Mandate Subscription/Redemption Data 產生SSB全委申贖資料 | Testing | Generate SSB Mandate Subscription/Redemption Data QA - unit-testing | Mid | BA/Testing | 1 | 2026-05-05 | 2026-05-05 | 1 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement Analysis | High | BA/Testing | 2 | 2026-04-24 | 2026-04-27 | 2 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | BA | Export SSB Mandate Subscription/Redemption Data Requirement | Low | BA/Testing | 2 | 2026-04-28 | 2026-05-04 | 2 | Not Started
Sprint 19 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 1 | Mid | FrontEnd | 3 | 2026-05-05 | 2026-05-07 | 3 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Development | Export SSB Mandate Subscription/Redemption Data - Development 2 | Mid | New AP Lead | 5 | 2026-05-05 | 2026-05-11 | 5 | Not Started
Sprint 20 | Mandate | FAS 81832 Export SSB Mandate Subscription/Redemption Data 匯出SSB全委申贖資料 | Testing | Export SSB Mandate Subscription/Redemption Data QA - unit-testing | Low | BA/Testing | 1 | 2026-05-12 | 2026-05-12 | 1 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Requirement Analysis | Low | BA/Testing | 1 | 2026-05-06 | 2026-05-06 | 1 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | BA | Fund NAV Auto Import Process Data Requirement | Low | BA/Testing | 2 | 2026-05-07 | 2026-05-08 | 2 | Not Started
Sprint 14 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 1 | Low | FrontEnd | 2 | 2026-05-11 | 2026-05-12 | 2 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Development | Fund NAV Auto Import Process Data - Development 2 | Mid | Kent | 3 | 2026-05-12 | 2026-05-14 | 3 | Not Started
Sprint 15 | Mandate | FAS 883 Fund NAV Auto Import Process 基金淨值自動匯入作業 | Testing | Fund NAV Auto Import Process QA - unit-testing | Mid | BA/Testing | 1 | 2026-05-15 | 2026-05-15 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Requirement Analysis | Mid | BA/Testing | 1 | 2026-05-11 | 2026-05-11 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | BA | Fund NAV Import Status Inquiry Data Requirement | Mid | BA/Testing | 1 | 2026-05-13 | 2026-05-13 | 1 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 1 | High | FrontEnd | 2 | 2026-05-14 | 2026-05-15 | 2 | Not Started
Sprint 16 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Development | Fund NAV Import Status Inquiry - Development 2 | Low | Kent | 2 | 2026-05-15 | 2026-05-18 | 2 | Not Started
Sprint 17 | Mandate | FAS 884 Fund NAV Import Status Inquiry 基金淨值匯入狀況查詢 | Testing | Fund NAV Import Status Inquiry QA - unit-testing | Mid | BA/Testing | 1 | 2026-05-19 | 2026-05-19 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement Analysis | Low | BA/Testing | 1 | 2026-05-18 | 2026-05-18 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | BA | Calendar File Requirement | Low | BA/Testing | 2 | 2026-05-20 | 2026-05-21 | 2 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 1 | Low | FrontEnd | 1 | 2026-05-22 | 2026-05-22 | 1 | Not Started
Sprint 17 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Development | Calendar File - Development 2 | Low | Kent | 2 | 2026-05-22 | 2026-05-25 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Calendar File - Mandate 全委日曆檔 | Testing | Calendar File QA - unit-testing | Low | BA/Testing | 1 | 2026-05-26 | 2026-05-26 | 1 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement Analysis | Low | BA/Testing | 2 | 2026-05-22 | 2026-05-25 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | BA | Payment Notice – Management Fee, Custody Fee Requirement | Mid | BA/Testing | 2 | 2026-05-27 | 2026-05-28 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 1 | Mid | FrontEnd | 2 | 2026-05-29 | 2026-06-01 | 2 | Not Started
Sprint 18 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Development | Payment Notice – Management Fee, Custody Fee - Development 2 | Mid | Kent | 2 | 2026-05-29 | 2026-06-01 | 2 | Not Started
Sprint 19 | Mandate | FAS 893 Payment Notice – Management Fee, Custody Fee 付款通知書-經理費、保管費 | Testing | Payment Notice – Management Fee, Custody Fee QA - unit-testing | High | BA/Testing | 1 | 2026-06-02 | 2026-06-02 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement Analysis | Low | BA/Testing | 1 | 2026-05-29 | 2026-05-29 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | BA | Validation – Dividend Data Requirement | Mid | BA/Testing | 1 | 2026-06-01 | 2026-06-01 | 1 | Not Started
Sprint 19 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 1 | Low | FrontEnd | 1 | 2026-06-02 | 2026-06-02 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Development | Validation – Dividend Data - Development 2 | Low | Kent | 2 | 2026-06-02 | 2026-06-03 | 2 | Not Started
Sprint 20 | Mandate | FAS 893 Validation – Dividend Data 檢核-配息資料 | Testing | Validation – Dividend Data QA - unit-testing | Low | BA/Testing | 1 | 2026-06-04 | 2026-06-04 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement Analysis | Low | BA/Testing | 1 | 2026-06-03 | 2026-06-03 | 1 | Not Started
Sprint 20 | Mandate | FAS 893 Payment Notice – Dividend Distribution | BA | Payment Notice – Dividend Distribution Requirement | Low | BA/Testing | 1 | 2026-06-05 | 2026-06-05 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 1 | Low | FrontEnd | 1 | 2026-06-08 | 2026-06-08 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Development | Payment Notice – Dividend Distribution - Development 2 | Mid | Kent | 2 | 2026-06-08 | 2026-06-09 | 2 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Distribution | Testing | Payment Notice – Dividend Distribution QA - unit-testing | Mid | BA/Testing | 1 | 2026-06-10 | 2026-06-10 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement Analysis | Mid | BA/Testing | 1 | 2026-06-08 | 2026-06-08 | 1 | Not Started
Sprint 21 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | BA | Payment Notice – Dividend Instruction Printing Requirement | High | BA/Testing | 1 | 2026-06-09 | 2026-06-09 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 1 | Low | FrontEnd | 1 | 2026-06-10 | 2026-06-10 | 1 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Development | Payment Notice – Dividend Instruction Printing - Development 2 | Mid | Kent | 2 | 2026-06-10 | 2026-06-11 | 2 | Not Started
Sprint 22 | Mandate | FAS 893 Payment Notice – Dividend Instruction Printing | Testing | Payment Notice – Dividend Instruction Printing QA - unit-testing | Low | BA/Testing | 1 | 2026-06-12 | 2026-06-12 | 1 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Analysis | Low | BA/Testing | 1 | 2026-06-11 | 2026-06-11 | 1 | Not Started
Sprint 8 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | BA | Mandate Data Generation Process Requirement Doc | Low | BA/Testing | 1 | 2026-06-15 | 2026-06-15 | 1 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 1 | Mid | FrontEnd | 4 | 2026-06-16 | 2026-06-19 | 4 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Development | Mandate Data Generation Process - Development 2 | Mid | New AP Lead | 4 | 2026-06-16 | 2026-06-22 | 4 | Not Started
Sprint 9 | Mandate | DMS 271 Mandate Data Generation Process 全委資料產生作業 | Testing | Mandate Data Generation Process QA - unit-testing | Low | BA/Testing | 2 | 2026-06-23 | 2026-06-24 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Analysis | Mid | BA/Testing | 2 | 2026-06-16 | 2026-06-18 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | BA | Mandate Data Maintenance Process Requirement Doc | Mid | BA/Testing | 2 | 2026-06-25 | 2026-06-26 | 2 | Not Started
Sprint 10 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 1 | Mid | FrontEnd | 3 | 2026-06-29 | 2026-07-01 | 3 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Development | Mandate Data Maintenance Process - Development 2 | High | Kent | 5 | 2026-06-29 | 2026-07-03 | 5 | Not Started
Sprint 11 | Mandate | DMS 272 Mandate Data Maintenance Process 全委資料維護作業 | Testing | Mandate Data Maintenance Process QA - unit-testing | Low | BA/Testing | 2 | 2026-07-06 | 2026-07-07 | 2 | Not Started
Sprint 11 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Analysis | Mid | BA/Testing | 1 | 2026-06-29 | 2026-06-29 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | BA | Subscription/Redemption Posting Details Report Requirement Doc | Low | BA/Testing | 1 | 2026-06-30 | 2026-06-30 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 1 | Low | FrontEnd | 1 | 2026-07-01 | 2026-07-01 | 1 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Development | Subscription/Redemption Posting Details Report - Development 2 | Low | New AP Lead | 2 | 2026-07-01 | 2026-07-02 | 2 | Not Started
Sprint 12 | Mandate | DMS 593916 Subscription/Redemption Posting Details Report 申購贖回入帳明細表 | Testing | Subscription/Redemption Posting Details Report QA - unit-testing | Low | BA/Testing | 1 | 2026-07-08 | 2026-07-08 | 1 | Not Started
Sprint 12 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Analysis | Low | BA/Testing | 1 | 2026-07-09 | 2026-07-09 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | BA | Mandate Contract Asset Movement Report Requirement Doc | Low | BA/Testing | 1 | 2026-07-10 | 2026-07-10 | 1 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 1 | Mid | FrontEnd | 3 | 2026-07-13 | 2026-07-15 | 3 | Not Started
Sprint 13 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Development | Mandate Contract Asset Movement Report - Development 2 | Mid | New AP Lead | 4 | 2026-07-13 | 2026-07-16 | 4 | Not Started
Sprint 14 | Mandate | DMS 6571B Mandate Contract Asset Movement Report 全委契約資產動動表 | Testing | Mandate Contract Asset Movement Report QA - unit-testing | Mid | BA/Testing | 2 | 2026-07-17 | 2026-07-20 | 2 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Analysis | High | BA/Testing | 1 | 2026-07-13 | 2026-07-13 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | BA | PAMS Inventory File Export Requirement Doc | Low | BA/Testing | 1 | 2026-07-14 | 2026-07-14 | 1 | Not Started
Sprint 14 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 1 | Mid | FrontEnd | 2 | 2026-07-15 | 2026-07-16 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Development | PAMS Inventory File Export - Development 2 | Low | Kent | 2 | 2026-07-17 | 2026-07-20 | 2 | Not Started
Sprint 15 | Mandate | DMS 65731 PAMS Inventory File Export PAMS 庫存檔轉出 | Testing | PAMS Inventory File Export QA - unit-testing | Low | BA/Testing | 1 | 2026-07-21 | 2026-07-21 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement Analysis | Low | BA/Testing | 1 | 2026-07-15 | 2026-07-15 | 1 | Not Started
Sprint 15 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | BA | Mandate Stock Stop-Loss Control Table Requirement | Low | BA/Testing | 1 | 2026-07-22 | 2026-07-22 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 1 | Low | FrontEnd | 1 | 2026-07-23 | 2026-07-23 | 1 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Development | Mandate Stock Stop-Loss Control Table - Development 2 | Mid | New AP Lead | 4 | 2026-07-23 | 2026-07-28 | 4 | Not Started
Sprint 16 | Mandate | DMS 756 Mandate Stock Stop-Loss Control Table 全權委託股票停損控管表 | Testing | Mandate Stock Stop-Loss Control Table QA - unit-testing | Mid | BA/Testing | 1 | 2026-07-29 | 2026-07-29 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Analysis | Mid | BA/Testing | 1 | 2026-07-23 | 2026-07-23 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | BA | Report - 基金規模報表查詢 Requirement Doc | Mid | BA/Testing | 1 | 2026-07-24 | 2026-07-24 | 1 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | Development | Report - 基金規模報表查詢 - Development | High | Kent | 3 | 2026-07-27 | 2026-07-29 | 3 | Not Started
Sprint 17 | Mandate | Report - 基金規模報表查詢 | Testing | Report - 基金規模報表查詢 QA - unit-testing | Low | BA/Testing | 1 | 2026-07-30 | 2026-07-30 | 1 | Not Started
Sprint 22 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Analysis | Mid | BA/Testing | 1 | 2026-07-31 | 2026-07-31 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | BA | Taiwan Ratings Reporting Data Requirement Doc | Low | BA/Testing | 1 | 2026-08-03 | 2026-08-03 | 1 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | Development | Taiwan Ratings Reporting Data - Development | Mid | Kent | 3 | 2026-08-04 | 2026-08-06 | 3 | Not Started
Sprint 23 | Mandate | DMS 744 Taiwan Ratings Reporting Data 中華信評申報資料 | Testing | Taiwan Ratings Reporting Data QA - unit-testing | Low | BA/Testing | 1 | 2026-08-07 | 2026-08-07 | 1 | Not Started
Sprint 23 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Analysis | Low | BA/Testing | 1 | 2026-08-10 | 2026-08-10 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | BA | Mutual Fund Asset Size Export Process Requirement Doc | Low | BA/Testing | 1 | 2026-08-11 | 2026-08-11 | 1 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | Development | Mutual Fund Asset Size Export Process - Development | Mid | New AP Lead | 3 | 2026-08-12 | 2026-08-14 | 3 | Not Started
Sprint 24 | Mandate | DMS 758 Mutual Fund Asset Size Export Process 共同基金資產規模轉出作業 | Testing | Mutual Fund Asset Size Export Process - unit-testing | Mid | BA/Testing | 1 | 2026-08-17 | 2026-08-17 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement Analysis | Mid | BA/Testing | 1 | 2026-08-12 | 2026-08-13 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement | Mid | BA/Testing | 1 | 2026-08-14 | 2026-08-17 | 1 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 1 | High | FrontEnd | 3 | 2026-08-18 | 2026-08-21 | 3 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 2 | Low | Kent | 4 | 2026-08-18 | 2026-08-24 | 4 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Testing | Generate Shareholder Meeting Data QA - unit-testing | Mid | BA/Testing | 2 | 2026-08-25 | 2026-08-27 | 2 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement Analysis | Low | BA/Testing | 1 | 2026-08-18 | 2026-08-19 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement | Low | BA/Testing | 1 | 2026-08-20 | 2026-08-21 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 1 | Low | FrontEnd | 1 | 2026-08-24 | 2026-08-25 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 2 | Mid | New AP Lead | 3 | 2026-08-24 | 2026-08-27 | 3 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Testing | Generate Memo for Assigned Personnel/Function QA - unit-testing | Low | BA/Testing | 1 | 2026-08-28 | 2026-08-31 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement Analysis | Low | BA/Testing | 1 | 2026-08-24 | 2026-08-25 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement | Mid | BA/Testing | 1 | 2026-08-26 | 2026-08-27 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 1 | Mid | FrontEnd | 2 | 2026-08-28 | 2026-09-01 | 2 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 2 | Mid | Kent | 2 | 2026-07-21 | 2026-07-23 | 2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Testing | Director/Supervisor Election Report/Function QA - unit-testing | High | BA/Testing | 1 | 2026-07-24 | 2026-07-27 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement Analysis | Low | BA/Testing | 1 | 2026-08-28 | 2026-08-31 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement | Mid | BA/Testing | 1 | 2026-09-01 | 2026-09-02 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 1 | Low | FrontEnd | 1 | 2026-07-23 | 2026-07-24 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 2 | Low | New AP Lead | 1 | 2026-07-23 | 2026-07-24 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Testing | Shareholder Meeting Fund Attendance Details Report QA - unit-testing | Low | BA/Testing | 1 | 2026-07-27 | 2026-07-28 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Requirement Analysis | Low | BA/Testing | 1 | 2026-09-03 | 2026-09-04 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Report Requirement | Low | BA/Testing | 1 | 2026-09-07 | 2026-09-08 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details Report - Development 1 | Low | FrontEnd | 1 | 2026-09-09 | 2026-09-10 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details - Development 2 | Mid | Kent | 1 | 2026-09-09 | 2026-09-10 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Testing | Shareholder Meeting Missing Election Report Details QA - unit-testing | Mid | BA/Testing | 1 | 2026-09-11 | 2026-09-14 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement Analysis | Mid | BA/Testing | 1 | 2026-09-09 | 2026-09-10 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement | High | BA/Testing | 1 | 2026-09-11 | 2026-09-14 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 1 | Low | FrontEnd | 1.5 | 2026-09-15 | 2026-09-16 | 1.5 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 2 | Mid | Kent | 2.5 | 2026-09-15 | 2026-09-17 | 2.5 | Not Started
Sprint 30 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Testing | Stock Basic Data Maintenance QA - unit-testing | Low | BA/Testing | 1 | 2026-09-18 | 2026-09-21 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement Analysis | Low | BA/Testing | 1 | 2027-03-01 | 2027-03-02 | 1 | Not Started
Sprint 24 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | BA | Generate Shareholder Meeting Data Requirement | Low | BA/Testing | 1 | 2027-03-03 | 2027-03-04 | 1 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 1 | Mid | FrontEnd | 3 | 2027-03-05 | 2027-03-10 | 3 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | Development | Generate Shareholder Meeting Data - Development 2 | Mid | New AP Lead | 4 | 2027-03-05 | 2027-03-11 | 4 | Not Started
Sprint 25 | Shareholders' Meeting & Management | Generate Shareholder Meeting Data | QA | Generate Shareholder Meeting Data QA - unit-testing | Low | New AP Lead | 2 | 2027-03-12 | 2027-03-16 | 2 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement Analysis | Mid | Kent | 1 | 2027-03-01 | 2027-03-02 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | BA | Generate Memo for Assigned Personnel/Function Requirement | Mid | Kent | 1 | 2027-03-03 | 2027-03-04 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 1 | Mid | FrontEnd | 1 | 2027-03-05 | 2027-03-08 | 1 | Not Started
Sprint 26 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | Development | Generate Memo for Assigned Personnel/Function - Development 2 | High | Kent | 3 | 2027-03-05 | 2027-03-10 | 3 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Generate Memo for Assigned Personnel/Function | QA | Generate Memo for Assigned Personnel/Function QA - unit-testing | Low | Kent | 1 | 2027-03-11 | 2027-03-12 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement Analysis | Mid | BA/Testing | 1 | 2027-03-05 | 2027-03-08 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | BA | Director/Supervisor Election Report/Function Requirement | Low | BA/Testing | 1 | 2027-03-09 | 2027-03-10 | 1 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 1 | Low | FrontEnd | 2 | 2027-03-11 | 2027-03-15 | 2 | Not Started
Sprint 27 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | Development | Director/Supervisor Election Report/Function - Development 2 | Low | New AP Lead | 2 | 2027-03-11 | 2027-03-15 | 2 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Director/Supervisor Election Report/Function | QA | Director/Supervisor Election Report/Function QA - unit-testing | Low | New AP Lead | 1 | 2027-03-16 | 2027-03-17 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement Analysis | Low | BA/Testing | 1 | 2027-03-11 | 2027-03-12 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | BA | Shareholder Meeting Fund Attendance Details Report Requirement | Low | BA/Testing | 1 | 2027-03-15 | 2027-03-16 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 1 | Mid | FrontEnd | 1 | 2027-03-17 | 2027-03-18 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | Development | Shareholder Meeting Fund Attendance Details Report - Development 2 | Mid | New AP Lead | 1 | 2027-03-18 | 2027-03-19 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Fund Attendance Details Report | QA | Shareholder Meeting Fund Attendance Details Report QA - unit-testing | Mid | New AP Lead | 1 | 2027-03-22 | 2027-03-23 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Requirement Analysis | High | Kent | 1 | 2027-03-15 | 2027-03-16 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | BA | Shareholder Meeting Missing Election Report Details Report Requirement | Low | Kent | 1 | 2027-03-17 | 2027-03-18 | 1 | Not Started
Sprint 28 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details Report - Development 1 | Mid | FrontEnd | 1 | 2027-03-19 | 2027-03-22 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | Development | Shareholder Meeting Missing Election Report Details - Development 2 | Low | New AP Lead | 1 | 2027-03-19 | 2027-03-22 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Shareholder Meeting Missing Election Report Details | QA | Shareholder Meeting Missing Election Report Details QA - unit-testing | Low | New AP Lead | 1 | 2027-03-23 | 2027-03-24 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement Analysis | Low | BA/Testing | 1 | 2027-03-17 | 2027-03-18 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | BA | Stock Basic Data Maintenance Requirement | Low | BA/Testing | 1 | 2027-03-19 | 2027-03-22 | 1 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 1 | Low | FrontEnd | 2 | 2027-03-23 | 2027-03-25 | 2 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | Development | Stock Basic Data Maintenance - Development 2 | Mid | Kent | 3 | 2027-03-23 | 2027-03-26 | 3 | Not Started
Sprint 29 | Shareholders' Meeting & Management | Stock Basic Data Maintenance | QA | Stock Basic Data Maintenance QA - unit-testing | Mid | Kent | 1 | 2027-03-29 | 2027-03-30 | 1 | Not Started
Sprint30 | Shareholders' Meeting & Management | Pararell Run | All |  | Mid | New AP Lead |  | 2027-03-31 | 2027-04-30 |  | Not Started
Formulas:
FINISH = WORKDAY([START],[DURATION])
START = WORKDAY([FINISH, row above],1)